## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | RP | Provide a view on TNUoS/BNUoS ongoing work relating to constraints (see slide 22, WG1). Including Risk and mitigation and modelling | Ongoing waiting update from Balancing team | WG3 | Closed | WG4
2 | WG1 | RP | Provide view on Electrolysers - Is this within Final Demand? Subject to locational signals? | Ongoing waiting on update from revenue team | WG3 | Closed | WG4
3 | WG1 | LJ | Share Fronteir slides with WG |  | WG2 | Closed | WG2
4 | WG1 | LJ | Provide worked numbers as per slide 29 (WG1) | This will be included in later reports. Still waiting on data from revenue team | WG3 | Closed | WG5
5 | WG1 | LJ and RP | Look at party profiles ahead of next WG | The Proposer and NESO Representative to look at examining different profile shapes of possible customer types. | WG3 | Closed | WG2
6 | WG2 | MC | To gain data from the Revenue team for actual NHH for 4-7pm and NHH for all periods | NESO were requested to provide the data for this action, but it will now use estimated data and go through the methodology. | WG4 | Closed | WG5
7 | WG2 | LJ and RP/ PM | To review 14.16.2 Legal text | The proposer and NESO Representative are reviewing section 14.16.2 of the legal text. This would be closed following workgroup discussions. | WG4 | Closed | WG5
8 | WG3 | LJ | To work through equation for understanding of example for 20 million by the 4 to 7 demands, splitting up into 4 to 7 for peak and year-round using different volume. | The Proposer has worked through the equation of understanding examples for 20 million by the four to seven demands and splitting up into four to seven for peak and year-round using different volumes. | WG4 | Closed | WG7
9 | WG3 | DH | Provide confirmation of the charging year the data was analysed from. | DH confimed that the data given to the Workgroup was from 23. | WG4 | Closed | WG5
10 | WG3 | TP/LJ+C11:H11 | Schedule time for proposer and TP to review document Workgroup Consultation Document | Initial review done. | WG4 | Closed | WG5
11 | WG4 | LJ | The Proposer took an action to add percentage changes into the impact tables showing the impact on bills for better clarity. | All tariffs and customer bill tariff tables were added. | WG5 | Closed | WG8
12 | WG4 | LJ/ All | The Proposer took an action to clearly define the original proposal for discussion at the next meeting. Workgroup members to discuss whether any alternatives should then be proposed ahead of the Workgroup Consultation. | The Proposer advised defining the original proposal and discussing alternatives, was completed. | WG5 | Closed | WG7
13 | WG5 | DH / AS | Workgroup members discussed the need for additional data analysis, particularly focusing on the impact of the charging year forecast on the pound per MW hour and pence per kWh. A follow up action was taken to look into providing a forecast of the consumption for the 2029/30 year and to apply the necessary ratios for later years. A Workgroup member to provide historic wholesale prices to compare with the 10 years component | A Workgroup member provided an update, which involved providing additional data on the impact of the charging year forecast. They mentioned they had pulled together data from Elexon and shared it with the Chair and the Proposer. | WG6 | Closed | WG6
14 | WG5 | DH | Workgroup members identified anomalies in the data for certain zones, particularly Zone 1. A Workgroup member agreed to investigate further to ensure accurate data representation. | The Proposer noted that the anomalies have been resolved with updated data, but further review is needed, and the calculation tables will need to be updated. | WG6 | Closed | WG6
15 | WG6 | TP/SW | Update the timeline and circulate it to the Workgroup for review before sending it to the panel. | SW circulated the timlined to Workgroup members. | WG7 | Closed | WG7
16 | WG6 | All | Review and edit the Workgroup consultation document, adding comments and changes as necessary. | Consultation document reviewed, and comments added. | Ongoing | Closed | WG8
17 | WG6 | AS | Develop the WACCM proposal and share it with the work group for review before the next Workgroup. | This was shared with the Workgroup ahead of Workgroup 7 | WG7 | Closed | WG7
18 | WG6 | LJ/PM | Develop the legal text on the current CUSC section 14 baseline | The Proposer and PM acknowledged that they had not yet completed this task, and advised it was ongoing and would be important in the autumn. | Ongoing | Closed | WG11
19 | WG7 | RH | Check If the alternative solution raised by GD is within scope of this modification | The Chair informed that NESO legal had advised the alternative solution proposed by a Workgroup member was out of scope. | WG8 | Closed | WG8
20 | WG8 | SW | ​​Send an offline version of the updated consultation report to all Workgroup members for review before publication.​ | The Workgroup Consultation was circulated for review before submission | 2025-07-07 | Closed | 2025-07-07
21 | WG10 | RH/SW | Send out options for the next workgroup meeting date, via a poll. | Sent out and new Workgroup date confirmed | WG11 | Closed | WG11
22 | WG11 | KH/SW | Reduce the executive summary on the Workgroup Report. | Completed. | WG12 | Closed | WG12
23 | WG11 | All | Add a clear explanation and purpose of 'Triad' to the Workgroup Report. | Added to the Workgroup report | WG12 | Closed | WG12
24 | WG11 | PM | Correct the wording and formulae in the legal text to accurately reflect the treatment of residuals and the application of tariffs, consulting with legal and relevant colleagues as needed. | This has been added to the legal test (uploaded on collaboration space) | WG12 | Closed | WG12
25 | WG11 | PM | Update the legal text to include separate calculations for non half-hourly and half-hourly demand in negative zones, ensuring both are clearly delineated. | This has been added to the legal test (uploaded on collaboration space) | WG12 | Closed | WG12
26 | WG11 | KH/SW | Share the updated Legal text and add to the collaboration space. | Shared and sent to the Workgroup on 09/10/2025 | WG12 | Closed
27 | WG11 | PM | Revise the descriptive section on the de minimis half-hour zero level in the legal text to reflect current requirements and CMP440 changes | Corrected by the Workgroup member in the legal text 14.17.3. PM to update on master version. | WG12 | Closed | WG12
28 | WG11 | AS | Add further explanatory text and information tables in the WACM section, in order to mirror the headings 'issues raised' in the main proposal | The Alternative Proposer made the required amendments and additional tables added. | WG12 | Closed | WG12
29 | WG12 | LJ/XZ | Provide the full Frontier Economics analysis referenced in the Workgroup report. | The Proposer clarified the correct link to the Frontier Economics analysis is now included in the Workgroup report, addressing previous confusion about the referenced material. | WG13 | Closed | WG13
30 | WG12 | LJ/XZ | Update Table 11 and 13 on the Workgroup report and any that can subsequently be updated with the most recent data. | The Proposer confirmed tables 11, 13, and others (tables 8-15) have been updated with the most recent data. | WG13 | Closed | WG13
31 | WG12 | PM | Review and update legal text sections 14.17.4 and subsequent paragraphs to ensure correct application and clarity, then share for Workgroup member feedback. | The NESO Representative confirmed updates to legal text sections 14.17.4 and related paragraphs have been completed. | WG13 | Closed | WG13
32 | WG12 | PM | Confirm with the Revenue Team whether additional data flows or demand forecasts are required for half-hourly customers in negative zones for monthly charges and reconciliation. | The National Energy System Operator (NESO) Representative confirmed no additional data flows are needed, but changes to supply and demand forecast requirements for monthly billing have been identified and will be reflected in legal text. | WG13 | Closed | WG13
33 | WG12 | LJ/XZ | Verify the source and accuracy of the domestic EHVC table and clarify whether the demand chargeable demand locational capacity is moving towards energy-based charging for Non Half-Hourly segments. | The Proposer explained post Market-Wide Half Hourly Settlement (MHHS) charging will be based on metering type, not measurement class, with some customers moving between charging methodologies as a result. | WG13 | Closed | WG13
34 | WG12 | LJ/XZ | Check and update the locational charge calculations in the Workgroup report to ensure consistency between Non Half-Hourly and original CMP using average profile, and provide logical explanation for any differences. | Incorrect action captured | WG13 | Closed | WG14
35 | WG13 | KH/SW | Reschedule the next Workgroup if alternates are unable to attend. | Liaised with Workgroup members to ascertain availability and re sheduled. | WG14 | Closed | WG14
36 | WG13 | LJ/AS | Review the background section of the Workgroup report offline and ensure that both the original proposal and WACM1 views are clearly captured, with each proposer editing their own section as appropriate.​ | Both Proposers views are now clearly captured. | WG14 | Closed | WG14
37 | WG13 | LJ/AS | Check and, if necessary, update the Workgroup report to ensure it accurately describes the difference between the original and WACM1 regarding the calculation and application of pence per kWh tariffs, particularly in relation to the number of tariffs and their derivation.​ | Workgroup report updated to describe differences in pence per kWh tariffs; summary and legal text redrafted. | WG14 | Closed | WG14
38 | WG13 | PM | Review and if required update the flow chart in section 14.27 of the CUSC to reflect changes resulting from the modification, including any necessary amendments to the description of how demand charges are applied. | Revised flow chart included in legal text. | WG14 | Closed | WG14
39 | WG13 | DH | Check the forecasting requirements in the legal text to ensure that the necessary data splits (e.g., final and non-final demand, half hourly and non-half hourly, positive and negative zones) are correctly specified for both the original and WACM1 solutions. | A small change was required to the legal text, which was communicated to Workgroup via email. | WG14 | Closed | WG14
40 | WG13 | PM | Confirm with legal whether the floor for the Transmission Demand Residual (TDR) at £0 per site per day is necessary in the legal text and update accordingly based on legal advice. | Legal text flaw on TDR discussed and retained due to CMP363. | WG14 | Closed | WG14
41 | WG13 | DH | Work through the NRRT (Non Recovered Revenue Tariff) formula to determine if the additional term is necessary to avoid double counting, and confirm whether it should be included in the legal text. | No changes were required to the legal text. | WG14 | Closed | WG14
42 | WG13 | PM | Write a summary in the Workgroup report describing all changes made to the legal text, ensuring clarity for Workgroup members ahead of the final meeting and vote. | Summary of legal text changes written for Workgroup report. | WG14 | Closed | WG14