## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | Proposer | Consider legal text changes offline as agreed in Workgroup 1 | Proposer has set up a sharepoint site for members to add any comments to the legal text. These will the be addressed at the next Workgroup. All considerations from WG1 have been addressed | WG2 | Complete | Workgroup 2
2 | WG1 | Chair | Revise Timeline and share with members for approval. | Timeline agreed by Workgroup members. Awaiting Panel approval (25 January 2024) | WG2 | Complete | Workgroup 2
3 | WG2 | Proposer | OC2.1.6: Proposer to seek clarification on this clause with ESO SME’s in application. |  | WG3 | Complete | Workgroup 3
4 | WG2 | Proposer | OC2.3.1.1: Proposer to consider merging subparagraphs (a) and (b) |  | WG3 | Complete | Workgroup 3
5 | WG2 | Proposer | Checked whether headings are bolded in the Grid Code. | Headings are not bolded unless they contain defined terms. All headings have been checked and un bolded | WG3 | Complete | Workgroup 3
6 | WG2 | Proposer | OC2.3.1.2.1 (a) and (b) consider re-wording |  | WG3 | Complete | Workgroup 3
7 | WG2 | Proposer | OC2.3.1.2.1 (c) consider the wording and use of its obligations | Yes (Kept as it currently stands. A) considers an unplanned change while b) considers a planned change | WG3 | Complete | Workgroup 3
8 | WG2 | All | Workgroup to review offline OC2 document from page 5 onwards |  | WG4 | Complete | Workgroup 3
9 | WG3 | Proposer and SW | Review wording in Figure 2 Summary of obligations from end of week 8 to end of week 34 subclause (d). | Meeting held and wording reviewed | WG4 | Complete | Workgroup 4
10 | WG | Proposer | Proposer to consider amending table to clarify the expectation of the Generator | Table updated | WG4 | Complete | Workgroup 4
11 | WG3 | Proposer | Proposer to cross reference the definition of Maximum Export Limit with other codes | Cross reference done and updates completed | WG4 | Complete | Workgroup 4
12 | WG4 | Proposer | To consider the table in OC2.3.2.3.2 and the need for the key to remain. To consider the formatting, size, and color scheme. | Table updated and agreed with WG | WG5 | Complete | Workgroup 6
13 | WG4 | Proposer/GV | To get together and try to understand if there is a hook in the Planning Code to add the reference about the Generators Performance Charts. | Meeting held and wording reviewed | WG5 | Complete | Workgroup 6
14 | WG5 | Proposer | To look into OC2.3.2.1 a) and b) | Updated given to WG who agreed proposed changes | WG5 | Complete | Workgroup 6
15 | WG5 | Proposer | To check with legal team about OC2.3.1.2.2 | Checked no issues | WG5 | Complete | Workgroup 6
16 | WG6 | Workgroup members | Members to review the legal text and share any comments or queries | Members reviewed shared documents | WG6 | Complete | Workgroup 8
17 | WG6 | Chair | Issue extended timeline | Timeline issued to members | WG6 | Complete | Workgroup 6
18 | WG10 | Workgroup members | Share how much time has been invested in the process. | Members shared details | WG12 | Complete | Workgroup 11
19 | WG10 | Proposer | Review Grid Code to update any refernces relating to OC2 |  | WG11 | Complete | Workgroup 11
23 | WG10 | Proposer | Allign current text to GC156 |  | WG11 | Complete | Workgroup 11
24 | WG10 | Proposer | Review the definitions on Financial Year |  | WG11 | Complete | Workgroup 11
25 | WG10 | Proposer | Share revised legal text |  | WG11 | Complete | Workgroup 12
26 | WG11 | Proposer | Share updated baseline |  | WG12 | Complete | Workgroup 12
27 | WG11 | Proposer & AC | Review flow process diagram |  | WG12 | Complete | Workgroup 12
28 | WG11 | Proposer | Share feedback spreadsheet with Workgroup members |  | WG12 | Complete | Workgroup 12