# SCHEDULE 2 EXHIBIT 3

## PART 1

### For use with User’s in the categories of (i) Power Stations directly connected to the National Electricity Transmission system, (ii) Embedded Power Stations which are the subject of a Bilateral Embedded Generation Agreement, or (iii) where, associated with Distributed Generation, a Distribution System directly connected to the National Electricity Transmission System.

### Please note this construction agreement reflects and is based on the Connect and Manage Arrangments applying to these categories.

### Please note that the Queue Management Process will not be applied and included in 
(i) Construction Agreements with an Embedded Power Station  relating to a Bilateral Embedded Generation Agreement or (ii) in Construction Agreements with the owner/operator of a Distribution System directly connected to the National Electricity Transmission System where the Construction Agreement is required because of a connection to that Distribution System and the Distribution Queue Management Process applies.

INDICATIVE

DATED [   ] 20[17]

NATIONAL ENERGY SYSTEM OPERATOR LIMITED		(1)

and

[					]		(2)

THE  CONNECTION AND USE OF SYSTEM CODE

CONSTRUCTION AGREEMENT

CONTENTS

| Clause | Title |
| --- | --- |
| 1 | Definitions, Interpretation and Construction |
| 2 | Carrying out of the Works |
| 3 | Delays |
| 4 | Commissioning Programme and Liquidated Damages |
| 5 | Approval to Connect/Energise/Become Operational |
| 6 | Independent Engineer |
| 7 | Becoming Operational |
| 8 | Compliance with Site Specific Technical Conditions |
| 9 | Provision of Security |
| 10 | Event of Default |
| 11 | Termination |
| 12 | Term |
| 13 | CUSC |
| 14 | Disputes |
| 15 | Variations |
| 16 | Distributed Generation |
| [17 | Queue Management Process] |
| [18 | Distribution Queue Management] |
| Appendix B1 | One Off Works |
| Appendix G | Transmission Connection Asset Works |
| Appendix H | Transmission Reinforcement Works |
| Appendix I | User's Works |
| Appendix J | Construction Programme |
| Appendix K | Liquidated Damages |
| Appendix L | Independent Engineer |
| Appendix MM | Attributable Works and Key Consents |
| Appendix N | Third Party Works |
| Appendix [O][P] | User’s Data/Developer’s Data |
| Appendix Q | Queue Management Process – User Progression Milestones |

THIS CONSTRUCTION AGREEMENT is made on the [   ] day of [   ] 20[17]

BETWEEN

(1)	The company registered in England with number 11014226 (“The Company” (“The Company”, which expression shall include its successors and/or permitted assigns); and

(2)	[   ] a company registered in [   ] with number [   ] whose registered office is at [   ] (“User”, which expression shall include its successors and/or permitted assigns)

WHEREAS

(A)	Pursuant to the ESO Licence, The Company has prepared a Connection and Use of System Code (CUSC) setting out the terms of the arrangements for connection to and use of the National Electricity Transmission System and the provision of certain Balancing Services.

(B)	The User has applied for [connection to] [and use of] [modification to its connection to] [or use of] the National Electricity Transmission System and  pursuant to condition E12 of the ESO Licence, The Company is required to offer terms in accordance with the CUSC in this respect or [specific recital to reflect that the Construction Agreement is an amendment of an existing signed offer pursuant to the CUSC amending documents]

(C) 	The Company and the User are parties to the CUSC Framework Agreement (being an agreement by which the CUSC is made contractually binding between the parties).

(D)	Certain works are required as part of this offer as set out in this Construction Agreement.

(E)	This Construction Agreement is entered into pursuant to the terms of the CUSC.

(F)	This Construction Agreement has been prepared under the Connect and Manage Arrangements [and is subject to the Queue Management Process].

(G)	This Construction Agreement is a [Gate 1 Agreement][Gate 2 Agreement].

NOW IT IS HEREBY AGREED as follows:

## 1.	DEFINITIONS, INTERPRETATION AND CONSTRUCTION

Unless the subject matter or context otherwise requires or is inconsistent therewith, terms and expressions defined in Section 11 of the CUSC and in the Bilateral Connection Agreement have the same meanings, interpretations or constructions in this Construction Agreement.

| “Attributable Works” | those Construction Works identified as such in accordance with the User Commitment Methodology and which are set out in Appendix MM Part 1. |  |
| --- | --- | --- |
| "Authority" | as defined in the CUSC. |  |
| “Bilateral Connection Agreement” | the Bilateral Connection Agreement entered into between the parties on even date herewith. |  |
| "Bilateral Embedded Generation Agreement" | the Bilateral Embedded Generation Agreement entered into between the parties on even date herewith. |  |
| “Cancellation Charge” | as calculated in accordance with the User Commitment Methodology. |  |
| "Charging Date" | the date upon which the Construction Works are first Commissioned and available for use by the User or if the Independent Engineer before, on or after the Commissioning Programme Commencement Date shall have certified in writing that the Transmission Connection Assets, are completed to a stage where The Company could commence commissioning and by such date the User’s Works shall not have been so certified then the date falling [ ] days after the date of such certification, provided that the Transmission Reinforcement Works are Commissioned and Network Options Assessment Works are completed as at that date. In the event that the Transmission Reinforcement Works are not so Commissioned and/or the Network Options Assessment Works are not so completed the Charging Date shall be the date on which they are Commissioned and/or completed as appropriate. [Exclude Network Options Assessment Works from this definition if they are not also Enabling Works]. |  |
| “Commissioning Programme Commencement Date” | the date specified in the Construction Programme for the commencement of the Commissioning Programme or any substituted date fixed under the terms of this Construction Agreement |  |
| “Commissioning Programme” | the sequence of operations/tests necessary to connect the User’s Works and the Transmission Connection Asset Works to the National Electricity Transmission System for the purpose of making the User's Works available for operation to be determined pursuant to Clause 2.10 of this Construction Agreement. |  |
| “Completion Date” | [ ] or such other date as may be agreed in terms of this Construction Agreement for completion of the Construction Works. |  |
| “Connect and Manage Derogation” | the temporary derogation from the NETS SQSS available to The Company under condition E7 of the ESO Licence and/or the Relevant Transmission Licensee under Standard Condition D3 of its transmission licence; |  |
| “Connected Planning Data” | data required pursuant to the Planning Code which replaces data containing estimated values assumed for planning purposes by validated actual values and updated estimates for the future and by updated forecasts for forecast data items. |  |
| “Consents” | in relation to any Works:- (a) all such planning and other statutory consents; and (b) all wayleaves, easements, rights over or interests in land or any other consent; or (c) permission of any kind as shall be necessary for the construction of the Works and for commencement and carrying on of any activity proposed to be undertaken at or from such Works when completed. |  |
| “Construction Programme” | the agreed programme for the Works to be carried out by or on behalf of The Company and the User set out in detail in Appendix [J] to this Construction Agreement or as amended from time to time pursuant to Clauses 2.3 and 3.2 of this Construction Agreement. |  |
| "Construction Site" | the site where the Transmission Connection Asset Works are being undertaken by or on behalf of The Company; |  |
| “Construction Works” | the Transmission Connection Asset Works, Enabling Works, Network Options Assessment Works and One Off Works and such additional works as are required in order to comply with any relevant Consents relating to any such works but excluding for the avoidance of doubt any Third Party Works. |  |
| "Dispute Resolution Procedure” | the procedure for referral to arbitration set out in Paragraph 7.4 of the CUSC. |  |
| “Enabling Works” | those Transmission Reinforcement Works which are specified in Appendix H Part 1 to this Construction Agreement. |  |
| “Event of Default” | any of the events set out in Clause 10 of this Construction Agreement as constituting an event of default. |  |
| “Gate 2 Date” | means the date on which the last of the conditions at Clause 1.2 of this Construction Agreement are satisfied - [include only in Gate 1 Agreements with Reservation] |  |
| “Independent Engineer” | the engineer specified in Appendix L to this Construction Agreement. Provided that:- (a) where the parties fail to agree on a suitable engineer within 120 days of the date of this Construction Agreement; or |  |
|  | (b) where any Independent Engineer appointed from time to time shall fail, refuse or cease to act in the capacity set out herein and no substitute engineer of suitable standing and qualification can be agreed by the parties within 30 days; then such engineer as the President of the Institution of Electrical Engineers shall, on the application of either party, nominate shall be the Independent Engineer. |  |
| “Installed Capacity” | the installed capacity provided in the Original Red Line Boundary and set out in Appendix [O][P]. |  |
| “Key Consents” | those Consents required in respect of the [User’s/Developer’s] Power Station which The Company has identified as such and which are set out in Appendix MM Part 2. |  |
| “Liquidated Damages” | the sums specified in or calculated pursuant to Appendix K to this Construction Agreement. |  |
| “Network Options Assessment Works” | the works set out in the Networks Options Assessment report prepared by The Company pursuant to C13 of the ESO Licence and issued by The Company in [ ] which in The Company’s reasonable opinion are required to be completed before the Completion Date to ensure that the National Electricity Transmission System complies with the requirements of condition E7 of the ESO Licence and Standard Condition D3 of any Relevant Transmission Licensee’s transmission licence prior to the Connection of the User’s Equipment in terms of Clause 7.1 [or 7.2] of this Construction Agreement. |  |
| “One Off Works” | the works described in Appendix B1 to this Construction Agreement. |  |
| “Reservation Expiry Date” | [ ] being the date as bilaterally negotiated between The Company and the User [and which may be extended by agreement between the parties] on which the Reservation expires.[include only in Gate 1 Agreements with Reservation] |  |
| “Term” | the term of this Construction Agreement commencing on the date hereof and ending in accordance with Clause 12. |  |
| “Third Party Works” | the works to be undertaken on assets belonging to a party other than a Relevant Transmission Licensee and the User to enable The Company to provide or as a consequence of the connection to and\or use of the National Electricity Transmission System by the User as specified in Appendix N; |  |
| "Transmission Connection Assets" | the assets specified in Appendix A to the Bilateral Connection Agreement. |  |
| “Transmission Connection Asset Works” | the works necessary for construction and installation of the Transmission Connection Assets at the Connection Site specified in Appendix G to this Construction Agreement. |  |
| “Transmission Reinforcement Works” | those works other than the Transmission Connection Asset Works Network Options Assessment Works and One Off Works, which in the reasonable opinion of The Company (and in the absence of the Connect and Manage Derogation) are all necessary to extend or reinforce the National Electricity Transmission System to ensure that the National Electricity Transmission System complies with the requirements of condition E7 of the ESO Licence and Standard Condition D3 of any Relevant Transmission Licensee’s transmission system and which are specified in Appendix H to this Construction Agreement, where Part 1 is the Enabling Works and Part 2 is the Wider Transmission Reinforcement Works. |  |
| “Trigger Date” | [date] as identified in accordance with the User Commitment methodology. |  |
| “User Progression Milestones” | the milestones (applied in accordance with CUSC Section 16) for the User’s project as set out in Appendix Q of this Construction Agreement. |  |
| “User’s Works” | those works necessary for installation of the User’s Equipment which are specified in Appendix I to this Construction Agreement. |  |
| “Wider Transmission Reinforcement Works” | those Transmission Reinforcement Works which are specified in Appendix H Part 2 to this Construction Agreement where Part 2.1 is works required for the User and Part 2.2 is works required for wider system reasons. |  |
| “Works” | the Construction Works and the User’s Works. |  |
| Users in the capacity of a Directly Connected Power Station or Embedded Power Station (other than those who are a BELLA) insert the following: |  |  |
| [Notice of Intent |  | the notice issued by The Company pursuant to Clause 7.4.4. |
| Notice of Reduction |  | the notice issued by The Company pursuant to Clause 7.4.7 including a revised Appendix C specifying the revised Transmission Entry Capacity. |
| Preliminary Request |  | the request issued by The Company pursuant to Clause 7.4.1. |
| Reduction Fee |  | the fee payable by the User to The Company in respect of the agreement to vary issued pursuant to Clause 7.4.9 such fee being calculated on the same basis as that set out in the Charging Statements as payable on a payment of actual costs basis in respect of a Modification Application.. |
| Users in the capacity of a Directly Connected Distribution System where works are required in respect of a BELLA or a Relevant Embedded Power Station insert the following (and where the Construction Agreement relates to more than one, for each of the Developers): |  |  |
| [Developer Capacity |  | the MW figure [for export] specified in the Developer’s Data. |
| Developer |  | Insert name address and registered number who is party to a BELLA with The Company or the subject of the Transmission Evaluation Application. |
| Developer’s Data |  | the information provided by the [Developer-BELLA] [User in respect of the Developer in the Transmission Evaluation Application-relevant embedded power station] and set out in Appendix [P]. |
| Developer’s Project |  | the connection of a [xMW wind farm\power station to the User’s Distribution System at [ ]] |
| Notice of Intent |  | the notice issued by The Company pursuant to Clause 7.4.4. |
| Notice of Reduction |  | the notice issued by The Company pursuant to Clause 7.4.7 revising the Developer’s Capacity for this Construction Agreement and Appendix A to the BELLA. |
| Preliminary Request |  | the request issued by The Company pursuant to Clause 7.4.1. |
| Reduction Fee |  | the fee payable by the User to The Company in respect of the agreement to vary issued pursuant to Clause 7.4.9 such fee being calculated on the same basis as that set out in the Charging Statements as payable on a payment of actual costs basis in respect of a Modification Application. |
| - [A Gate 1 Agreement with/without Reservation only] - 1.2 GATED Application AND OFFER PRocess – GATE 1 Conditional Clause [AND RESERVATION] 1.2.1 The rights and obligations of the User and The Company under this Construction Agreement [and the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement]] are conditional on: 1.2.1.1 the User making a Gate 2 Application; 1.2.1.2 the Gate 2 Application meeting the Gate 2 Criteria; and 1.2.1.3 the User accepting the terms of the [Gate 2 Offer]; [and in the case of a BEGA, 1.2.1.4 the owner/operator of the Distribution System accepting the related Gate 2 Offer.] 1.2.2 The parties agree and acknowledge that until the Gate 2 Date, the rights and obligations of each party pursuant to this Construction Agreement (other than this Clause 1.2 and Clause 13 – edit to include any other provisions agreed between the parties as useful to include) and the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement] shall be suspended. 1.2.3 [The parties further agree that the information provided for the purposes of this Gate 1 Agreement and set out in the Appendix [O][P] to this Construction Agreement being a proposed [Connection Site] [Site of Connection], Completion Date and requested [Transmission Entry Capacity – edit for other capacity types] are indicative only prior to the Gate 2 Date and shall not be binding on the parties or confer any commitment by The Company to the [Connection Site][Site of Connection], Completion Date or requested [Transmission Entry Capacity – add other relevant capacity refs as appropriate] and any reliance on them for any purpose prior to the Gate 2 Date is at the User’s risk- no reservation]. [The parties further agree that the [Connection Site] [Site of Connection] and Completion Date and [Transmission Entry Capacity-add other relevant capacity refs as appropriate] as set out in Appendix [O][P] to this Construction Agreement have been Reserved for the purposes of this connection/use of system and any Gate 2 Offer will reflect this position and the requested [Transmission Entry Capacity- add other relevant capacity refs as appropriate] provided that the Gate 2 Application is made prior to the Reservation Expiry Date and the Gate 2 Offer is accepted- Reservation only]. 1.2.4 At any time prior to the Gate 2 Date, the User shall have the right to terminate this Connection Agreement by written notice to The Company without any liability for any Cancellation Charge. This right to terminate shall expire with effect from the Gate 2 Date. 1.2.5 With effect from the Gate 2 Date the provisions of this Construction Agreement, as amended by the Gate 2 Offer by agreement of the parties, shall be in full force and effect. |  |  |

## CARRYING OUT OF THE WORKS

### Forthwith following the date of this Construction Agreement the User shall agree with the Relevant Transmission Licensee the Safety Rules and Local Safety Instructions to apply during the Construction Programme and Commissioning Programme.  Failing agreement within three months of the date of this Construction Agreement the matter shall be referred to the Independent Engineer for determination in accordance with Clause 6 of the Construction Agreement.

### Subject to Clauses 2.3 and 2.4 of this Construction Agreement forthwith following the date of this Construction Agreement The Company shall use its best endeavours to obtain in relation to the Construction Works, and the User shall use its best endeavours to obtain in relation to the User's Works, all Consents.  Each shall give advice and assistance to the other to the extent reasonably required by the other in the furtherance of these obligations.  Further, each party shall, so far as it is legally able to do so, grant to the other or the Relevant Transmission Licensee, all such wayleaves, easements, servitude rights, rights over or interests (but not estates as regards land in England and Wales and not heritable or leasehold interests as regards land in Scotland) in land or any other consents reasonably required by the other or the Relevant Transmission Licensee in order to enable the Works to be expeditiously completed and to enable that other to carry out its obligations to the other under this Construction Agreement and in all cases subject to such terms and conditions as are reasonable.

### The following additional provisions shall apply in respect of the Consents and	 Construction Works:-

#### All dates specified in this Construction Agreement are subject to The Company obtaining Consents for the Construction Works in a form acceptable to it within the time required to carry out the Construction Works in accordance with the Construction Programme.

#### In the event of:-

##### the Consents not being obtained by the required date; or

##### the Consents being subject to conditions which affect the dates; or

##### The Company wishing to amend the Construction Works to facilitate the granting of the Consents,

The Company shall be entitled to revise the Construction Works (and as a consequence Appendix A to the Bilateral Connection Agreement) and all dates specified in this Construction Agreement and the charges specified in Appendix B to the Bilateral Connection Agreement.  For the avoidance of doubt such revisions shall be at The Company 's absolute discretion and the consent of the User is not required.

#### The User shall be regularly updated by The Company in writing or by such other means as the parties may agree as to progress made by The Company from time to time in the obtaining of relevant Consents pursuant to its obligations under Clause 2.2 or 2.3 of this Construction Agreement.

2.4	Paragraphs 11.2.3 to 11.2.5 of the CUSC relating to Consents shall apply to the Construction Agreement as if set out here in full.

2.5	Prior to the commencement of the Transmission Connection Asset Works the User shall have the right to terminate this Construction Agreement upon giving not less than 7 (seven) days notice in writing to The Company.  In the event of the User terminating this Construction Agreement in terms of this Clause 2.5 the provisions of Clause 11 shall apply].

2.6	If the User fails to obtain all Consents for the User's Works having complied with the obligations in Clause 2.2 of this Construction Agreement the obligation on the User to complete the User's Works shall cease and the User may by written notice to The Company terminate this Construction Agreement and the provisions of Clause 11 shall apply

2.7	Both parties shall be entitled to contract or sub-contract for the carrying out of their respective parts of the Works (which in the case of The Company shall include work carried out by a Relevant Transmission Licensee or its contractors or sub-contractors).  The User or any contractor on its behalf shall be responsible for commencing and for carrying out the User's Works to such stage of completion as shall render them capable of being Commissioned in accordance with the Construction Programme and The Company or any contractor on its behalf shall be responsible for commencing and carrying out the Construction Works to such stage of completion as shall render them capable of being Commissioned in accordance with the Construction Programme.

2.8	The parties shall continuously liaise throughout the Construction Programme and Commissioning Programme and each shall provide to the other all information relating to in the case of the User the User’s Works and in the case of The Company the Construction Works reasonably necessary to assist the other in performance of that other’s part of the Works, and shall use all reasonable endeavours to coordinate and integrate their respective part of the Works.  There shall be on-site meetings between representatives of the parties at intervals to be agreed between the parties.  Each party shall deliver to the other party a written report of progress during each calendar quarter within 7 days of the end of that quarter.

Users in the capacity of a Directly Connected Distribution System where works are required in respect of a BELLA or a Relevant Embedded Power Station insert the following:

[“2.8	The parties shall continuously liaise throughout the Construction Programme and Commissioning Programme and each shall provide to the other all information relating to its own Works reasonably necessary to assist the other in performance of that other’s part of the Works, and shall use all reasonable endeavours to coordinate and integrate their respective part of the Works.  There shall be on-site meetings between representatives of the parties at intervals to be agreed between the parties.  The User shall also provide to The Company such information as The Company shall reasonably request and which the User is entitled to disclose in respect of the Developer’s Project. Each party shall deliver to the other party where requested a written report of progress during each calendar quarter (including in the case of the User progress on the Developer’s Project to the extent that the User has such information and is entitled to disclose it) within 7 days of the end of that quarter.”]

2.9	During the period of and at the times and otherwise as provided in the Construction Programme and the Commissioning Programme The Company shall allow the User, its employees, agents, suppliers, contractors and sub-contractors necessary access to the Construction Site and the User shall allow the Relevant Transmission Licensee and in either case their employees, agents, suppliers, contractors and sub-contractors necessary access to its site to enable each to carry out the Transmission Connection Asset Works and One Off Works or User's Works but not so as to disrupt or  delay the construction and completion of the other’s Works on the said sites or the operation of the other’s Plant and Apparatus located thereon, such access to be in accordance with any reasonable regulations relating thereto made by the site owner or occupier.

2.10	Not later than six months prior to the Commissioning Programme Commencement Date The Company shall provide the User with a draft Commissioning Programme for the Commissioning of the Transmission Connection Assets, and the User's Equipment.  The User shall, as quickly as practicable and in any event within three months of receipt thereof, determine whether or not to approve the proposed Commissioning Programme (which approval shall not be unreasonably withheld or delayed) and shall within such three month period either notify The Company of its approval or, in the event that the User reasonably withholds its approval, notify The Company of any changes or variations to the proposed commissioning programme recommended by the User.  If The Company does not accept such changes or variations submitted by the User any dispute shall be referred to the Independent Engineer for determination.  The Commissioning Programme agreed between the parties or determined by the Independent Engineer as the case may be shall be implemented by the parties and their sub-contractors in accordance with its terms.

2.11	If at any time prior to the Completion Date it is necessary for The Company or The Company in its reasonable discretion wishes to make any addition to or omission from or amendment to the Transmission Connection Asset Works and/or Transmission Reinforcement Works and/or the One Off Works and/or the Third Party Works The Company shall notify the User in writing of such addition, omission or amendment and Appendices [B1 (One Off Works), G (Transmission Connection Asset Works) H (Transmission Reinforcement Works), MM (Attributable Works) and N (Third Party Works)] to this Construction Agreement and consequently Appendices [A (Transmission Connection Assets) and B (Connection Charges and One Off Charges)] to the associated Bilateral Connection Agreement shall be automatically amended to reflect the change. Provided that where a User has elected for the Actual Attrubutable Works Cancellation Charge to be based on the Fixed Attributable Works Cancellation Charge the Attributable Works can only be changed after the Trigger Date as provided for in CUSC Section 15.

### 2.12	[The User shall apply to the Secretary of State for Trade and Industry as part of its application under Section 36 of the Act for its generating station, for deemed planning permission in relation to the substation forming part of the Transmission Connection Asset Works.  The User shall use its best endeavours to procure that the said deemed planning permission is so obtained.  The Company's obligations under Clause 2.2 of this Construction Agreement shall not require it to obtain planning consent for the said substation unless and until the relevant Secretary of State shall for whatever reason refuse to deem the grant of planning permission in respect of the same.  The User shall liaise with The Company as to its construction and operational requirements and shall ensure that the said application meets The Company's requirements.  The Company shall provide the User with all information reasonably required by it in relation to the application and the User shall ensure that all requirements of The Company are incorporated in the application for deemed planning consent.]

2.13	[The Enabling Works are conditional on British Energy Generation Limited and/or Magnox Electric plc (as the case may be)granting approval to the carrying out of the Construction Works in terms of the Nuclear Site Licence Provisions Agreement being an agreement dated 30 March 1990 between The Company and Nuclear Electric plc (now called Magnox Electric plc) and an agreement dated 31 March 1996 between The Company and British Energy Generation Limited (and described as such).  In the event of British Energy Generation Limited and/or Magnox Electric plc (as the case may be) not granting approval The Company shall be entitled to change the Construction Works, the Construction Programme and all dates specified in this Construction Agreement.]

2.14	[It is hereby agreed and declared for the purposes of the Construction (Design and Management) Regulations 1994 that the User is the only client in respect of the User's Works and The Company is the only client in respect of the Construction Works and Wider Transmission Reinforcement Works and each of the User and The Company shall accordingly discharge all the duties of clients under the said Regulations.]

2.15	[The Company and the User hereby agree and acknowledge that this Construction Agreement is not to be treated as a construction contract within the meaning of section 104 of the Housing Grants, Construction and Re-generation Act 1996 and sections 104 to 113 of the said Act shall have no application either to the Construction Works or the User's Works and the parties’ rights and obligations with regard to matters of dispute resolution and payment procedures are as expressly set out herein.

2.16	Third Party Works

2.16.1	The User shall be responsible for carrying out or procuring that the Third Party Works are carried out and shall carry them out or procure that they are carried out in accordance with the timescales specified in the Construction Programme. The User shall confirm to The Company or, where requested to do so by The Company, provide confirmation from the third party that the Third Party Works have been completed.

2.16.2	Given the nature of these works it may not be possible to fully identify the works required or the third parties they relate to at the date hereof. Where this is the case The Company shall, subject to 2.16.3 below, advise the User as soon as practicable and in any event by [  ] of the Third Party Works and shall be entitled to revise Appendix N and as a consequence the Construction Programme as necessary to reflect this.

2.16.3 Where Third Party Works are likely to be Modifications required to be made by another user(s) (“the “First User(s)”) as a consequence of Modifications to the National Electricity Transmission System to be undertaken by The Company under this Construction Agreement The Company shall as soon as practicable after the date hereof issue the notification to such First User’s in accordance with CUSC Paragraph 6.9.3.1. The User should note its obligations under CUSC Paragraph 6.10.3 in respect of the costs of any Modifications required by the First User(s).

2.16.4	In the event that the Third Party Works have not been completed by the date specified in the Construction Programme or, in The Company’s reasonable opinion are unlikely to be completed by such date, The Company shall be entitled to revise the Construction Programme as necessary to reflect such delay and also, where The Company considers it necessary to do so, shall be entitled to revise the Construction Works (and as a consequence Appendices A and B to the Bilateral Connection Agreement). For the avoidance of doubt such revisions shall be at The Company's absolute discretion and the consent of the User is not required. Further, in the event that the Third Party Works have not been completed by [   ] The Company shall have the right to terminate this Construction Agreement upon giving notice in writing to the User and in this event the provisions of Clause 11 of this Construction Agreement shall apply.

2.17	Wider Transmission Reinforcement Works

The Company shall keep the User advised as to progress on the Wider Transmission Reinforcement Works  and shall include information on these in the reports produced pursuant to Clause 2.8.

## DELAYS

### If either party shall have reason to believe that it is  being delayed or will be delayed in carrying out that party’s Works for any reason (whether it is one entitling it to the fixing of a new date under Clause 3.2 of this Construction Agreement or not) it shall forthwith notify  the other party in writing of the circumstances giving   rise to the delay and of the extent of the actual and/or  anticipated delay.

### If prior to the Completion Date a party (in this Clause 3.2 “the Affected Party”) shall be delayed in carrying out any of the Affected Party’s Works (including their commissioning) by reason of any act, default or omission on the part of the other Party (in this Clause the “Defaulting Party”) or the Defaulting Party’s employees, agents, contractors or sub-contractors or by reason of an event of Force Majeure, the Affected Party shall be entitled to have such later date or dates fixed as  the Commissioning Programme Commencement Date and/or (as the case may be) the Completion Date as may be fair and reasonable in the circumstances provided that it shall have notified the Defaulting Party in writing of such act, default or omission or event of Force Majeure within 28 days of it becoming aware of the occurrence giving rise to the delay together with an estimate of the proposed delay which it will cause the Affected Party.  In the event of a dispute between the parties over what is or are any fair and reasonable new date or dates to be fixed in the circumstances this shall be promptly referred to and determined by the Independent Engineer.  Once the new date or dates are fixed the Construction Programme and/or Commissioning Programme shall be deemed automatically amended as appropriate.

## COMMISSIONING PROGRAMME AND LIQUIDATED DAMAGES

### Each party shall give written notice to the other declaring its readiness to commence the Commissioning Programme when this is the case.

### The Commissioning Programme shall commence forthwith once both parties have given written notice to the other under Clause 4.1.

### The Works shall be deemed to have been Commissioned on the date that the Independent Engineer certifies in writing to that effect.

### In the event that the actual date of commencement of the Commissioning Programme is later than the Commissioning Programme Commencement Date The Company (if and to the extent that it is responsible for delayed commissioning beyond the Commissioning Programme Commencement Date, such responsibility and/or its extent to be determined by the Independent Engineer failing agreement between the parties) shall be liable to pay to the User Liquidated Damages for each day that the actual date of commencement of the Commissioning Programme is later than the Commissioning Programme Commencement Date.  It is declared and agreed that such Liquidated Damages shall cease to be payable in respect of any period after the date of actual commencement of the Commissioning Programme.

### In the event that the actual date on which the Construction Works are Commissioned is later than the Completion Date The Company (if and to the extent that it is responsible for delayed completion beyond the Completion Date, such responsibility and/or its extent to be determined by the Independent Engineer failing agreement between the parties) shall be liable to pay to the User Liquidated Damages for each day that the actual date on which the Construction Works are Commissioned is later than the Completion Date.  It is hereby agreed and declared that such Liquidated Damages shall cease to be payable in respect of any period after completion of the Construction Works.

### Liquidated Damages payable under Clauses 4.4 and 4.5 of this Construction Agreement shall accumulate on a daily basis but shall be payable calendar monthly.  On or before the 15th day of each month the party entitled to receive the payment of Liquidated Damages shall send to the other party a statement of the Liquidated Damages which have accrued due in the previous calendar month.  The party receiving such statement shall in the absence of manifest error pay the Liquidated Damages shown on the statement within 28 days of the date upon which the statement is received.

### Without prejudice to and in addition to the obligation of the User pursuant to Clause 2.4 of this Construction Agreement, the payment or allowance of Liquidated Damages pursuant to this Clause 4 shall be in full satisfaction of The Company's liability for failure to perform its obligations by the Commissioning Programme Commencement Date and/or the Completion Date as appropriate.

### 4.8	In the event that the User shall have failed, in circumstances not entitling it to the fixing of a new date as the Commissioning Programme Commencement Date pursuant to Clause 3.2, to complete the User's Works by [  ] to a stage where the User is ready to commence the Commissioning Programme, The Company shall have the right to terminate this Construction Agreement upon giving notice in writing to the User  and the provisions of Clause 11 shall apply.

## APPROVAL TO CONNECT/ENERGISE/BECOME OPERATIONAL

### Not later than 4 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties the parties shall prepare and submit the Operation Diagrams required to be prepared and submitted by each of them respectively under CC 7.4.7 and 7.4.10 and likewise the Site Common Drawings required under CC 7.5.2 and 7.5.4 and, if necessary, Gas Zone Diagrams referred to in CC 7.4.9 and 7.4.12.

### Not later than 3 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties the parties shall prepare and submit the Operation Diagrams required to be prepared and submitted by each of them respectively under CC 7.4.8 and 7.4.11 and likewise the Site Common Drawings required under CC 7.5.3 and 7.5.5.

### Not later than 3 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties:-

#### each party shall submit to the other data within its possession needed to enable the completion of Appendices F3 and F4 to the Bilateral Connection Agreement; and

#### the User shall submit to The Company evidence satisfactory to The Company that the User's Equipment complies or will on completion of the User's Works comply with Clause 8 of this Construction Agreement and Paragraphs [1.3.3(b), 2.9 and 6.7] of the CUSC.

### Not later than 8 weeks prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties each party shall submit to the other:

#### for the Connection Site information to enable preparation of Site Responsibility Schedules complying with the provisions of Appendix 1 to the Connection  Conditions together with a list of managers who have been duly authorised by the User to sign such Site Responsibility Schedules on the User's behalf;

#### written confirmation as required under CC.5.2(g) that the list of Safety Co-ordinators are authorised and competent [and a list of persons appointed pursuant to Grid Code CC5.2(m)];

#### a list of the telephone numbers for the facsimile machines referred to in CC6.5.9.

#### Confirmation of access to the Electronic Communications Platform referred to in CC6.5.9 upon access being provided by The Company.

### If directly connected to the National Electricity Transmission System not later than 3 months prior to the expected Commissioning Programme Commencement Date each party shall submit to the other a statement of readiness to complete the Commissioning Programme in respect of the Works and the statement submitted by the User shall in addition contain relevant Connected Planning Data and a report certifying to The Company that, to the best of the information, knowledge and belief of the User, all relevant Connection Conditions applicable to the User have been considered and complied with.  If The Company considers that it is necessary, it will require this latter report to be prepared by the Independent Engineer.  The report shall incorporate if requested by The Company type test reports and test certificates produced by the manufacturer showing that the User's Equipment meets the criteria specified in CC6.

5.6	If embedded not later than 3 months prior to the Charging Date or by such other time as may be agreed between the Parties the User shall submit to The Company a statement of readiness to use the National Electricity Transmission System together with Connected Planning Data and a report certifying to The Company that, to the best of the information, knowledge and belief of the User:-

(i)	all relevant Connection Conditions applicable to the User have been considered;

(ii)	CC 6 insofar as it is applicable to the User has been complied with; and

(iii)	the site-specific conditions set out in Appendices [F1, F3, F4] and [F5] to the Bilateral Embedded Generation Agreement have been complied with.

If The Company considers that it is necessary, it will require this report to be prepared by the Independent Engineer. The report shall incorporate if requested by The Company type test reports and test certificates produced by the manufacturer showing that the User's Equipment meets the criteria.

## INDEPENDENT ENGINEER

The parties agree and shall procure that the Independent Engineer shall act as an expert and not as an arbitrator and shall decide those matters referred or reserved to them under this Construction Agreement by reference to Good Industry Practice using their skill, experience and knowledge and with regard to such other matters as the  Independent Engineer in their sole discretion considers appropriate.  All references to the Independent Engineer shall be made in writing by either party with notice to the other being given contemporaneously as soon as reasonably practicable and in any event within 14 days of the occurrence of the dispute to be referred to the Independent Engineer.  The parties shall promptly supply the Independent Engineer with such documents and information as they may request when considering such question.  The Independent Engineer shall use their best endeavours to give their decision upon the question before them as soon as possible following its referral to them.  The parties shall share equally the fees and expenses of the Independent Engineer.  The parties expressly acknowledge that submission  of disputes for resolution by the Independent Engineer does not preclude subsequent submission of disputes for resolution by arbitration as provided for in the Dispute Resolution Procedure.  Pending any such submission the parties shall treat the Independent Engineer’s decision as final and binding.

7.	BECOMING OPERATIONAL

[7.1	If directly connected to the National Electricity Transmission System The Company shall connect and Energise the User's Equipment at the Connection Site during the course of and in accordance with the Commissioning Programme and thereafter upon compliance by the User with the provisions of Clause 5 and provided (1) the Construction Works excluding the Network Options Assessment Works [delete  Network Options Assessment Works under the Connect and Manage Arrangements if these are not Enabling Works] shall be Commissioned and (2) [the Network Options Assessment Works and Third Party Works shall be completed The Company shall forthwith notify the User in writing that the Connection Site shall become Operational.] or

[7.2	If Embedded upon compliance by the User with the provisions of Clauses 5.1, 5.2 and 5.3 and subject, if The Company so requires, to the Enabling Works [and/or works for the Modification] being carried out and/or the [New] Connection Site being Operational (any or all as appropriate) The Company shall forthwith notify the User ("Operational Notification") in writing that it has the right to use the National Electricity Transmission System.  It is an express condition of this Construction Agreement that in no circumstances, will the User use or operate the User's Equipment without receiving the Operational Notification from The Company.]

7.3	If, on completion of the User's Works in accordance with the terms of this Construction Agreement the Registered Capacity of the User's Equipment is less than [	]MW, The Company shall automatically have the right to amend Clause 7 and Appendix C to the Bilateral Connection Agreement to reflect the actual Registered Capacity of the User's Equipment.

Users in the capacity of a Directly Connected Power Station or Embedded Power Station (other than those who are a BELLA) insert the following:

[7.4	Transmission Entry Capacity Reduction

7.4.1	If, at any time prior to the Completion Date The Company reasonably believes from data provided by the User to The Company, the reports provided by the User pursuant to Clause 2.8 and Clause 5 of this Construction Agreement, the commissioning process under the Construction Agreement or otherwise that the User’s Equipment will be such that it will not be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity The Company shall advise the User accordingly in writing setting out its reasons for this belief, the source of the information giving rise to the concern and seeking clarification from the User.

7.4.2	The User shall respond to The Company within 15 Business Days of the date of the Preliminary Request providing such information or data as is necessary to satisfy The Company’s concerns set out in the Preliminary Request and making any amendments necessary to the report provided by the User pursuant to Clause 2.8 and / or data provided by the User to The Company to reflect this.

    - In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.2 by the User that the User’s Equipment will be such that it will be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity The Company shall notify the User accordingly.

    - In the event that the User does not respond to the Preliminary Request or, notwithstanding the User’s response, The Company remains of the view that the User’s Equipment will be such that it will not reasonably be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity The Company shall inform the User in writing that it intends to amend Clause 7 and Appendix C to the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement] to reflect the Transmission Entry Capacity that it reasonably believes to be the level of power that the User's Equipment will be capable of exporting .

    - The User shall respond to the Notice of Intent within 15 Business Days of the date of the Notice of Intent explaining why it still reasonably believes that its User's Equipment will be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or providing a reasonable explanation as to why this is not the case.

    - In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.5 by the User that the User’s Equipment will be such that it will be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity The Company shall notify the User accordingly.

7.4.7	Where notwithstanding the User’s response to the Notice of Intent The Company remains of the view that the User’s Equipment will be such that it will not reasonably be capable of exporting power onto the National Electricity Transmission System at the level of the Transmission Entry Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or the User does not provide a response that is satisfactory to The Company within the timescale specified in 7.4.5 above The Company will issue the Notice of Reduction to the User and will send a copy of the same to the Authority.

7.4.8	Unless during such period the matter has been referred by the User to the Authority for determination by the Authority under the provisions of condition E13.5 of the ESO Licence, the Notice of Reduction shall take effect on the day 15 Business Days after the date of the Notice of Reduction and Appendix C of the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement] shall be amended on that date in the manner set out in the Notice of Reduction.  Where the matter has been referred the amendments to Appendix C of the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement] and the date they take effect shall be as set out in the Authority’s determination.

7.4.9	After a Notice of Reduction has taken effect The Company shall be entitled to make such amendments to this Construction Agreement as it requires as a result of the reduction in Transmission Entry Capacity effected by the Notice of Reduction and as a consequence to the [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement]. The Company shall advise the User as soon as practicable and in any event within 3 months of the date of the Notice of Reduction (or if the matter has been referred by the User to the Authority for determination, the date of determination) of such amendments by way of offer of an agreement to vary the Construction Agreement and [Bilateral Connection Agreement] [Bilateral Embedded Generation Agreement]. This agreement to vary will also provide for payment by the User of the Reduction Fee where applicable. The parties acknowledge that any dispute regarding this variation shall be referable to and determined by the Authority under the provisions of condition E13.5 of the ESO Licence.

[7.5	Compliance with Original Red Line Boundary -add only where it’s a Gated Agreement for a direct connection

If a User is not compliant at a User Progression Milestone with the Original Red Line Boundary (other than as it may be changed under the Queue Management Guidance) for one or more technologies, The Company shall be entitled to amend the Construction Agreement and as a consequence the Bilateral Connection Agreement to:

    - reduce the Installed Capacity (of each technology that is non-compliant).

    - remove that technology if the Installed Capacity of a technology is reduced to 0 MW.

    - reduce the [Transmission Entry Capacity] [other relevant capacity] if the sum of the Installed Capacity of all technologies is reduced such that it is less than the [Transmission Entry Capacity] [other relevant capacity] and such that the [Transmission Entry Capacity] [other relevant capacity] is no higher than the sum of the Installed Capacity of all technologies.]

[7.6	Where there is a reduction in Transmission Entry Capacity under Clause 7.4 [or Clause 7.5] prior to the Charging Date, on such reduction in Transmission Entry Capacity taking effect the User the User shall pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice in respect thereof.]

Users in the capacity of a Directly Connected Distribution System where works are required in respect of a BELLA or a Relevant Embedded Power Station insert the following (and where the Construction Agreement relates to more than one, for each of the Developers):

[7.4	Developer Capacity Reduction

7.4.1	If, at any time prior to the Completion Date The Company reasonably believes from the reports provided by the User pursuant to Clause 2.8 and Clause 5 of this Construction Agreement [in the case of relevant embedded power stations – and\or CUSC Paragraphs 6.5.8 or 6.5.5.11], the commissioning process generally or otherwise that the Developer’s Equipment will be such that it will not be capable of generating at the Developer Capacity, The Company shall advise the User accordingly in writing setting out its reasons and seeking clarification of the position from the User.

    - The User shall respond to The Company within 15 Business Days of the date of the Preliminary Request providing such information or data as is necessary to satisfy The Company’s concerns set out in the Preliminary Request and making any amendments necessary to the report provided by the User pursuant to Clause 2.8 and /or data provided by the User to The Company to reflect this.

    - In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.2 by the User that the Developer’s Equipment will be such that it will be capable of generating at the Developer Capacity The Company shall notify the User accordingly.

    - In the event that the User does not respond to the Preliminary Request or, notwithstanding the User’s response, The Company remains of the view that the Developer’s Equipment will be such that it will not reasonably be capable of generating at the Developer Capacity , The Company shall inform the User and the Developer in writing that it intends to amend the Developer Capacity in this Construction Agreement [and the associated BELLA] to reflect the whole MW figure that it reasonably believes the Developer's Equipment will be capable of generating at.

    - The User shall respond to the Notice of Intent within 15 Business Days of the date of the Notice of Intent explaining why it still reasonably believes that the Developer's Equipment will be capable of generating at the Developer Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or providing a reasonable explanation as to why this is not the case.

    - In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.5 by the User that the Developer’s Equipment will be such that it will be capable of generating at the Developer Capacity The Company shall notify the User accordingly.

7.4.7	Where notwithstanding the User’s response The Company remains of the view that the Developer’s Equipment will be such that it will not be capable of generating at the Developer Capacity or at or at more than the MW figure proposed by The Company in the Notice of Intent or the User does not provide a response that is satisfactory to The Company within the timescale specified in Clause 7.4.5 above The Company will issue the Notice of Reduction to the User and the Developer and will send a copy of the same to the Authority.

7.4.8	Unless during such period the matter has been referred by the User to the Authority for determination by the Authority under the provisions of condition E13.5 of the ESO Licence, the Notice of Reduction shall take effect on the day 15 Business Days after the date of the Notice of Reduction and the Developer Capacity in this Construction Agreement [and Appendix A of the associated BELLA] shall be amended on that date in the manner set out in the Notice of Reduction.  Where the matter has been referred the amendments to Appendix A of the associated BELLA and the date they take effect shall be as set out in the Authority’s determination.

7.4.9	After a Notice of Reduction has taken effect The Company shall be entitled to make such amendments to this Construction Agreement as it requires as a result of the reduction in the Developer Capacity effected by the Notice of Reduction and as a consequence to the [Bilateral Connection Agreement or Agreement to Vary] [and BELLA]. The Company shall advise the User as soon as practicable and in any event within 3 months of the date of the Notice of Reduction (or if the matter has been referred by the User [and BELLA] to the Authority, the date of determination) of such amendments by way of agreement(s) to vary. The agreement to vary will also provide for payment by the User of the Reduction Fee and on such reduction in Developer Capacity taking effect the User shall pay the Cancellation Charge in respect of the reduction such payment to be made within 14 days of the date of The Company’s invoice in respect thereof. The parties acknowledge that any dispute regarding this variation shall be referable to and determined by the Authority under the provisions of condition E13.5 of the ESO Licence.”]

    - Where as a result of the reduction in the Developer Capacity effected by the Notice of Reduction the Developer is no longer an Embedded Exemptable Large Power Station and as a result the BELLA is to be terminated as provided for in the BELLA then the following provisions shall apply:

      - The agreement to vary referred to in Clause 7.4.9 above shall also provide for such amendments as are necessary to the Construction Agreement and [Bilateral Connection Agreement or Agreement to Vary] to reflect the fact that the Developer is no longer to be party to a BELLA but is a Relevant Embedded Power Station.

      - Where The Company determines that the reduction in the Developer Capacity effected by the Notice of Reduction is such that if a Transmission Evaluation Application had been made by the User on the basis of that reduced Developer Capacity on the same date as, but instead of, the Developer’s application for the BELLA then no works would have been required on the National Electricity Transmission System then The Company shall be entitled to terminate this Construction Agreement and the provisions of Clause 11 shall apply. In such case The Company shall be entitled to make such amendments as are necessary to the [Bilateral Connection Agreement or Agreement to Vary] to reflect the fact that the Developer is no longer party to a BELLA but is a Relevant Embedded Power Station.

      - The Company and the User shall treat the Developer as if it had been a Relevant Embedded Power Station at the time of its application for a BELLA and for the purposes of CUSC Paragraph 6.5 as if a) the Developer’s application for the BELLA had been a Transmission Evaluation Application under CUSC 6.5.5, b)  this Construction Agreement had been entered into as a result of the Modification Application referred to in CUSC Paragraph 6.5.5.5, c) the Notice of Reduction is a revised Transmission Evaluation Application from the User under CUSC Paragraph 6.5.5.8 by reference to the reduction in the Developer Capacity effected by the Notice of Reduction and d) the agreement to vary referred to in Clause 7.4.10.1 or 7.4.10.2 as The Company’s response to the User’s revised Transmission Evaluation Application and the provisions of CUSC Paragraph 6.5 shall apply on that basis.

7.5	Where there is a reduction in Developer Capacity under Clause 7.4 prior to the Charging Date, on such reduction in Developer Capacity taking effect the User shall pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice in respect thereof.

8.	Compliance with Site Specific Technical Conditions

The User shall ensure that on the Completion Date the User's Equipment complies with the site specific technical conditions set out in Appendices F1-5 to the Bilateral Connection Agreement .

9.	PROVISION OF SECURITY

Where required to do so under CUSC Section 15, the User shall provide The Company with security arrangements in accordance with CUSC Section 15 Part Three in respect of the User’s obligations to pay the Cancellation Charge to The Company on termination of this Construction Agreement or a reduction in [Transmission Entry Capacity] [Developer Capacity] prior to the Charging Date.

10.	EVENT OF DEFAULT

Once any of the Events of Default in Paragraph 5.3.1 and/or Paragraph 5.4.6.2 and/or Paragraph 5.4.6.3 of the CUSC has occurred and is continuing The Company may give notice of termination to the User whereupon this Construction Agreement shall forthwith terminate and the provisions of Clause 11 shall apply.

11.	TERMINATION

11.1	On termination of this Construction Agreement The Company shall disconnect all the User’s Equipment at the Connection Site and:

(a)		the User shall remove any of the User’s Equipment on the Relevant Transmission Licensee's land within 6 months of the date of termination or such longer period as may be agreed between the Relevant Transmission Licensee  and the User; and

### (b)	The Company shall procure that the Relevant Transmission Licensee removes, any Transmission Connection Assets on the User’s land within 6 months of the date of termination or such longer period as may be agreed between the Relevant Transmission Licensee and the User.

11.2	The User shall  where  this Construction Agreement terminates prior to the Charging Date be liable forthwith on the date this Construction Agreement so terminates to pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice in respect thereof.

12.	TERM

12.1	Subject to the provisions for earlier termination set out in the CUSC this Construction Agreement shall continue until terminated in accordance with Clause 2.5, 2.6, 4.8, 11 or 17 hereof.

12.2	In addition this Construction Agreement shall terminate upon termination of the associated Bilateral Connection Agreement and in the event that this is prior to the Charging Date the User the provisions of Clause 11 shall apply.

12.3	The associated [Bilateral Connection Agreements or Agreement to Vary the Bilateral Connection Agreement] will automatically terminate upon termination of this Construction Agreement prior to the Charging Date.

12.4	Any provisions for payment shall survive termination of this Construction Agreement.

13.	CUSC

The provisions of Sections 6.6 (Payment), 6.14 (Transfer and Subcontracting), 6.15 (Confidentiality), 6.18 (Intellectual Property), 6.19 (Force Majeure), 6.20 (Waiver), 6.21 (Notices), 6.22 (Third party Rights), 6.23 (Jurisdiction), 6.24 (Counterparts), 6.25 (Governing Law), 6.26 (Severance of Terms), 6.27 (Language), 6.38 (Directions related to national security) inclusive of the CUSC shall apply mutatis mutandis to this Construction Agreement as if set out in this Construction Agreement.

14.	DISPUTES

14.1	Except as specifically provided for in this Construction Agreement any dispute arising under the terms of this Construction Agreement shall be referred to arbitration in accordance with the Dispute Resolution Procedure.

15.	VARIATIONS

15.1	Subject to Clause 15.2 and 15.3 below, no variation to this Construction Agreement shall be effective unless made in writing and signed by or on behalf of both The Company and the User.

15.2	The Company and the User shall effect any amendment required to be made to this Construction Agreement by the Authority as a result of a change in the CUSC, the ESO Licence or the Transmission Licence, an order or direction made pursuant to the Act or a Licence, or as a result of settling any of the terms hereof. The User hereby authorises and instructs The Company to make any such amendment on its behalf and undertakes not to withdraw, qualify or revoke such authority or instruction at any time.

15.3	The Company has the right to vary Appendices in accordance with Clauses 2.3, 2.11 and 7.4 and 7.5 and 17 and Paragraph 6.9 of the CUSC.

[Users in the capacity of a Directly Connected Distribution System insert the

following:

16. Distributed Generation

16.1 	In consideration of and recognising the provisions at Clause 16.4 of this

Construction Agreement and notwithstanding that the liability for the Cancellation Charge rests with the User, the User will within 5 Business Days of receipt of the same provide the Developer with a copy of the Cancellation Charge Secured Amount Statement.

16.2 	Where this Construction Agreement is entered into by reference to and

provides for the Construction Works required as a consequence of more

than one Developer a Cancellation Charge, Cancellation Charge Statement and Cancellation Charge Secured Amount will be prepared by reference to each Developer and the reference to “Cancellation Charge” “Developer” and “Developer Capacity” in this Construction Agreement and CUSC Section 15 shall be construed accordingly.

16.3 	In the event that the/a Developer reduces its Developer Capacity and/or terminates its agreement for connection to the Distribution System the User shall notify The Company in writing within 5 Business Days of that event.

16.4 In the event of a Cancellation Charge Shortfall:

16.4.1 On application by the User in writing (which cannot be made prior to

the Shortfall Application Date and without the conditions at Clause 16.5 having been met), The Company shall pay the Cancellation Charge Shortfall to the User together with interest calculated thereon on a daily basis at Base Rate from the date of the payment of the Cancellation Charge to The Company by the User to the date of the payment of the Cancellation Charge Shortfall by The Company to the User.

16.4.2	The User shall keep The Company advised as to any ongoing process to recover the Cancellation Charge Shortfall and any associated interest charges from the Developer and notify The Company when it has reasonable grounds to believe that it is not practicable to take any further action) to recover the Cancellation Charge Shortfall from the Developer.

16.4.3	If at any time the User subsequently successfully recovers the Cancellation Charge Shortfall in full or part from the Developer, the User shall forthwith notify The Company and pay the amount received to The Company together with interest calculated thereon on a daily basis at Base Rate from the date of the payment of the Cancellation Charge Secured Amount to The Company by the User to the date of the payment of the Cancellation Charge Shortfall by the User to The Company.

16.5	In order for the User to make an application for payment of a Cancellation Charge Shortfall the following conditions must have been met and evidence of this provided to The Company by the User with the application.

- that the User asked the Developer whether or not it wishes the User to elect for the Fixed Cancellation Charge and elected accordingly; and

ii) 	(in respect of its liability for the Cancellation Charge as it relates to this Contruction Agreement) for each Security Period the User only sought security from the Developer for the amount as set out in the Cancellation Charge Secured Amount Statement for that Security Period]

17	QUEUE MANAGEMENT PROCESS

17.1	The Queue Management Process shall be incorporated into this Construction Agreement and apply between The Company and the User and Appendix Q to this Construction Agreement has been prepared in accordance with the principles set out in CUSC Section 16.

17.2	Where, in accordance with the Queue Management Process:

17.2.1	in the case of any of the Conditional Progression Milestones, the status of the User’s project at the end of the Project Milestone Remedy Period is categorised as “Termination”, The Company will terminate this Construction Agreement by notice in writing (such notice being not less than 10 Business Days); and

17.2.2	in the case of any of the Construction Progression Milestones, the status of the User’s project at the end of the Project Milestone Remedy Period is categorised as “Termination”, The Company may terminate this Construction Agreement by notice in writing (such notice being not less than 10 Business Days) and on such termination the provisions of Clause 11 of this Construction Agreement shall apply.

17.3	Where in accordance with the Queue Management Process there is a variation to the date by which a User Progression Milestone has to be met The Company shall revise Appendix Q to this Construction Agreement as required to reflect such change.

17.4	Any dispute or difference between The Company and the User on the Queue Management Process in respect of this Construction Agreement shall be resolved as an Other Dispute under the Dispute Resolution Procedure.

[18	Distribution Queue Management

The User will keep The Company advised as to the categorisation of the [User’s project/Developer’s Project] in the Distribution Queue Management Process and notify The Company as soon as practicable if the categorisation of the [User’s project/Developer’s Project]  is changed to “Termination” and if and when, in accordance with that process, the Distribution Connection Agreements are terminated.]

IN WITNESS WHEREOF the hands of the duly authorised representatives of the parties hereto at the date first above written

SIGNED BY	)

[name]	)

for and on behalf of	)

National Energy System Operator	)

Limited	)

SIGNED BY	)

[name]	)

for and on behalf of	)

[User]	)

APPENDIX [B]

ONE OFF WORKS

APPENDIX [G]

TRANSMISSION CONNECTION ASSET WORKS

APPENDIX [H]

TRANSMISSION REINFORCEMENT WORKS

Part 1	Enabling Works

Part 2	Wider Transmission Reinforcement Works

APPENDIX [I]

USER’S WORKS

APPENDIX [J]

CONSTRUCTION PROGRAMME

APPENDIX [K]

LIQUIDATED DAMAGES

Company:

Connection site:

Type:

The amount of Liquidated Damages payable by The Company to the User pursuant to this Construction Agreement shall be:

Liquidated Damages under Clause [4] of this Construction Agreement shall be calculated on a daily basis at a rate of £XXXXX per week subject to the limit that the total Liquidated Damages payable by The Company to the User under this Clause shall not exceed £XXXXX.

APPENDIX [L]

INDEPENDENT ENGINEER

Company:

Connection site:

Type:

The Independent Engineer will be a Member of the Association of Consulting Engineers (ACE)  and shall be agreed between the parties within 120 days of execution of this Construction Agreement or such other period as may be agreed between the parties. Failing agreement it shall be referred to the President of the Institution of Electrical Engineers who shall nominate the Independent Engineer.

APPENDIX [MM]

ATTRIBUTABLE WORKS AND KEY CONSENTS

Part 1	Attributable Works

Part 2	Key Consents

APPENDIX [N]

THIRD PARTY WORKS

APPENDIX [O][P]

[GATE 1 VERSIONS

USER’S DATA

Power Station/other

Location of Power station/other

Connection Site [(provided for indicative purposes only and subject to Clause 1.2)] [Reserved (subject to Clause 1.2]

Indicative Site of Connection [(provided for indicative purposes only and subject to Clause 1.2)] [Reserved subject to Clause 1.2]

Transmission Entry Capacity/ Demand [requested] [Reserved subject to Clause 1.2]

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date [(provided for indicative purposes only and subject to Clause 1.2)] [Reserved subject to Clause 1.2] when Power Station’s/other connection to\use of the National Electricity Transmission System/Distribution System will be energised.

DEVELOPER’S DATA

Power Station

Location of Power station

Connection Site (GSP) [(provided for indicative purposes only and subject to Clause 1.2)] [Large BEGA and BELLA only - Reserved subject to Clause 1.2]

Site of Connection [(provided for indicative purposes only and subject to Clause 1.2)] [Large BEGA and BELLA only - Reserved subject to Clause 1.2]

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date [(provided for indicative purposes only and subject to Clause 1.2)] [Large BEGA and BELLA only - Reserved subject to Clause 1.2]

when Power Station’s connection to\use of the Distribution System will be energised.

APPENDIX [O][P]

[GATE 2 VERSIONS

USER’S DATA

Power Station/other

Location of Power station/other

Connection Site

Site of Connection

Transmission Entry Capacity/ Demand (as set out in Appendix C of Bilateral Connection Agreement/Bilateral Embedded Generation Agreement)

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date when Power Station’s/other connection to\use of the National Electricity Transmission System/Distribution System will be energised.

Installed Capacity

DEVELOPER’S DATA

Power Station

Location of Power station

Connection Site (GSP)

Site of Connection

Developer Capcity

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date when Power Station’s connection to\use of the Distribution System will be energised.

Installed Capacity

APPENDIX [Q]

QUEUE MANAGEMENT PROCESS – USER PROGRESSION MILESTONES

The table below specifies the dates (derived in accordance with CUSC Section16) for the User Progression Milestones in respect of the User’s project and the application of the Queue Management Process.

Conditional Progression Milestones

| Milestone | Date due |
| --- | --- |
| M1 – Initiate Planning Consent |  |
| M2 – Secure Consent |  |
| M3 – Land Rights |  |

Construction Progression Milestones

| Milestone | Date due |
| --- | --- |
| M5 – Contestable Design Works Submission |  |
| M6 – Agree Construction Plan |  |
| M7 – Project Commitment |  |
| M8 – Initiate Construction |  |

# SCHEDULE 2 EXHIBIT 3

## PART 2

### For use with Users other than in the categories referred to in PART 1. This includes, where associated with Distributed Demand, a Distribution System directly connected to the National Electricity Transmission Process though, as Distributed Demand is not subject to the Gated Application and Offer Process adaptions may be required to reflect this.

### Please note unlike Part 1 this construction agreement reflects and is based on the fact that the Connect and Manage Arrangments do not apply to these categories

### Please note that the Queue Management Process will not be applied and included in Construction Agreements with the owner/operator of a Distribution System directly connected to the National Electricity Transmission System where the Construction Agreement is  required because of a connection to that Distribution System and the Distribution Queue Management Process applies

INDICATIVE

DATED [   ] 200[1]

NATIONAL ENERGY SYSTEM OPERATOR LIMITED		(1)

and

[					]		(2)

THE  CONNECTION AND USE OF SYSTEM CODE

CONSTRUCTION AGREEMENT

CONTENTS

| Clause | Title |
| --- | --- |
| 1 | Definitions, Interpretation and Construction |
| 2 | Carrying out of the Works |
| 3 | Delays |
| 4 | Commissioning Programme and Liquidated Damages |
| 5 | Approval to Connect/Energise/Become Operational |
| 6 | Independent Engineer |
| 7 | Becoming Operational |
| 8 | Compliance with Site Specific Technical Conditions |
| 9 | Provision of Security |
| 10 | Event of Default |
| 11 | Termination |
| 12 | Term |
| 13 | CUSC |
| 14 | Disputes |
| 15 | Variations |
| [16 | Queue Management Process] |
| [17 | Distribution Queue Process] |
| Appendix B | One Off Works |
| Appendix G | Transmission Connection Asset Works |
| Appendix H | Transmission Reinforcement Works |
| Appendix I | User's Works |
| Appendix J | Construction Programme |
| Appendix K | Liquidated Damages |
| Appendix L | Independent Engineer |
| Appendix MM | Attributable Works and Key Consents |
| Appendix N | Third Party Works |
| Appendix [O][P] | User’s Data/Developer’s Data |
| Appendix Q | Queue Management Process - User Progression Milestones |

THIS CONSTRUCTION AGREEMENT is made on the [   ] day of [   ] 200[1]

BETWEEN

(1)	The company registered in England with number 11014226 (“The Company”, which expression shall include its successors and/or permitted assigns); and

(2)	[   ] a company registered in [   ] with number [   ] whose registered office is at [   ] (“User”, which expression shall include its successors and/or permitted assigns)

WHEREAS

(A)	Pursuant to the ESO Licence, The Company has prepared a Connection and Use of System Code (CUSC) setting out the terms of the arrangements for connection to and use of the National Electricity Transmission System and the provision of certain Balancing Services.

(B)	The User has applied for [connection to] [and use of] [modification to its connection to] [or use of] the National Electricity Transmission System and  pursuant to condition E12 of the ESO Licence, The Company is required to offer terms in accordance with the CUSC in this respect or [specific recital to reflect that the Construction Agreement is an amendment of an existing signed offer pursuant to the CUSC amending documents]

(C) 	The Company and the User are parties to the CUSC Framework Agreement (being an agreement by which the CUSC is made contractually binding between the parties).

(D)	Certain works are required as part of this offer as set out in this Construction Agreement.

(E)	This Construction Agreement is entered into pursuant to the terms of the CUSC.

(F)	[This Construction Agreement is subject to the Queue Management Process].

(G)	This Construction Agrement is a [Gate 1 Agreement] [Gate 2 Agreement].

NOW IT IS HEREBY AGREED as follows:

## 1.	DEFINITIONS, INTERPRETATION AND CONSTRUCTION

Unless the subject matter or context otherwise requires or is inconsistent therewith, terms and expressions defined in Section 11 of the CUSC and in the Bilateral Connection Agreement have the same meanings, interpretations or constructions in this Construction Agreement.

| “Attributable Works” | those Construction Works identified as such in accordance with the User Commitment Methodology and which are set out in Appendix MM Part 1. |
| --- | --- |
| "Authority" | as defined in the CUSC. |
| “Bilateral Connection Agreement” | the Bilateral Connection Agreement entered into between the parties on even date herewith. |
| “Cancellation Charge” | as calculated in accordance with the User Commitment Methodology. |
| "Charging Date" | the date upon which the Construction Works are first Commissioned and available for use by the User or if the Independent Engineer before, on or after the Commissioning Programme Commencement Date shall have certified in writing that the Transmission Connection Assets, are completed to a stage where The Company could commence commissioning and by such date the User’s Works shall not have been so certified then the date falling [ ] days after the date of such certification, provided that the Transmission Reinforcement Works are Commissioned and Network Options Assessment Works are completed as at that date. In the event that the Transmission Reinforcement Works are not so Commissioned and/or the Network Options Assessment Works are not so completed the Charging Date shall be the date on which they are Commissioned and/or completed as appropriate. |
| “Commissioning Programme Commencement Date” | the date specified in the Construction Programme for the commencement of the Commissioning Programme or any substituted date fixed under the terms of this Construction Agreement |
| “Commissioning Programme” | the sequence of operations/tests necessary to connect the User’s Works and the Transmission Connection Asset Works to the National Electricity Transmission System for the purpose of making the User's Works available for operation to be determined pursuant to Clause 2.10 of this Construction Agreement. |
| “Completion Date” | [ ] or such other date as may be agreed in terms of this Construction Agreement for completion of the Construction Works. |
| “Connected Planning Data” | data required pursuant to the Planning Code which replaces data containing estimated values assumed for planning purposes by validated actual values and updated estimates for the future and by updated forecasts for forecast data items. |
| “Consents” | in relation to any Works:- (a) all such planning and other statutory consents; and (b) all wayleaves, easements, rights over or interests in land or any other consent; or (c) permission of any kind as shall be necessary for the construction of the Works and for commencement and carrying on of any activity proposed to be undertaken at or from such Works when completed. |
| “Construction Programme” | the agreed programme for the Works to be carried out by The Company and the User set out in detail in Appendix [J] to this Construction Agreement or as amended from time to time pursuant to Clauses 2.3 and 3.2 of this Construction Agreement. |
| "Construction Site" | the site where the Transmission Connection Asset Works are being undertaken by or on behalf of The Company; |
| “Construction Works” | the Transmission Connection Asset Works, Transmission Reinforcement Works, Network Options Assessment Works and One Off Works and such additional works as are required in order to comply with any relevant Consents relating to any such works but excluding for the avoidance of doubt any Third Party Works. |
| “Dispute Resolution Procedure” | the procedure for referral to arbitration set out in Paragraph 7.4 of the CUSC. |
| “Developer” | [insert name address and registered number] who is party to the Distribution Connection Agreements with the User |
| “Developer’s Project” | the connection of a [ ] to the User's Distribution System |
| “Embedded Demand Capacity” | the MW figure [for import] specified in the Developer’s Data. |
| “Event of Default” | any of the events set out in Clause 10 of this Construction Agreement as constituting an event of default. |
| “Gate 2 Date” | means [the date on which the last of the conditions at Clause 1.2 of this Construction Agreement are satisfied - include only in Gate 1 Agreements with Reservation] |
| “Independent Engineer” | the engineer specified in Appendix L to this Construction Agreement. Provided that:- (a) where the parties fail to agree on a suitable engineer within 120 days of the date of this Construction Agreement; or |
|  | (b) where any Independent Engineer appointed from time to time shall fail, refuse or cease to act in the capacity set out herein and no substitute engineer of suitable standing and qualification can be agreed by the parties within 30 days; then such engineer as the President of the Institution of Electrical Engineers shall, on the application of either party, nominate shall be the Independent Engineer. |
| “Installed Capacity” | the installed capacity provided in the Original Red Line Boundary and set out in Appendix [O][P]. |
| “Key Consents” | those Consents required in respect of the [User’s/Developer’s] [project] which The Company has identified as such and which are set out in Appendix MM Part 2. |
| “Liquidated Damages” | the sums specified in or calculated pursuant to Appendix K to this Construction Agreement. |
| “Network Options Assessment Works” | the works set out in the Networks Options Assessment report prepared by The Company pursuant to C13 of the ESO Licence and issued by The Company in [ ] which in The Company’s reasonable opinion are required to be completed before the Completion Date to ensure that the National Electricity Transmission System complies with the requirements of condition E7 of the ESO Licence and Standard Condition D3 of any Relevant Transmission Licensee’s transmission licence prior to the Connection of the User’s Equipment in terms of Clause 7.1 [or 7.2] of this Construction Agreement. |
| Notice of Intent | the notice issued by The Company pursuant to Clause 7.3.4. |
| Notice of Reduction | the notice issued by The Company pursuant to Clause 7.3.7 including a revised Appendix C specifying the revised Transmission Entry Capacity. |
| “One Off Works” | the works described in Appendix B1 to this Construction Agreement. |
| Preliminary Request | the request issued by The Company pursuant to Clause 7.3.1. |
| Reduction Fee | the fee payable by the User to The Company in respect of the agreement to vary issued pursuant to Clause 7.3.9 such fee being calculated on the same basis as that set out in the Charging Statements as payable on a payment of actual costs basis in respect of a Modification Application. |
| [“Reservation Expiry Date” | [ ] being the date as bilaterally negotiated between The Company and the User [and which may be extended by agreement between the parties] on which the Reservation expires.- include only in Gate 1 Agreements with Reservation] |
| “Term” | the term of this Construction Agreement commencing on the date hereof and ending in accordance with Clause 12. |
| “Third Party Works” | the works to be undertaken on assets belonging to a party other than a Revelvant Transmission Licensee and the User to enable The Company to provide or as a consequence of the connection to and\or use of the National Electricity Transmission System by the User as specified in Appendix N; |
| "Transmission Connection Assets" | the assets specified in Appendix A to the Bilateral Connection Agreement. |
| “Transmission Connection Asset Works” | the works necessary for construction and installation of the Transmission Connection Assets at the Connection Site specified in Appendix G to this Construction Agreement. |
| “Transmission Reinforcement Works” | those works other than the Transmission Connection Asset Works, ) Network Options Assessment Works and One Off Works, which in the reasonable opinion of The Company are all necessary to extend or reinforce the National Electricity Transmission System to ensure that the National Electricity Transmission System complies with the requirements of condition E7 of the ESO Licence and Standard Condition D3 of any Relevant Transmission Licensee’s transmission system in relation to and prior to the connection of the User’s Equipment at the Connection Site and which are specified in Appendix H to this Construction Agreement, where Part 1 is works required for the User and Part 2 is works required for wider system reasons. |
| “Trigger Date” | [date] as identified in accordance with the User Commitment methodology. |
| “User Progression Milestones” | the milestones (applied in accordance with CUSC Section 16) for the User’s project as set out in Appendix Q of this Construction Agreement. |
| “User’s Works” | those works necessary for installation of the User’s Equipment which are specified in Appendix I to this Construction Agreement. |
| “Works” | the Construction Works and the User’s Works. |

- [A Gate 1 Agreement with/without Reservation only]

- 1.2	GATED Application AND OFFER PRocess – GATE 1 Conditional Clause [AND RESERVATION]

1.2.1	The rights and obligations of the User and The Company under this Construction Agreement [and the [Bilateral Connection Agreement] are conditional on:

1.2.1.1	the User making a Gate 2 Application;

1.2.1.2	the Gate 2 Application meeting the Gate 2 Criteria; and

1.2.1.3	the User accepting the terms of the Gate 2 Offer

1.2.2	The parties agree that until the Gate 2 Date, the rights and obligations of each party pursuant to this Construction Agreement (other than this Clause 1.2 and Clause 13 – and any other provisions that the parties agree are appropriate) and the [Bilateral Connection Agreement] shall be suspended.

1.2.3	[The parties further agree that the information provided for the purposes of this Gate 1 Agreement and set out in the Appendix [O] to this Construction Agreement being a proposed Connection Site, Completion Date and requested [capacity] are indicative only prior to the Gate 2 Date and shall not be binding on the parties or confer any commitment  by The Company to the Connection Site, Completion Date or requested [capacity] and any reliance on them for any purpose prior to the Gate 2 Date is at the User’s risk – no reservation] [The parties further agree that the Connection Site and Completion Date and [capacity] as set out in Appendix [O][P] to this Construction Agreement have been Reserved for the purposes of this connection/use of system and any Gate 2 Offer will reflect this position and the requested [capacity] provided that the Gate 2 Application is made prior to the Reservation Expiry Date and the Gate 2 Offer is accepted- reservation only].

1.2.4	At any time prior to the Gate 2 Date, the User shall have the right to terminate this Connection Agreement by written notice to The Company without any liability for any Cancellation Charge. This right to terminate shall expire with effect from the Gate 2 Date.

1.2.5		With effect from the [Gate 2 Date] the provisions of this Construction Agreement, as amended by the [Gate 2 Offer] by agreement of the parties, shall be in full force and effect.

## 2	CARRYING OUT OF THE WORKS

### 2.1	Forthwith following the date of this Construction Agreement the User shall agree with the Relevant Transmission Licensee the Safety Rules and Local Safety Instructions to apply during the Construction Programme and Commissioning Programme.  Failing agreement within three months of the date of this Construction Agreement the matter shall be referred to the Independent Engineer for determination in accordance with Clause 6 of the Construction Agreement.

### 2.2	Subject to Clauses 2.3 and 2.4 of this Construction Agreement forthwith following the date of this Construction Agreement The Company shall use its best endeavours to obtain in relation to the Construction Works, and the User shall use its best endeavours to obtain in relation to the User's Works, all Consents.  Each shall give advice and assistance to the other to the extent reasonably required by the other in the furtherance of these obligations.  Further, each party shall, so far as it is legally able to do so, grant to the other, or the Relevant Transmission Licensee, all such wayleaves, easements, servitude rights, rights over or interests (but not estates as regards land in England and Wales and not heritable or leasehold interests as regards land in Scotland) in land or any other consents reasonably required by the other or the Relevant Transmission Licensee in order to enable the Works to be expeditiously completed and to enable that other to carry out its obligations to the other under this Construction Agreement and in all cases subject to such terms and conditions as are reasonable.

### 2.3	The following additional provisions shall apply in respect of the Consents and Construction Works:-

#### 2.3.1	All dates specified in this Construction Agreement are subject to The Company obtaining Consents for the Construction Works in a form acceptable to it within the time required to carry out the Construction Works in accordance with the Construction Programme.

#### 2.3.2	In the event of:-

##### (a)	the Consents not being obtained by the required date; or

##### the Consents being subject to conditions which affect the dates; or

##### The Company wishing to amend the Construction Works to facilitate the granting of the Consents,

The Company shall be entitled to revise the Construction Works (and as a consequence Appendix A to the Bilateral Connection Agreement) and all dates specified in this Construction Agreement and the charges specified in Appendix B to the Bilateral Connection Agreement.  For the avoidance of doubt such revisions shall be at The Company 's absolute discretion and the consent of the User is not required.

#### 2.3.3	The User shall be regularly updated by The Company in writing or by such other means as the parties may agree as to progress made by The Company from time to time in the obtaining of relevant Consents pursuant to its obligations under Clause 2.2 or 2.3 of this Construction Agreement.

2.4	Paragraphs 11.2.3 to 11.2.5 of the CUSC relating to Consents shall apply to the Construction Agreement as if set out here in full.

2.5	Prior to the commencement of the Transmission Connection Asset Works the User shall have the right to terminate this Construction Agreement upon giving not less than 7 (seven) days notice in writing to The Company.  In the event of the User terminating this Construction Agreement in terms of this Clause 2.5 the provisions of Clause 11 shall apply.

2.6	If the User fails to obtain all Consents for the User's Works having complied with the obligations in Clause 2.2 of this Construction Agreement the obligation on the User to complete the User's Works shall cease and the User may by written notice to The Company terminate this Construction Agreement and the provisions of Clause 11 shall apply.

2.7	Both parties shall be entitled to contract or sub-contract for the carrying out of their respective parts of the Works (which in the case of The Company shall include work carried out by a Relevant Transmission Licensee or its contractors or sub-contractors).  The User or any contractor on its behalf shall be responsible for commencing and for carrying out the User's Works to such stage of completion as shall render them capable of being Commissioned in accordance with the Construction Programme and The Company or any contractor on its behalf shall be responsible for commencing and carrying out the Construction Works to such stage of completion as shall render them capable of being Commissioned in accordance with the Construction Programme.

2.8	The parties shall continuously liaise throughout the Construction Programme and Commissioning Programme and each shall provide to the other all information relating to its own Works reasonably necessary to assist the other in performance of that other’s part of the Works, and shall use all reasonable endeavours to coordinate and integrate their respective part of the Works.  There shall be on-site meetings between representatives of the parties at intervals to be agreed between the parties.  Each party shall deliver to the other party a written report of progress during each calendar quarter within 7 days of the end of that quarter.

Users in the capacity of a Directly Connected Distribution System where works are required in respect of Distributed Demand insert the following:

[2.8	The parties shall continuously liaise throughout the Construction Programme and Commissioning Programme and each shall provide to the other all information relating to its own Works reasonably necessary to assist the other in performance of that other’s part of the Works, and shall use all reasonable endeavours to coordinate and integrate their respective part of the Works. There shall be on-site meetings between representatives of the parties at intervals to be agreed between the parties. The User shall also provide to The Company such information as The Company shall reasonably request and which the User is entitled to disclose in respect of the Developer’s Project. Each party shall deliver to the other party where requested a written report of progress during each calendar quarter (including in the case of the User progress on the Developer’s Project to the extent that the User has such information and is entitled to disclose it) within 7 days of the end of that quarter.”]

2.9	During the period of and at the times and otherwise as provided in the Construction Programme and the Commissioning Programme The Company shall allow the User, its employees, agents, suppliers, contractors and sub-contractors necessary access to the Construction Site and the User shall allow the Relevant Transmission Licensee and in either case their employees, agents, suppliers, contractors and sub-contractors necessary access to its site to enable each to carry out the Transmission Connection Asset Works and One Off Works or User's Works but not so as to disrupt or  delay the construction and completion of the other’s Works on the said sites or the operation of the other’s Plant and Apparatus located thereon, such access to be in accordance with any reasonable regulations relating thereto made by the site owner or occupier.

2.10	Not later than six months prior to the Commissioning Programme Commencement Date The Company shall provide the User with a draft Commissioning Programme for the Commissioning of the Transmission Connection Assets, and the User's Equipment.  The User shall, as quickly as practicable and in any event within three months of receipt thereof, determine whether or not to approve the proposed Commissioning Programme (which approval shall not be unreasonably withheld or delayed) and shall within such three month period either notify The Company of its approval or, in the event that the User reasonably withholds its approval, notify The Company of any changes or variations to the proposed commissioning programme recommended by the User.  If The Company does not accept such changes or variations submitted by the User any dispute shall be referred to the Independent Engineer for determination.  The Commissioning Programme agreed between the parties or determined by the Independent Engineer as the case may be shall be implemented by the parties and their sub-contractors in accordance with its terms.

2.11	If at any time prior to the Completion Date it is necessary for The Company or The Company in its reasonable discretion wishes to make any addition to or omission from or amendment to the Transmission Connection Asset Works and/or Transmission Reinforcement Works and/or the One Off Works and/or the Third Party Works The Company shall notify the User in writing of such addition, omission or amendment and Appendices [B1 (One Off Works), G (Transmission Connection Asset Works) H (Transmission Reinforcement Works). MM (Attributable Works)  and N (Third Party Works)] to this Construction Agreement and consequently Appendices [A (Transmission Connection Assets) and B (Connection Charges and One Off Charges)] to the associated Bilateral Connection Agreement shall be automatically amended to reflect the change. Provided that where a User has elected for the Actual Attributable Works Cancellation Charge to be based on the Fixed Attributable Works Cancellation Charge the Attributable Works can only be changed after the Trigger Date as provided for in CUSC Section 15.

### 2.12	[The User shall apply to the Secretary of State for Trade and Industry as part of its application under Section 36 of the Act for its generating station, for deemed planning permission in relation to the substation forming part of the Transmission Connection Asset Works.  The User shall use its best endeavours to procure that the said deemed planning permission is so obtained.  The Company's obligations under Clause 2.2 of this Construction Agreement shall not require it to obtain planning consent for the said substation unless and until the relevant Secretary of State shall for whatever reason refuse to deem the grant of planning permission in respect of the same.  The User shall liaise with The Company as to its construction and operational requirements and shall ensure that the said application meets The Company's requirements.  The Company shall provide the User with all information reasonably required by it in relation to the application and the User shall ensure that all requirements of The Company are incorporated in the application for deemed planning consent.]

2.13	[The Transmission Reinforcement Works are conditional on British Energy Generation Limited and/or Magnox Electric plc (as the case may be)granting approval to the carrying out of the Construction Works in terms of the Nuclear Site Licence Provisions Agreement being an agreement dated 30 March 1990 between The Company and Nuclear Electric plc (now called Magnox Electric plc) and an agreement dated 31 March 1996 between The Company and British Energy Generation Limited (and described as such).  In the event of British Energy Generation Limited and/or Magnox Electric plc (as the case may be) not granting approval The Company shall be entitled to change the Construction Works, the Construction Programme and all dates specified in this Construction Agreement.]

2.14	[It is hereby agreed and declared for the purposes of the Construction (Design and Management) Regulations 1994 that the User is the only client in respect of the User's Works and The Company is the only client in respect of the Construction Works and each of the User and The Company shall accordingly discharge all the duties of clients under the said Regulations.]

2.15	[The Company and the User hereby agree and acknowledge that this Construction Agreement is not to be treated as a construction contract within the meaning of section 104 of the Housing Grants, Construction and Re-generation Act 1996 and sections 104 to 113 of the said Act shall have no application either to the Construction Works or the User's Works and the parties’ rights and obligations with regard to matters of dispute resolution and payment procedures are as expressly set out herein.

2.16	Third Party Works

2.16.1	The User shall be responsible for carrying out or procuring that the Third Party Works are carried out and shall carry them out or procure that they are carried out in accordance with the timescales specified in the Construction Programme. The User shall confirm to The Company or, where requested to do so by The Company, provide confirmation from the third party that the Third Party Works have been completed.

2.16.2	Given the nature of these works it may not be possible to fully identify the works required or the third parties they relate to at the date hereof. Where this is the case The Company shall, subject to 2.x.3 below, advise the User as soon as practicable and in any event by [  ] of the Third Party Works and shall be entitled to revise Appendix N and as a consequence the Construction Programme as necessary to reflect this.

2.16.3 Where Third Party Works are likely to be Modifications required to be made by another user(s) (“the “First User(s)”) as a consequence of Modifications to the National Electricity Transmission System to be undertaken by The Company under this Construction Agreement The Company shall as soon as practicable after the date hereof issue the notification to such First User’s in accordance with CUSC Paragraph 6.9.3.1. The User should note its obligations under CUSC Paragraph 6.10.3 in respect of the costs of any Modifications required by the First User(s).

2.16.4	In the event that the Third Party Works have not been completed by the date specified in the Construction Programme or, in The Company’s reasonable opinion are unlikely to be completed by such date, The Company shall be entitled to revise the Construction Programme as necessary to reflect such delay and also, where The Company considers it necessary to do so, shall be entitled to revise the Construction Works (and as a consequence Appendices A and B to the Bilateral Connection Agreement). For the avoidance of doubt such revisions shall be at The Company's absolute discretion and the consent of the User is not required. Further, in the event that the Third Party Works have not been completed by [   ] The Company shall have the right to terminate this Construction Agreement upon giving notice in writing to the User and in this event the provisions of Clause 11 of this Construction Agreement shall apply.

## 3	DELAYS

### 3.1 	If either party shall have reason to believe that it is  being delayed or will be delayed in carrying out that party’s Works for any reason (whether it is one entitling it to the fixing of a new date under Clause 3.2 of this Construction Agreement or not) it shall forthwith notify  the other party in writing of the circumstances giving   rise to the delay and of the extent of the actual and/or  anticipated delay.

### 3.2	If prior to the Completion Date a party (in this Clause 3.2 “the Affected Party”) shall be delayed in carrying out any of the Affected Party’s Works (including their commissioning) by reason of any act, default or omission on the part of the other Party (in this Clause the “Defaulting Party”) or the Defaulting Party’s employees, agents, contractors or sub-contractors or by reason of an event of Force Majeure, the Affected Party shall be entitled to have such later date or dates fixed as  the Commissioning Programme Commencement Date and/or (as the case may be) the Completion Date as may be fair and reasonable in the circumstances provided that it shall have notified the Defaulting Party in writing of such act, default or omission or event of Force Majeure within 28 days of it becoming aware of the occurrence giving rise to the delay together with an estimate of the proposed delay which it will cause the Affected Party.  In the event of a dispute between the parties over what is or are any fair and reasonable new date or dates to be fixed in the circumstances this shall be promptly referred to and determined by the Independent Engineer.  Once the new date or dates are fixed the Construction Programme and/or Commissioning Programme shall be deemed automatically amended as appropriate.

## 4	COMMISSIONING PROGRAMME AND LIQUIDATED DAMAGES

### 4.1	Each party shall give written notice to the other declaring its readiness to commence the Commissioning Programme when this is the case.

### 4.2	The Commissioning Programme shall commence forthwith once both parties have given written notice to the other under Clause 4.1.

### 4.3	The Works shall be deemed to have been Commissioned on the date that the Independent Engineer certifies in writing to that effect.

### 4.4	In the event that the actual date of commencement of the Commissioning Programme is later than the Commissioning Programme Commencement Date The Company (if and to the extent that it is responsible for delayed commissioning beyond the Commissioning Programme Commencement Date, such responsibility and/or its extent to be determined by the Independent Engineer failing agreement between the parties) shall be liable to pay to the User Liquidated Damages for each day that the actual date of commencement of the Commissioning Programme is later than the Commissioning Programme Commencement Date.  It is declared and agreed that such Liquidated Damages shall cease to be payable in respect of any period after the date of actual commencement of the Commissioning Programme.

### 4.5	In the event that the actual date on which the Construction Works are Commissioned is later than the Completion Date The Company (if and to the extent that it is responsible for delayed completion beyond the Completion Date, such responsibility and/or its extent to be determined by the Independent Engineer failing agreement between the parties) shall be liable to pay to the User Liquidated Damages for each day that the actual date on which the Construction Works are Commissioned is later than the Completion Date.  It is hereby agreed and declared that such Liquidated Damages shall cease to be payable in respect of any period after completion of the Construction Works.

### 4.6	Liquidated Damages payable under Clauses 4.4 and 4.5 of this Construction Agreement shall accumulate on a daily basis but shall be payable calendar monthly.  On or before the 15th day of each month the party entitled to receive the payment of Liquidated Damages shall send to the other party a statement of the Liquidated Damages which have accrued due in the previous calendar month.  The party receiving such statement shall in the absence of manifest error pay the Liquidated Damages shown on the statement within 28 days of the date upon which the statement is received.

### 4.7	Without prejudice to and in addition to the obligation of the User pursuant to Clause 2.4 of this Construction Agreement, the payment or allowance of Liquidated Damages pursuant to this Clause 4 shall be in full satisfaction of The Company's liability for failure to perform its obligations by the Commissioning Programme Commencement Date and/or the Completion Date as appropriate.

### 4.8	In the event that the User shall have failed, in circumstances not entitling it to the fixing of a new date as the Commissioning Programme Commencement Date pursuant to Clause 3.2, to complete the User's Works by [  ] to a stage where the User is ready to commence the Commissioning Programme, The Company shall have the right to terminate this Construction Agreement upon giving notice in writing to the User and the provisions of Clause 11 shall apply.

## 5	APPROVAL TO CONNECT/ENERGISE/BECOME OPERATIONAL

### 5.1	Not later than 4 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties the parties shall prepare and submit the Operation Diagrams required to be prepared and submitted by each of them respectively under CC 7.4.7 and 7.4.10 and likewise the Site Common Drawings required under CC 7.5.2 and 7.5.4 and, if necessary, Gas Zone Diagrams referred to in CC 7.4.9 and 7.4.12.

### 5.2	Not later than 3 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties the parties shall prepare and submit the Operation Diagrams required to be prepared and submitted by each of them respectively under CC 7.4.8 and 7.4.11 and likewise the Site Common Drawings required under CC 7.5.3 and 7.5.5.

### 5.3	Not later than 3 months prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties:-

#### 5.3.1	each party shall submit to the other data within its possession needed to enable the completion of Appendices F3 and F4 to the Bilateral Connection Agreement; and

#### 5.3.2	the User shall submit to The Company evidence satisfactory to The Company that the User's Equipment complies or will on completion of the User's Works comply with Clause 8 of this Construction Agreement and Paragraphs [2.9 and 6.7] of the CUSC.

### 5.4	Not later than 8 weeks prior to the expected Commissioning Programme Commencement Date or by such other time as may be agreed between the parties each party shall submit to the other:

#### 5.4.1	for the Connection Site information to enable preparation of Site Responsibility Schedules complying with the provisions of Appendix 1 to the Connection  Conditions together with a list of managers who have been duly authorised by the User to sign such Site Responsibility Schedules on the User's behalf;

#### 5.4.2	written confirmation as required under CC.5.2(g) that the list of Safety Co-ordinators are authorised and competent [and a list of persons appointed pursuant to Grid Code CC5.2(m)];

#### 5.4.3	a list of the telephone numbers for the facsimile machines referred to in CC6.5.9.

#### 5.4.4.	Confirmation of access to the Electronic Communications Platform referred to in CC6.5.9 upon access being provided by The Company.

### 5.5	Not later than 3 months prior to the expected Commissioning Programme Commencement Date each party shall submit to the other a statement of readiness to complete the Commissioning Programme in respect of the Works and the statement submitted by the User shall in addition contain relevant Connected Planning Data and a report certifying to The Company that, to the best of the information, knowledge and belief of the User, all relevant Connection Conditions applicable to the User have been considered and complied with.  If The Company considers that it is necessary, it will require this latter report to be prepared by the Independent Engineer.  The report shall incorporate if requested by The Company type test reports and test certificates produced by the manufacturer showing that the User's Equipment meets the criteria specified in CC6.

## 6	INDEPENDENT ENGINEER

The parties agree and shall procure that the Independent Engineer shall act as an expert and not as an arbitrator and shall decide those matters referred or reserved to  them under this Construction Agreement by reference to Good Industry Practice using their skill, experience and knowledge and with regard to such other matters as the  Independent Engineer in their sole discretion considers appropriate.  All references to the Independent Engineer shall be made in writing by either party with notice to the other being given contemporaneously as soon as reasonably practicable and in any event within 14 days of the occurrence of the dispute to be referred to the Independent Engineer.  The parties shall promptly supply the Independent Engineer with such documents and information as they may request when considering such question.  The Independent Engineer shall use their best endeavours to give their decision upon the question before them as soon as possible following its referral to them.  The parties shall share equally the fees and expenses of the Independent Engineer.  The parties expressly acknowledge that submission  of disputes for resolution by the Independent Engineer does not preclude subsequent submission of disputes for resolution by arbitration as provided for in the Dispute Resolution Procedure.  Pending any such submission the parties shall treat the Independent Engineer’s decision as final and binding.

7.	BECOMING OPERATIONAL

7.1	The Company shall connect and Energise the User's Equipment at the Connection Site during the course of and in accordance with the Commissioning Programme and thereafter upon compliance by the User with the provisions of Clause 5 and provided (1) the Construction Works excluding the Network Options Assessment  Works shall be Commissioned and (2) [the Network Options Assessment Works and Third Party Works shall be completed The Company shall forthwith notify the User in writing that the Connection Site shall become Operational.

7.2	Demand Capacity Reduction

7.2.1 	If, at any time prior to the Completion Date The Company reasonably believes from data provided by the User to The Company, the reports provided by the User pursuant to Clause 2.8 and Clause 5 of this Construction Agreement, the commissioning process under the Construction Agreement or otherwise that the User’s Equipment will be such that it will not be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity The Company shall advise the User accordingly in writing setting out its reasons for this belief, the source of the information giving rise to the concern and seeking clarification from the User.

7.2.2 The User shall respond to The Company within 15 Business Days of the date of the Preliminary Request providing such information or data as is necessary to satisfy The Company’s concerns set out in the Preliminary Request and making any amendments necessary to the report provided by the User pursuant to Clause 2.8 and / or data provided by the User to The Company to reflect this.

7.2.3 In the event that The Company is satisfied from the information provided in accordance with Clause 7.3.2 by the User that the User’s Equipment will be such that it will be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity The Company shall notify the User accordingly.

7.2.4 In the event that the User does not respond to the Preliminary Request or, notwithstanding the User’s response, The Company remains of the view that the User’s Equipment will be such that it will not reasonably be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity The Company shall inform the User in writing that it intends to amend Clause 7 and the Demand Capacity value in the Bilateral Connection Agreement to reflect the Demand Capacity that it reasonably believes that the User's Equipment will be capable of importing.

7.2.5 The User shall respond to the Notice of Intent within 15 Business Days of the date of the Notice of Intent explaining why it still reasonably believes that its User's Equipment will be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or providing a reasonable explanation as to why this is not the case.

7.2.6 In the event that The Company is satisfied from the information provided in accordance with Clause 7.3.5 by the User that the User’s Equipment will be such that it will be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity The Company shall notify the User accordingly.

7.2.7 Where notwithstanding the User’s response to the Notice of Intent The Company remains of the view that the User’s Equipment will be such that it will not reasonably be capable of importing from the National Electricity Transmission System at the level of the Demand Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or the User does not provide a response that is satisfactory to The Company within the timescale specified in 7.3.5 above The Company will issue the Notice of Reduction to the User and will send a copy of the same to the Authority.

7.2.8 Unless during such period the matter has been referred by the User to the Authority for determination by the Authority under the provisions of condition E13.5 of the ESO Licence, the Notice of Reduction shall take effect on the day 15 Business Days after the date of the Notice of Reduction and the Demand Capacity value in the Bilateral Connection Agreement shall be amended on that date in the manner set out in the Notice of Reduction. Where the matter has been referred the amendments to the Demand Capacity value in the Bilateral Connection Agreement and the date they take effect shall be as set out in the Authority’s determination.

7.2.9 After a Notice of Reduction has taken effect The Company shall be entitled to make such amendments to this Construction Agreement as it requires as a result of the reduction in Demand Capacity effected by the Notice of Reduction and as a consequence to the Bilateral Connection Agreement. The Company shall advise the User as soon as practicable and in any event within 3 months of the date of the Notice of Reduction (or if the matter has been referred by the User to the Authority for determination, the date of determination) of such amendments by way of offer of an agreement to vary the Construction Agreement and Bilateral Connection Agreement. This agreement to vary will also provide for payment by the User of the Reduction Fee where applicable. The parties acknowledge that any dispute regarding this variation shall be referable to and determined by the Authority under the provisions of condition E13.5 of the ESO Licence.

7.2.10 	Where there is a reduction in Demand Capacity under Clause 7.2 or Clause 7.3 prior to the Charging Date, on such reduction in Demand Capacity taking effect the User shall pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice in respect thereof.

7.3	[Compliance with Original Red Line Boundary - add only where it’s a Gated Agreement for a direct connection

If a User is not compliant at a User Progression Milestone with the Original Red Line Boundary (other than as it may be changed under the Gate 2 Criteria) for one or more technologies, The Company shall be entitled to amend the Construction Agreement and as a consequence the Bilateral Connection Agreement to:

7.3.1 reduce the Installed Capacity (of each technology that is non-compliant).

7.3.2 remove that technology if the Installed Capacity of a technology is reduced to 0 MW.

7.3.3 reduce the [relevant capacity] if the sum of the Installed Capacity of all technologies is reduced such that it is less than the [capacity] and such that the [capacity] is no higher than the sum of the Installed Capacity of all technologies.]

Users in the capacity of a Directly Connected Distribution System where works are required in respect of Distributed Demand insert the following (and where the Construction Agreement relates to more than one, for each of the Developers:

[7.4	Embedded Demand Capacity Reduction

7.4.1	If, at any time prior to the Completion Date The Company reasonably believes from the reports provided by the User pursuant to Clause 2.8 and Clause 5 of this Construction Agreement, the commissioning process generally or otherwise that the Developer’s Equipment will be such that it will not be capable of importing at the Embedded Demand Capacity, The Company shall advise the User accordingly in writing setting out its reasons and seeking clarification of the position from the User.

7.4.2	The User shall respond to The Company within 15 Business Days of the date of the Preliminary Request providing such information or data as is necessary to satisfy The Company’s concerns set out in the Preliminary Request and making any amendments necessary to the report provided by the User pursuant to Clause 2.8 and /or data provided by the User to The Company to reflect this.

7.4.3	In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.2 by the User that the Developer’s Equipment will be such that it will be capable of importing at the Embedded Demand Capacity The Company shall notify the User accordingly.

7.4.4	In the event that the User does not respond to the Preliminary Request or, notwithstanding the User’s response, The Company remains of the view that the Developer’s Equipment will be such that it will not reasonably be capable of importing at the Embedded Demand Capacity, The Company shall inform the User and the Developer in writing that it intends to amend the Embedded Demand Capacity in this Construction Agreement to reflect the whole MW figure that it reasonably believes the Developer's Equipment will be capable of importing at.

7.4.5	The User shall respond to the Notice of Intent within 15 Business Days of the date of the Notice of Intent explaining why it still reasonably believes that the Developer's Equipment will be capable of importing at the Embedded Demand Capacity or at more than the MW figure proposed by The Company in the Notice of Intent or providing a reasonable explanation as to why this is not the case.

7.4.6	In the event that The Company is satisfied from the information provided in accordance with Clause 7.4.5 by the User that the Developer’s Equipment will be such that it will be capable of importing at the Embedded Demand Capacity The Company shall notify the User accordingly.

7.4.7	Where notwithstanding the User’s response The Company remains of the view that the Developer’s Equipment will be such that it will not be capable of taking demand at the Embedded Demand Capacity or at or at more than the MW figure proposed by The Company in the Notice of Intent or the User does not provide a response that is satisfactory to The Company within the timescale specified in Clause 7.4.5 above The Company will issue the Notice of Reduction to the User and the Developer and will send a copy of the same to the Authority.

7.4.8	Unless during such period the matter has been referred by the User to the Authority for determination by the Authority under the provisions of condition E13.5 of the ESO Licence, the Notice of Reduction shall take effect on the day 15 Business Days after the date of the Notice of Reduction and the Embedded Demand Capacity in this Construction Agreement shall be amended on that date in the manner set out in the Notice of Reduction.

7.4.9	After a Notice of Reduction has taken effect The Company shall be entitled to make such amendments to this Construction Agreement as it requires as a result of the reduction in the Embedded Demand Capacity effected by the Notice of Reduction and as a consequence to the [Bilateral Connection Agreement or Agreement to Vary]. The Company shall advise the User as soon as practicable and in any event within 3 months of the date of the Notice of Reduction (or if the matter has been referred by the User to the Authority, the date of determination) of such amendments by way of agreement(s) to vary. The agreement to vary will also provide for payment by the User of the Reduction Fee and on such reduction in Embedded Demand Capacity taking effect the User shall pay the Cancellation Charge in respect of the reduction such payment to be made within 14 days of the date of The Company’s invoice in respect thereof. The parties acknowledge that any dispute regarding this variation shall be referable to and determined by the Authority under the provisions of condition E13.5 of the ESO Licence.

7.5	Where there is a reduction in Embedded Demand Capacity under Clause 7.4 prior to the Charging Date, on such reduction in Embedded Demand Capacity taking effect the User shall pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice in respect thereof.]”

8.	Compliance with Site Specific Technical Conditions

The User shall ensure that on the Completion Date the User's Equipment complies with the site specific technical conditions set out in Appendix F 1-5 to the Bilateral Connection Agreement .

9.	PROVISION OF SECURITY

Where required to do so under CUSC Section 15, the User shall provide The Company with security arrangements in accordance with CUSC Section 15 Part Three in respect of the User’s obligations to pay the Cancellation Charge to The Company on termination of this Construction Agreement or a reduction in Demand Capacity or Embedded Demand Capacity prior to the Charging Date.

10.	EVENT OF DEFAULT

Once any of the Events of Default in Paragraph 5.3.1 and/or Paragraph 5.4.6.2 and/or Paragraph 5.4.6.3 of the CUSC has occurred and is continuing The Company may give notice of termination to the User whereupon this Construction Agreement shall forthwith terminate and the provisions of Clause 11 shall apply.

11.	TERMINATION

11.1		On termination of this Construction Agreement The Company shall disconnect all the User’s Equipment at the Connection Site and:

(a) the User shall remove any of the User’s Equipment on the Relevant Transmission Licensee's land within 6 months of the date of termination or such longer period as may be agreed between the Relevant Transmission Licensee and the User; and

### (b) The Company shall procure that the Relevant Transmission Licensee removes, any Transmission Connection Assets on the User’s land within 6 months of the date of termination or such longer period as may be agreed between the Relevant Transmission Licensee and the User.

11.2	The User shall where this Construction Agreement terminates prior to the Charging Date be liable forthwith on the date this Construction Agreement so terminates to pay to The Company the Cancellation Charge such payment to be made within 14 days of the date of The Company’s invoice thereof.

12.	TERM

12.1	Subject to the provisions for earlier termination set out in the CUSC this Construction Agreement shall continue until terminated in accordance with Clause 2.5, 2.6, 4.8, 10 or 16 hereof.

12.2	In addition this Construction Agreement shall terminate upon termination of the associated Bilateral Connection Agreement and in the event that this is prior to the Charging Date the provisions of Clause 11 shall apply.

12.3	The associated [Bilateral Connection Agreements or Agreement to Vary the Bilateral Connection Agreement] will automatically terminate upon termination of this Construction Agreement prior to the Charging Date.

12.4	Any provisions for payment shall survive termination of this Construction Agreement.

13.	CUSC

The provisions of Sections 6.6 (Payment), 6.14 (Transfer and Subcontracting), 6.15 (Confidentiality), 6.18 (Intellectual Property), 6.19 (Force Majeure), 6.20 (Waiver), 6.21 (Notices), 6.22 (Third party Rights), 6.23 (Jurisdiction), 6.24 (Counterparts), 6.25 (Governing Law), 6.26 (Severance of Terms), 6.27 (Language) inclusive of the CUSC shall apply mutatis mutandis to this Construction Agreement as if set out in this Construction Agreement.

14.	DISPUTES

Except as specifically provided for in this Construction Agreement any dispute arising under the terms of this Construction Agreement shall be referred to arbitration in accordance with the Dispute Resolution Procedure.

15.	VARIATIONS

15.1	Subject to Clause 15.2 and 15.3 below, no variation to this Construction Agreement shall be effective unless made in writing and signed by or on behalf of both The Company and the User.

15.2	The Company and the User shall effect any amendment required to be made to this Construction Agreement by the Authority as a result of a change in the CUSC, the ESO Licence or the Transmission Licence, an order or direction made pursuant to the Act or a Licence, or as a result of settling any of the terms hereof. The User hereby authorises and instructs The Company to make any such amendment on its behalf and undertakes not to withdraw, qualify or revoke such authority or instruction at any time.

15.3	The Company has the right to vary Appendices in accordance with Clauses 2.3, 2.11 and 7.4 and 16 and Paragraph 6.9 of the CUSC.

16. 	QUEUE MANAGEMENT PROCESS

16.1	The Queue Management Process shall be incorporated into this Construction Agreement and apply between The Company and the User and Appendix Q to this Construction Agreement  has been prepared in accordance with the principles set out in CUSC Section 16.

16.2	Where, in accordance with the Queue Management Process,:

16.2.1	in the case of any of the Conditional Progression Milestones, the status of the User’s project at the end of the Project Milestone Remedy Period is categorised as “Termination”, The Company will terminate this Construction Agreement by notice in writing (such notice being not less than 10 Business Days); and

16.2.2	in the case of any of the Construction Progression Milestones, the status of the User’s project at the end of the Project Milestone Remedy Period is categorised as “Termination” The Company may terminate this Construction Agreement by notice in writing (such notice being not less than 10 Business Days) and on such termination the provisions of Clause 11 of this Construction Agreement shall apply.

16.3	Where in accordance with the Queue Management Process there is a variation to the date by which a User Progression Milestone has to be met The Company shall revise Appendix Q to this Construction Agreement as required to reflect such change.

16.4	Any dispute or difference between The Company and the User on the Queue Management Process in respect of this Construction Agreement shall be resolved as an Other Dispute under the Dispute Resolution Procedure.

Users in the capacity of a Directly Connected Distribution Sytem with Distributed Demand insert the following:

[17. Distributed Demand

17.1 	In consideration of and recognising the provisions at Clause 17.4 of this

Construction Agreement and notwithstanding that the liability for the Cancellation Charge rests with the User, the User will within 5 Business Days of receipt of the same provide the Developer with a copy of the Cancellation Charge Secured Amount Statement.

17.2 	Where this Construction Agreement is entered into by reference to and

provides for the Construction Works required as a consequence of more

than one Developer Cancellation Charge, Cancellation Charge Statement and Cancellation Charge Secured Amount will be prepared by reference to each Developer and the reference to “Cancellation Charge” “Developer” and “Embedded Demand Capacity” in this Construction Agreement and CUSC Section 15 shall be construed accordingly.

17.3 	In the event that the/a Developer reduces its Embedded Demand Capacity and/or terminates its agreement for connection to the Distribution System the User shall notify The Company in writing within 5 Business Days of that event.

17.4 In the event of a Cancellation Charge Shortfall:

17.4.1 On application by the User in writing (which cannot be made prior to

the Shortfall Application Date and without the conditions at Clause 17.5 having been met), The Company shall pay the Cancellation Charge Shortfall to the User together with interest calculated thereon on a daily basis at Base Rate from the date of the payment of the Cancellation Charge to The Company by the User to the date of the payment of the Cancellation Charge Shortfall by The Company to the User.

17.4.2	The User shall keep The Company advised as to any ongoing process to recover the Cancellation Charge Shortfall and any associated interest charges from the Developer and notify The Company when it has reasonable grounds to believe that it is not practicable to take any further action) to recover the Cancellation Charge Shortfall from the Developer.

17.4.3	If at any time the User subsequently successfully recovers the Cancellation Charge Shortfall in full or part from the Developer, the User shall forthwith notify The Company and pay the amount received to The Company together with interest calculated thereon on a daily basis at Base Rate from the date of the payment of the Cancellation Charge Secured Amount to The Company by the User to the date of the payment of the Cancellation Charge Shortfall by the User to The Company.

17.5	In order for the User to make an application for payment of a Cancellation Charge Shortfall the following conditions must have been met and evidence of this provided to The Company by the User with the application.

- that the User asked the Developer whether or not it wishes the User to elect for the Fixed Cancellation Charge and elected accordingly; and

ii) 	(in respect of its liability for the Cancellation Charge as it relates to this Contruction Agreement) for each Security Period the User only sought security from the Developer for the amount as set out in the Cancellation Charge Secured Amount Statement for that Security Period.]

[18	Distribution Queue Management

The User will keep The Company advised as to the categorisation of the Developer’s Project in the Distribution Queue Management Process and notify The Company as soon as practicable if the categorisation of the Developer’s Project  is changed to “Termination” and if and when, in accordance with that process, the Distribution Connection Agreements are terminated.]

IN WITNESS WHEREOF the hands of the duly authorised representatives of the parties hereto at the date first above written

SIGNED BY	)

[name]	)

for and on behalf of	)

National Energy System Operator          )

Limited                                                    )

SIGNED BY	)

[name]	)

for and on behalf of	)

[User]	)

APPENDIX [B]

ONE OFF WORKS

APPENDIX [G]

TRANSMISSION CONNECTION ASSET WORKS

APPENDIX [H]

TRANSMISSION REINFORCEMENT WORKS

APPENDIX [J]

CONSTRUCTION PROGRAMME

APPENDIX [K]

LIQUIDATED DAMAGES

Company:

Connection site:

Type:

The amount of Liquidated Damages payable by The Company to the User pursuant to this Construction Agreement shall be:

Liquidated Damages under Clause [4] of this Construction Agreement shall be calculated on a daily basis at a rate of £XXXXX per week subject to the limit that the total Liquidated Damages payable by The Company to the User under this Clause shall not exceed £XXXXX.

APPENDIX [L]

INDEPENDENT ENGINEER

Company:

Connection site:

Type:

The Independent Engineer will be a Member of the Association of Consulting Engineers (ACE)  and shall be agreed between the parties within 120 days of execution of this Construction Agreement or such other period as may be agreed between the parties. Failing agreement it shall be referred to the President of the Institution of Electrical Engineers who shall nominate the Independent Engineer.

APPENDIX [MM]

ATTRIBUTABLE WORKS AND KEY CONSENTS

Part 1	Attributable Works

Part 2	Key Consents

APPENDIX [N]

THIRD PARTY WORKS

APPENDIX [O][P]

[GATE 1 VERSIONS

USER’S DATA

Project

Location

Connection Site [(provided for indicative purposes only and subject to Clause 1.2)] [Reserved (subject to Clause 1.2]

Demand [requested] [Reserved subject to Clause 1.2]

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date [(provided for indicative purposes only and subject to Clause 1.2)] [Reserved subject to Clause 1.2] when connection to\use of the National Electricity Transmission System will be energised.

DEVELOPER’S DATA

Project

Location

Connection Site (GSP) [(provided for indicative purposes only and subject to Clause 1.2)]

Site of Connection [(provided for indicative purposes only and subject to Clause 1.2)]

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date [(provided for indicative purposes only and subject to Clause 1.2)] use of the Distribution System will be energised.

Installed Capacity

This template will be adapted to remove references to gates and Installed Capacity where the Construction Agreement relates to Distributed Demand.

APPENDIX [O][P]

[GATE 2 VERSIONS

USER’S DATA

Project

Location

Connection Site

Demand (as set out in the Bilateral Connection Agreement)

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date when connection to\use of the National Electricity Transmission System will be energised.

Installed Capacity

DEVELOPER’S DATA

Project

Location

Connection Site (GSP)

Site of Connection

Embedded Demand Capacity

Agreement Reference

[Insert details equivalent to data listed in part 1 of the planning code]

Date when connection to\use of the Distribution System will be energised.

Installed Capacity

This template will be adapted to remove references to gates and Installed Capacity where the Construction Agreement relates to Distributed Demand.

APPENDIX [Q]

QUEUE MANAGEMENT PROCESS – USER PROGRESSION MILESTONES

The table below specifies the dates (derived in accordance with CUSC Section16) for the User Progression Milestones in respect of the User’s project and the application of the Queue Management Process.

Conditional Progression Milestones

| Milestone | Date due |
| --- | --- |
| M1 – Initiate Planning Consent |  |
| M2 – Secure Consent |  |
| M3 – Land Rights |  |

Construction Progression Milestones

| Milestone | Date due |
| --- | --- |
| M5 – Contestable Design Works Submission |  |
| M6 – Agree Construction Plan |  |
| M7 – Project Commitment |  |
| M8 – Initiate Construction |  |

END OF SCHEDULE 2 EXHIBIT 3

Only include where Construction Agreement is for a Power Station with a BEGA or for a DNO and associated with Distributed Generation

add where Construction Agreement is with owner/operator of a Distribution System and the Construction Agreement is required because of a developers connection to the Distribution System

Only include where Construction Agreement is for a Distribution Network Operator and associated with a connection to the Distribution System