## Slide 1: GSR035: System Access Reform - Changes to Enable Beneficial Outages Without Compromising System Security
Workgroup Meeting 4 , 29 April 2026
Online Meeting via Teams

## Slide 2: WELCOME

## Slide 3: Agenda
Topics to be discussed​ | Lead​
Objectives and Timeline​ • Walk-through of the timeline for the modification​ | Chair​
Action Log | All​
Review Workgroup Consultation | All
Review Draft Legal Text | All​
Any Other Business​ | Chair​
Next Steps​ | Chair​

## Slide 4: Objectives and Timeline
Ren Walker – NESO Code Administrator

## Slide 5: GSR035 Proposed Timeline
Milestone​ | Date​ | Milestone​ | Date​
Modification presented to Panel​ | 05 December 2025 | Code Administrator Consultation (15 Business Days) | 05 August 2026 to 27 August 2026
Workgroup Nominations (20 Business Days holiday period)​ ​ | 22 January 2026 – 12 February 2026 | Draft Final Modification Report (DFMR) issued to Panel (5 Business Days)​ | 15 September 2026
Workgroup 1 – review proposal and legal text Workgroup 2 and 3 – refine solution, build Workgroup Consultation document and legal text Workgroup 4 and 5 – approve Workgroup Consultation document | 03 March 2026 11 March 2026 30 March 2026 22 April 2026 (cancelled) 29 April 2026 07 May or 11 May | Panel undertake DFMR recommendation vote ​ | 29 September 2026
Workgroup Consultation (15 Business Days)​ | 08 May – 01 June 2026 12 May – 03 June 2026 15 May – 08 June 2026 | Final Modification Report issued to Panel to check votes recorded correctly | 29 September 2026 to 05 October 2026
Workgroup 5 – review consultation feedback ad build Workgroup Report Workgroup 6 – Review Workgroup Report and vote | 29 May 2026 26 June 2026 17 June 2026 23 June 2026 29 June 2026 01 July 2026 | Final Modification Report issued to Ofgem​ | 06 October 2026
Workgroup report issued to Panel (5 Business Days)​ | 15 July 2026 | Ofgem decision ​ | TBC
Panel sign off that Workgroup Report has met its Terms of Reference​ | 29 July 2026 | Implementation Date ​ | 10 Business Days after Authority decision

## Slide 6: Action Log
Ren Walker – NESO Code Administrator

## Slide 7
Action Number | Workgroup Raised |  | Owner | Action | Due by | Status
03 | WG1 |  | DN/SP/NESO/TO Representatives | Clarify and document how “unacceptable overloading” is interpreted and applied in practice by NESO and the TO’s in England & Wales and Scotland. | WG3 | Email circulated to SQSS Panel. Open
11 | WG2 |  | DN | Need for clearer problem definition: Clarify this before amending legal text. | WG3 | Closed
13 | WG3 |  | DN | Clarify governance location for the risk‑assessment process Determine where the risk‑assessment framework will sit (e.g. SQSS appendix, Grid Code, STC, or other mechanism), ensuring it properly includes DNOs and affected users rather than relying solely on NAP arrangements. | WG4 | Open
14 | WG3 |  | LW | Seek an offline view from the SQSS Panel on “what vs how “An email query to the SQSS Panel to confirm whether defining the content (“what”) of the risk assessment is appropriate within SQSS or should sit elsewhere. Chair to draft the query and circulate for workgroup sense check before sending. | Open | Email circulated to SQSS Panel. Propose to close.

## Slide 8
Action Number | Workgroup Raised |  | Owner | Action | Due by | Status
15 | WG3 |  | DN | Define the scope and minimum content of the risk assessment. Develop clarity on what the risk assessment must cover. | Open | WG4
16 | WG3 |  | DN/RW | Clarify stakeholder roles, consent, and dispute resolution Define: which parties must be involved (TOs, DNOs, generators, users), whether any party has veto rights, how disagreements are resolved if consensus is not reached. | Open | WG4
17 | WG3 |  | DN | Consider an additional Scotland specific case study (clause 5.3) NESO to explore whether a Scottish example linked to loss of supply >1500 MW (5.3) can be added to demonstrate where the new mechanism could apply in Scotland. | Open | WG4
18 | WG3 |  | DN | Clarify treatment of financial impacts and compensation Ensure the approach considers: constraint costs, customer compensation exposure (including DNO impacts), interaction with STC and System Access Reform arrangements. | Open | WG4
19 | WG3 |  | RW/ALL | Circulate draft consultation and legal text for offline comment Draft consultation and revised legal text to be shared outside meetings (email where collaboration space access is an issue), with comments reviewed ahead of the next workgroup. | Open | Propose to close.

## Slide 9
Action Number | Workgroup Raised |  | Owner | Action | Due by | Status
20 | WG3 |  | RW/DN | Review and, if needed, adjust the timetable. Consider adding an extra workgroup meeting and slightly delaying consultation to resolve outstanding governance and risk assessment‑ issues, without affecting the July SQSS Panel deadline. | Open | Timeline updated. Propose to close.
21 | WG3 |  | DN | Review the appropriate governance/code location (e.g., Grid Code, STCP, NAP) for the risk assessment process to ensure all impacted users (including DNOS and generators) are properly included. | Open | WG4

## Slide 10: Feedback from SQSS Panel
the ‘how’ shouldn’t be in the SQSS, provided that SQSS includes sufficient detail of the key aspects of the ‘what’ ie the proposed risk assessment. This allow for stakeholder input and, by virtue of being in the SQSS would be subject to Ofgem Approval. In line with other aspects of the SQSS I’d suggest a very high level summary of the ‘what’ in the main body of the SQSS (eg ‘a risk assessment considering the following factors …..) with supporting detail on each of those factors in an Annex. This would leave the ‘detailed methodology’ to be documented elsewhere.
The term is not referred to in the ToR, but given there has been discussion in the workgroup, which has been documented in the draft WG report, my view is that GSR035 needs to address the ambiguity associated with this term as its necessary to differentiate between the flexibility associated with managing unacceptable overloaded eg via a cascade tripping scheme, and the flexibility associated with the proposed risk base assessment

## Slide 11: Feedback from SQSS Panel
Our vote for below will be Option 1 which proportionally reflect the requirement of the network performance in SQSS whilst keeping processes defined together in relevant industry codes such as STC or STCPs.
In terms of a definition of unacceptable overloading, I am not fully convinced the need for it and agree this will require further understanding of impact from the workgroup if any proposals.

## Slide 12: Terms of Reference
Workgroup Term of Reference
Consider the governance arrangements for the risk based methodology as this need to be documented, open and transparent. The governance needs to be such that any affected stakeholder is able to influence the development and application of the methodology. The workgroup should explicitly consider whether the risk based methodology should form part of the SQSS.
b) Clearly state the key assumptions and principles associated with the risk based methodology.
c) Consider the rationale and benefits associated with the balance between short term increase in risk to stakeholders and the longer term benefits associated with the connection of projects associated with the transition to a low carbon economy.
d) Consider whether a risk based methodology should be associated with outages other than those to facilitate the implementation of the Clean Power 2030 Action Plan e.g. normal maintenance and asset replacement outages.
e) Consider whether the risk based methodology should be applied across all four seasons or just during winter, as implied by the modification proposal.
f) Consider the most appropriate place for the methodology to be documented, so that it is open and transparent.
g) Consider the requirement for a Grid Code modification such that there is an obligation for all relevant parties to provide the required data to undertake the risk assessment, engage in the risk assessment process, share the results from application of the methodology and agree to its findings. Consideration should be given to the process where the impacted party does not agree with the outcome of the risk assessment. The party responsible for applying the methodology should also be codified.
h) Consider the number of occasions per annum when the new arrangements are expected to be applied and the relaxations implemented, to form a view of the potential benefits.
i) Consider whether the risk based approach should be applied to high impact / low probability events only, or whether a risk based approach could / should be applied to low impact / high probability events.
j) Quantify or provide examples of the change in risk to customer supplies arising from the implementation of a risk based approach compared to a deterministic approach.
k) Consider the current risk assessment process applied in Scotland and whether it, in its current or modified form could be applied in England and Wales.

## Slide 13: Review Draft Workgroup Consultation
Ren Walker – NESO Code Administrator

## Slide 14: Any Other Business
Ren Walker – NESO Code Administrator

## Slide 15: Next Steps
Ren Walker – NESO Code Administrator