## All Actions
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | LW | Terms of Reference: Submit the proposed amentment to change the word "explain" to "consider" in the Terms of Reference (d) to the SQSS Panel for approval | Action 01: (Closed) Terms of Reference: Submit the proposed amendment to change the word "explain" to "consider" in the Terms of Reference (d) to the SQSS Panel for approval. Timeline confirmed: next workgroup 13 April, potential additional meeting before consultation if needed. | To be presented at SQSS March Panel | Closed | WG3
2 | WG1 | DN/SP | Case Studies Presentation: Prepare and present additional case studies at the next WG meeting, focussing on examples where outages move from insecure to secure and include Scottish practices for comparision. | 10.03.26 The Workgroup members discussed further case studies and requested, further clarification on numerical values, such as: Voltage levels, Overload magnitudes, Generator effectiveness, model assumptions and DNO modelling accuracy 30.03.26 Case studies presented at WG. discussed in detail. Action met. | COP 01.04.26 | Closed | WG3
3 | WG1 | DN/SP/NESO/TO Representatives | Clarification of Unacceptable Overloading Interpretation: Clarify and document how "unacceptable overloading" is interpreted and applied in practice by NESO and the three TO's in both Scotland, England & Wales, and present findings at the next meeting. | 29.04.26 Action to be revisited Clarification of unacceptatble overloading required. | To be revisited | Open
4 | WG1 | All Workgroup Members | Legal Text Review for Clause 5.11.3: Review and confirm the accuracy of the draft legal text for proposed clause 5.11.3 ensuring correct referecnes and alignment with intended scope and share with Workgroup. | 10.03.26 to be covered in next Workgroup 3 30.03.26 Legal text review for clause 5.11.3 action met. | Overload magnitudes | Closed | WG3
5 | WG1 | DN/AR | Consideration of Alternative approaches to SQSS: Investigate and report on whether alternative approaches such as temporary derogations or tools similar to connect and manage have been considered instead of deleting elements from the SQSS. | Context provided by Workgroup members, that Ofgem is steering towards codifying flexibility to reduce reliance on bespoke derogations, which are slow and administratively heavy. Workgroup agreed to close action 05. | Generator effectiveness | Closed | WG3
6 | WG1 | DN | Impact Assessment for GSR036 on generators: Ensure the impact assesment for GSR036 includes consideration of impacts on generators, particularly Nuclear plants and communicate to EDF. | GSR036 has gone to Code Administration Consultant and part of the code admin consultation will give industry the opportunity to feed in comments when we do publish that consultation. So just because there's not a work group, there is still opportunity to sort of raise your concerns via a consultation. | Model assumptions and DNO modelling accuracy | Closed | WG3
7 | WG2 | DN/SP | Case studies to be updated with clause‑by‑clause SQSS walkthroughs. | Case studies updated and presented to WG | WG3 | Closed | WG3
8 | WG2 | DN/SP | Engagement with “Affected Users” Request to explicitly define and document this in reports and slides. | Action met | WG3 | Closed | WG3
9 | WG2 | DN | Impact of Proposed Changes on Safety and Asset Protection: Clarification requested on who is responsible for safety and how this interacts with SQSS. |  | WG3 | Closed | WG3
10 | WG2 | DN | Relationship Between Chapter 5.4 Changes and Chapters 2 & 4 • Concern that any changes made to 5.4 will impact chapter 2 and 4 of the SQSS. Request for this linkage to be fully assessed. |  | WG3 | Closed | WG3
11 | WG2 | DN | Need for Clearer Problem Definition: Strong emphasis on clarifying this before modifying legal text. | 29.04.26 Action has been addressed via revised legal text for 5.3/5.4 point that is now outdated. | WG3 | Closed | WG4
12 | WG2 | DN | Purpose and Scope of 5.11 (Risk Based Approach) Request to revisit the rationale before moving to legal text drafting. | Change in approach acknowledged and accepted following revised legal text. | WG3 | Closed
13 | WG3 | DN/NESO Representative | Clarify governance location for the risk‑assessment process Determine where the risk‑assessment framework will sit (e.g. SQSS appendix, Grid Code, STC, or other mechanism), ensuring it properly includes DNOs and affected users rather than relying solely on NAP arrangements. | 29.04.26 DN and CN addressed this action in Workgroup with discussions around “how and “what” and where these sit. Action to be revisited | WG4 | Open
14 | WG3 | All Workgroup Members / RW | Seek an offline view from the SQSS Panel on “what vs how” An email query to the SQSS Panel to confirm whether defining the content (“what”) of the risk assessment is appropriate within SQSS, or should sit elsewhere.Lurrentia to draft the query and circulate for workgroup sense‑check before sending. | 29.04.26 Query and clarify “What vs How” and whether “unacceptable overload” is within or outside of scope. | WG4 | Open
15 | WG3 | DN | Define the scope and minimum content of the risk assessment Develop clarity on what the risk assessment must cover, including: safety and asset risk, security of supply, voltage impacts, customer and financial consequences, criteria for approval / rejection. | 29.04.26 Presented by DN at Workgroup regarding “how” sits outside the SQSS and the high-level description to be included in an appendix. No explicit close received for this action. | WG4 | Open
16 | WG3 | DN | Clarify stakeholder roles, consent, and dispute resolution Define: which parties must be involved (TOs, DNOs, generators, users), whether any party has veto rights, how disagreements are resolved if consensus is not reached. |  | WG4 | Open
17 | WG3 | DN | Consider an additional Scotland‑specific case study (clause 5.3) NISO to explore whether a Scottish example linked to loss of supply >1500 MW (5.3) can be added to demonstrate where the new mechanism could apply in Scotland. |  | WG4 | Open
18 | WG3 | DN | Clarify treatment of financial impacts and compensation Ensure the approach considers: constraint costs, customer compensation exposure (including DNO impacts), interaction with STC and System Access Reform arrangements. |  | WG4 | Open
19 | WG | RW/ALL | Circulate draft consultation and legal text for offline comment Draft consultation and revised legal text to be shared outside meetings (email where collaboration space access is an issue), with comments reviewed ahead of the next workgroup. | Draft consultation and legal text has been circulated | WG4 | Closed | WG4
20 | WG3 | RW/DN | Review and, if needed, adjust the timetable Consider adding an extra workgroup meeting and slightly delaying consultation to resolve outstanding governance and risk‑assessment issues, without affecting the July SQSS Panel deadline. | Timeline updated | WG4 | Closed | WG4
21 | WG3 | DN/AH | Review the appropriate governance/code location (e.g., Grid Code, STCP, NAP) for the risk assessment process to ensure all impacted users (including DNOS and generators) are properly included, and report back at the next meeting | 29.04.26 action to be revisited | WG4 | Open
22 | WG4 | RW | Arrange Meeting with Proposer and follow‑up on consequential modification timelines / packaging: understand when consequential mods (e.g., OC2 / SDCP) need to be raised and how timelines/panels align, to support submitting a coordinated package to Ofgem. |  | WG5 | Open
23 | WG4 | All | To review Workgroup Consultation Report and give feedback/comments |  | COP 01.04.26 | Open
24 | WG4 | DN | To review and update legal text comments and liaise with Legal department |  | WG5 | Open