## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | FK | Update legal text based on Workgroup feedback |  | WG2 | Closed | WG2
2 | WG1 | SS | Consider whether the Legal Text in OC6.9.5. is applicable within the bounds of the existing licence rather than through primary legislation |  | WG2 | Closed | WG3
3 | WG1 | LT | Discuss possible changes to the timeline with Proposer and Ofgem |  | WG2 | Closed | WG2
4 | WG2 | RS | Provide update on System Defence Plan | To be amended following conclusion of GC0176 | WG3 | Closed | WG3
5 | WG2 | AM/AC | Liaise to ensure that there were no misunderstandings about the ability to meet the 2-5 minute requirement with fast load blocks in OC6.5.3 |  | WG3 | Closed | WG3
6 | WG2 | FK | Confirm Grid Code defined terms in OC6.5.3 and OC6.9.7 |  | WG3 | Closed | WG3
7 | WG3 | All | Network Operators to provide a list of the licence requirements that are likely to need a derogation if DCRP is used, and the reasons why. |  | WG4 | Closed | WG4
8 | WG3 | JZH | Provide ETG with updates in OC6.5.5 and investigate whether OC6.2.2 is still required. |  | WG6 | Closed | WG6
9 | WG3 | RS | Provide OC7 legal text on correct Baseline document without Fax option in tables. |  | WG4 | Closed | WG4
10 | WG3 | All | Workgroup members to think of Specific Workgroup Consultation questions prior to next Workgroup meeting |  | WG4 | Closed | WG5
11 | WG3 | LT | Chair to contact Ofgem Representative regarding the outcome of discussions on Action 7. |  | WG5 | Closed | WG5
12 | WG4 | RS | NESO SME to update the Legal Text following WG4 discussions, including a timeline diagram in OC6. |  | WG5 | Closed | WG5
13 | WG4 | LT | Updated Workgroup Consultation document to be shared for review. |  | WG5 | Closed | WG5
14 | WG4 | All | Network Operators to confirm they’re content with timings in OC6.9.4 and NESO SME to take this point to next ETG. |  | WG5 | Closed | WG5
15 | WG4 | LT | Chair to provide Workgroup with update on revisions to the timeline. |  | WG5 | Closed | WG5
16 | WG7 | LT | Contact SS to identify whether DNOs will need to apply for derogations separately or if through the ENA is sufficient | To be resolved outside of scope of modification. | WG8 | Closed | WG8
17 | WG7 | RS | Reach out to AC on OC7 queries | Action resolved and no longer required | WG8 | Closed | WG8
18 | WG7 | JZH | Look into IDNO issue outside the scope of GC0176 Workgroup and determine whether activation schedules need to be issued for Transmission Connected IDNOs. Also include OC6 in Bilateral Agreements with Transmission Connected IDNOs. | Raised during Workgroups but outside scope of modification. This action will be ongoing once the Workgroup stage of the modification has concluded so has been closed. | Ongoing | Closed | WG8