## CUSC
Connection Use Of System Code (CUSC): is the contractual framework for connection to, and use of, the National Electricity Transmission System (NETS). | [24 empty] | 2022-10-26
[5 empty] | General Modification Information | [6 empty] | Workgroup | [5 empty] | Consultation |  |  |  | Ofgem |  |  | 2025-11-01
Mod Number | Title | Purpose: What is the Mod trying to deliver | Current Status | Latest Status | Priority No: | Proposer Organisation | Date raised | Impacted Parties | Governance Route | Cross Code Impact | Impact on EBR (Elec Balancing Regulation) | Number of Workgroup Members | Number of Workgroup Consultation Responses | Number of timeline amends | Number of alternative requests | Number of alternative solutions | Workgroup Report to Panel | Code Administrator Consultation | Number of Code Administrator Consultation Responses | Legal text issues from Code Administrator Consultation | Panel Vote | Sent to Ofgem / Appeals Window | Ofgem Decision | Implementation Date | 2025-03-31
CMP271 | Improving the cost reflectivity of demand transmission charges | Proposed that the transmission charging methodology should include a Peak Security demand tariff levied at Triad, a Year round demand tariff & C18revenue recovery levied on a year round supplier. | Withdrawn | The Panel met on 30 September 2016 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 1 November 2016. This was put on hold by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Code Admin have contacted Proposers to ascertain if Modification needs to be progressed or withdrawn. Code Admin noted to June 2020 Panel that Proposer confirmed on 22 June 2020 that this can be withdrawn but note that original Proposer has retired so reached out to RWE to confirm for certain that they wish to withdraw. RWE are considering options. A Code Administrator review of modifications in August 2023 highlighted that this modification has not yet been formally withdrawn, the CUSC Panel Secretary has reached out to RWE to confirm next steps. The Proposer formally provided notice of their withdrawal as Proposer. Comms went out to industry on 29 August 2023, giving a deadline of 5pm 05 September 2023 to become the official proposer of CMP271. [29/09/2023] As no support was received by 5pm 05 September 2023, the Proposers request to withdraw CMP271 was presented at the CUSC Modifications Panel on 29 September 2023 and under CUSC 8.16.10(c) the Panel agree to the withdrawal of CMP271. | n/a - hidden from tracker | RWE | 2016-09-29 | High impact on Generators, Suppliers, Embedded Generators | Standard Governance (Workgroup) | None | No | [5 empty] | NA | NA |  |  | NA | NA | NA | NA | 2024-01-29
CMP276 | Socialising TO costs associated with ''green policies'' | Proposes a reduction in the demand residual element of the TNUoS £/kW (''Triad'') charge by creating 2 new charge lines for all demand offtakes. (Please also refer to CMP264 & 265). | Withdrawn | The Panel met on 10 February 2017 and agreed that it goes to a Workgroup. They also considered the associated request for urgency. The majority view of the CUSC Panel was that CMP276 did not met Ofgem’s Urgency criteria and Ofgem, on 28 April 2017, did not grant Urgency. Workgroup meetings commenced on 17 March 2017. This was put on hold by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Code Admin have contacted Proposers to ascertain if Modification needs to be progressed or withdrawn. Proposer confirmed on 22 June 2020 that this can be withdrawn following the CMP264/CMP265 decision and Ofgem's Targeted Charging Review. Code Admin would commence formal withdrawal process. A Code Administrator review of modifications has highlighted that this modification had not yet been formally withdrawn, a verbal update was given at the August 2023 CUSC Panel ahead of comms being issued to industry on 29 August 2023, giving a deadline of 5pm 05 September 2023 to become the official proposer of CMP276. [29/09/2023] As no support was received by 5pm 05 September 2023, the Proposers request to withdraw CMP276 was presented at the CUSC Modifications Panel on 29 September 2023 and under CUSC 8.16.10(c) the Panel agree to the withdrawal of CMP276. | n/a - hidden from tracker | Alkane Energy Ltd | 2017-06-02 | High impact on Embedded Generators, Half Hourly metered consumers, ESO | Standard Governance (Workgroup) | None | No | [5 empty] | NA | NA |  |  | NA | NA | NA | NA | 2024-01-29
CMP286 | Improving TNUoS Predictability Through Increased Notice of the Target Revenue used in the TNUoS Tariff Setting Process | The purpose of this modification proposal is to improve the predictability of TNUoS demand charges by bringing forward the date at which the target revenue used in TNUoS tariff setting is fixed to allow customer prices to more accurately reflect final TNUoS rates. | Rejected | The Panel met on 20 October 2017 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 18 January 2018. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. The Proposer sought re-prioritisation of this Modification at October 2021 Panel and Panel agreed to move the priority from Low to Medium as clear drive from the Proposer and the Proposer argues that the lower risk premiums (that Suppliers will include) will benefit consumers. Workgroups re-commenced on 7 December 2021.2nd Workgroup Consultation was issued on 6 April 2022 and closed 5pm on 9 May 2022 with 7 non-confidential responses received. Workgroup Report was presented to September 2022 Panel and Panel agreed that the Terms of Reference have been met and agreed for CMP286/CMP287 to proceed to Code Administrator Consultation. The Code Administrator Consultation ran from 4 October 2022 to 5pm on 1 November 2022 and there were 4 responses. Panel recommended by majority (7 out of 9 Panel Members) that both the CMP286/CMP287 Original and WACM1 better facilitated the CUSC Objectives than the current CUSC arrangements. Final Modification Report was sent to Ofgem on 7 December 2022. CMP286/CMP287 was sent back by the Authourity on 30 June 2023 due to the FMR with a single set of Panel voting and a single proposed legal text; and a lack of analysis of the impact of CMP287 alone. At the July CUSC Panel it was agreed that the Workgroup should be reconvened and address the Send Back deficiencies via the approved Terms of Reference. The Workgroup reconvened on 20 September 2023, an updated timeline was approved by the September 2023 CUSC Panel. The Workgroup response to the Send back was to be issued to the October 2023 CUSC Panel, however due to outstanding queries around the legal text an updated timeline was presented and approved by the October 2023 CUSC Panel. The Workgroup response to the Send back was be issued to the November 2023 CUSC Panel, for approval to progress to the Second Code Administrator Consultation. The November 2023 CUSC Panel approved to progress to the second Code Administrator Consultation which ran from 29 November 2023 until 05 January 2024 and recieved 6 non- confidential responses. At the January 2024 CUSC Panel, the Panel has recommended by majority that the Proposer’s solution and WACM1 better facilitate the CUSC Applicable Objectives. The Final Modification Report was be sent to Ofgem on 08 February 2024. CMP286 had an expected decision date of 30 April 2024 as per Ofgem's published update on 23 February 2024. CMP286 had an expected decision date of 26 April 2024 (previously 30 April 2024) as per Ofgem's published update on 02 April 2024. CMP286 has an expected decision date of 03 May 2024 (previously 26 April 2024) as per Ofgem's update at the April 2024 CUSC Panel on 26 April 2024. [07/05/2024] Decision received on Friday 3 May 2024, from the Authority to advise they have rejected this modifiction. Details can be found on the website | n/a - hidden from tracker | Npower | 2017-10-10 | High impact on Suppliers, the ESO, Transmission Owners and Consumers | Standard Governance (Workgroup) | CUSC (CMP244) STC | No | [5 empty] | 2022-09-30 | First CAC: 04/10/2022 to 01/11/2022 Second CAC: 29/11/2023 to 05/01/2024 |  |  | First Vote: 25/11/2022 Second Vote : 26/01/2024 | First submission: 07/12/2022 Second submission: 08/02/2024 | Send Back: 30/06/2023 | TBC | 2024-09-18
CMP287 | Improving TNUoS Predictability Through Increased Notice of Inputs Used in the TNUoS Tariff Setting Process. | Seeks increased notice of the Target Revenue (CMP286) and inputs (CMP287) used in the TNUoS Tariff Setting Process | Withdrawn | The Panel met on 20 October 2017 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 18 January 2018. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. The Proposer sought re-prioritisation of this Modification at October 2021 Panel and Panel agreed to move the priority from Low to Medium as clear drive from the Proposer and the Proposer argues that the lower risk premiums (that Suppliers will include) will benefit consumers. Workgroups re-commenced on 7 December 2021.2nd Workgroup Consultation was issued on 6 April 2022 and closed 5pm on 9 May 2022 with 7 non-confidential responses received. Workgroup Report was presented to September 2022 Panel and Panel agreed that the Terms of Reference have been met and agreed for CMP286/CMP287 to proceed to Code Administrator Consultation. The Code Administrator Consultation ran from 4 October 2022 to 5pm on 1 November 2022 and there were 4 responses. Panel recommended by majority (7 out of 9 Panel Members) that both the CMP286/CMP287 Original and WACM1 better facilitated the CUSC Objectives than the current CUSC arrangements. Final Modification Report was sent to Ofgem on 7 December 2022. CMP286/CMP287 was sent back by the Authourity on 30 June 2023 due to the FMR with a single set of Panel voting and a single proposed legal text; and a lack of analysis of the impact of CMP287 alone. At the July 2023 CUSC Panel it was agreed that the Workgroup should be reconvened and address the Send Back deficiencies via the approved Terms of Reference. The Workgroup reconvened on 20 September 2023, an updated timeline was approved by the September 2023 CUSC Panel. An updated timeline was approved by the November 2023 CUSC Panel. The next Workgroup has been delayed due to waiting for analysis, a revised timeline was scheduled to be submitted to the March 2024 CUSC Panel. [25/03/2024] The Proposer withdrew their support for modification on 23 February 2024 and industry were invited to adopt the modification by 01 March 2024. As no Parties came forward the modfication the Proposer's request to withdraw CMP287 was presented to the March 2024 CUSC Panel and under CUSC 8.16.10(c) the Panel agree to the withdrawal of CMP287. | n/a - hidden from tracker | Npower | 2017-10-10 | High impact on Suppliers, the ESO, Transmission Owners and Consumers | Standard Governance (Workgroup) | CUSC (CMP244) STC | No | [5 empty] | 2022-09-30 | First CAC: 04/10/2022 to 01/11/2022 Second CAC: 27/02/2024 to 18/03/2024 |  |  | First Vote: 25/11/2022 Second Vote : 26/04/2024 | First submission: 07/12/2022 Second submission: 07/05/2024 | Send Back: 30/06/2023 | Withdrawn | 2024-08-15
CMP288 | Explicit charging arrangements for customer delays and backfeeds | To introduce explicit charging arrangements to recover additional costs incurred by Transmission Owners and TNUoS liable parties as a result of transmission works undertaken early due to a User initiated delay to the Completion Date of the works, or to facilitate a backfeed. | Workgroup Stage | The Panel met on 23 February 2018 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 16 May 2018.June 2022 Panel agreed that the Workgroup had met its Terms of Reference. Code Administrator Consultation was issued on 27 June 2022 and closed 5pm on 18 July 2022 with 6 non-confidential responses received. Draft Final Modification Report was presented to July 2022 Panel for their recommendation vote and Panel by majority recommended that CMP288 should not be implemented. Send back was 14 September 2023. The December 2023 CUSC Panel approved an updated timeline and Terms of Reference. An updated timeline was approved by the February 2024 CUSC Panel. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings, the Workgroup Consultation Document will be finalised and circulated for Workgroup approval ahead of being published to industry. October 2024 CUSC Panel prioritised as Low, therefore no work will take place on this modification until further notice.The Panel will be reviewing the status of this modification in the January 2025 Panel. Upon receipt of the Authority Open Letter on 31 Jauary: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification remained low priority. On 30 January 2026 at the CUSC Panel, the Panel discussed CMP288 and agreed there is limited work left to prepare CMP288 for Workgroup Consultation. Clarity of delay payments will be important once the connections reform is complete and that this modification should be considered medium in the next priority review. | Low | NESO | 2018-02-15 | High impact on Transmission Owners, Developers requiring new generation, interconnector or demand connections; Low impact on Parties paying TNUoS. | Standard Governance (Workgroup) | None | No | 8 | 12 | Unknown | 1 | 0 | 2022-06-24 | First CAC: 27/06/2022 to 18/07/2022 Second CAC: 30/07/2024 to 20/08/2024 | 6 | No | First Vote: 29/07/2022 Second Vote: 27/09/2024 | First Submission: 10/08/2022 Second Submission: 09/10/2024 | Send back 14/09/2023 | 10 working days after Ofgem decision | 2025-03-18
CMP291 | The open, transparent, non discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation set out within the Bilateral Agreements | Aims to set out within the CUSC the obligations in the EU Connection Network Codes and System Operation Guideline as they relate to the harmonised rules for connection and system operation in GB. | Withdrawn | The Panel met on 23 February 2018 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 12 July 2018. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At June 2021 Panel, Panel discussed the interaction with GC0117 and Code Admin confirmed with the Grid Code Review Panel ESO representative confirmed that progression of GC0117 is not dependent on CMP291 progressing . Therefore, CMP291 will remain “Low” in the prioritisation stack. At the quarterly prioritisation deep-dive at Panel on 28 April 2023, no case was presented to change the priority. At the quarterly prioritisation deep-dive at the July 2023 Panel, no case was presented to change the priority. The Proposer formally provided notice of their withdrawal as Proposer. Comms went out to industry on 16 August 2023, giving a deadline of 5pm 23 August 2023 to become the official proposer of CMP291 on 16 August 2023. [25/08/2023] As no support was received by 5pm 23 August 2023, the Proposers request to withdraw CMP291 was presented at the CUSC Modifications Panel on 25 August 2023 and under CUSC 8.16.10(c) the Panel agree to the withdrawal of CMP291. | n/a - hidden from tracker | SSE Generation | 2018-02-15 | Transmission Owners, Offshore Transmission Owners, Interconnectors, Distribution Network Operators, Transmission System Users, ESO, Generators, Demand Customers and Providers of services | Standard Governance (Workgroup) | Grid Code (GC0117) DCUSA | No | [5 empty] | NA | NA |  |  | NA | NA | NA | NA | 2024-01-30
CMP292 | Introducing a Section 8 cut-off date for changes to the Charging Methodologies | Ensure that CUSC Charging Methodologies are fixed in advance of the relevant Charging Year to allow ESO to appropriately set and forecast charges with the aim of reducing the risk of charges out-turning differently to the forecasts produced by ESO and created by Users. | Implemented | The Panel met on 23 February 2018 and agreed that it goes to a Workgroup. Workgroup meetings were held between 5 December 2018 and 17 May 2019. The Final Modification Report was submitted to Ofgem on 16 August 2019. The CMP292 decision was expected 20 September 2019 but Ofgem have consistently advised that this de-prioritised. Since 4 May 2021 (last updated 10 February 2022), Ofgem have published a table that provides the expected decision date, or date they intend to publish an impact assessment or consultation, for code modifications/proposals that are with them for decision. [08/04/2024] Ofgem decision approving the Original proposal was received 25 August 2023 and was implemented on 01 April 2024. | n/a - hidden from tracker | ESO | 2018-02-15 | High impact on Chargeable Users and ESO | Standard Governance (Workgroup) | None | No | [5 empty] | 2019-05-01 | 2019-06-01 |  |  | 2019-07-01 | 2019-08-16 | 2023-08-25 | 2024-04-01 | 2024-07-29
CMP298 | Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation | Process for aggregated assessment of Distributed Generators that impact (or may impact) on the National Electricity Transmission System. | Implemented | The Panel met on 27 April 2018 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 2 October 2018. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed and June 2020 Panel determined that Priority of this was Low. October Panel reviewed the request from the Open Networks to re-start Workgroups and noted the increasing risk of divergence in treatment across Network Operators. Therefore, priority was raised to Medium. Workgroups re-started on 23 February 2021 and concluded on 14 January 2022. January 2022 Panel agreed that the Workgroup had met its Terms of Reference. Code Administrator Consultation was issued on 31 January 2022 and closed 5pm on 21 February 2022 with 4 non-confidential responses received. Panel on 25 March 2022 recommended unanimously that all options better facilitated the CUSC Objectives than the current CUSC and there was a strong preference (8 out of 9 votes) for WACM3 (deemed acceptance by the ESO and no re-work fee). Final Modification Report was issued to Ofgem 6 April 2022 (The Final Modification Report for the associated STC change (CM080) was issued to Ofgem on 11 October 2022). CMP298 had an expected decision date of 29 September 2023 (previously 21 August 2023) as per Ofgem's update at the July 2023 CUSC Panel. CMP298 had an expected decision date of 20 October 2023 (previously 29 September 2023) as per Ofgem's update at the September 2023 CUSC Panel. CMP298 had an expected decision date of 16 November 2023 (previously 20 October 2023) as per Ofgem's update published on 13 October 2023. CMP298 had an expected decision date of 30 November 2023 (previously 16 November 2023) as per Ofgem's update published on 14 November 2023. The Authority Representative indicated at the December 2023 CUSC Panel that due to the publication moratorium the approval of WACM3 would be published on 04 January 2024 (previously 12 December 2023 [18/01/2024] The Authority approved WACM3 on 04 January 2024 and directed it to be implemented on 18 January 2024. | n/a - hidden from tracker | ESO | 2018-04-17 | Medium impact on Distribution Network Operators, Transmission Owners, Embedded Generators and ESO | Standard Governance (Workgroup) | STC (CM080) | No | [5 empty] | 2022-01-26 | 31/01/2022 to 21/02/2022 |  |  | 2022-03-25 | 2022-04-06 | 2024-01-04 | 2024-01-18 | 2024-07-29
CMP304 | Improving the Enhanced Reactive Power Service by making it fit for purpose | Seeks to enable reforms +D16+C14 | Workgroup Stage | The Panel met on 31 August 2018 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 9 October 2018.This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Workgroups recommenced on 8 November 2021 and at January 2022 Panel, Panel agreed that the Workgroup Report will be presented to April 2022 Panel as more time required to issue the Workgroup Consultation and resolve actions. Workgroup Consultation opened on 17 February 2022 and closed 5pm on 10 March 2022 with 3 non-confidential responses received. Workgroups delayed thereafter so Proposer could first understand the proposed future steps for a Reactive Power Market before finalising their solution. Prioritisation was discussed at October 2022 Panel and priority was not changed, as there remains a need for reactive services. However, the Panel (and Proposer) agreed that work on CMP304 is paused until such time that the ESO team, who are leading on the Reactive Reform (Market Design), have completed their Feasibility studies, which in turn will help to inform the Proposer's solution. Prioritisation was discussed at July 2023 CUSC Panel and priority was not changed, however the Proposer and ESO Panel Rep will review the output of Phase 1 of the ESO's feasibility studies ahead of reconvening the Workgroup October 2024 CUSC Panel prioritised as Low, therefore no work will take place on this modification until further notice. The Panel will be reviewing the status of this modification in the January 2025 Panel. (07/02/2025) Upon receipt of the Authority Open Letter on 31 January Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. (18/02/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification remained low proirity and therefore . (05.02.2026) The CUSC Panel carried out a deep dive of the CUSC Modifications and agreed that CMP304 should be moved from low to medium priority. Their rationale for this was: CMP304 was paused during the NESO reactive power review. The review is now complete, and NESO raised CMP457: Revision of the Obligatory Reactive Power Service (ORPS) as a result. | Medium | SSE Generation | 2018-08-23 | Medium impact on NESO and providers of reactive power. | Standard Governance (Workgroup) | CUSC (CMP305) | No | 8 | 3 | Unknown | 0 | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2025-05-07
CMP305 | Removal of the Enhanced Reactive Power Service (ERPS) | Remove references to the Enhanced Reactive Power Service (ERPS) from the CUSC. ERPS is an opt-in tendered commercial service for which no tenders have been submitted in seven and a half years, and no contracts have been agreed in nine years. | Send Back | The Panel met on 31 August 2018 and agreed that it goes straight to Code Administrator Consultation. Final Modification Report was sent to Ofgem on 12 December 2018 for decision; however Ofgem sent back CMP305 on 1 February 2019 asking that the revised Final Modification Report should include information on the stated administrative impacts of the current tendering requirements for the Enhanced Reactive Power Service. As CMP304 and CMP305 are two different options related to treatment of the same service, Ofgem feel it would be appropriate that they assess and make their decisions on these related proposals at the same time and therefore asked that CMP305 is resubmitted to Ofgem alongside CMP304. | Medium | NESO | 2018-08-23 | Low impact on industry and providers of balancing services. | Standard Governance (Workgroup) | CUSC (CMP304) | No | n/a | n/a | n/a | n/a | n/a | N/A - Straight to Code Administrator Consultation | 2018-10-05 |  |  | 2018-11-30 | 2018-12-19 | Sent back - Timeline to align to CMP304 | TBC | 2025-05-07
CMP315 | TNUoS: Review of the expansion constant and the elements of the transmission system charged for | The expansion constant is a key input in setting the value of the locational element of transmission network use of system charges. This modification proposal would review how the expansion constant is determined such that it best reflects the costs involved. | Pending Authority Decision | The Panel met on 26 April 2019 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 5 September 2019.This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 (rather than be formally amalgamated) with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. Workgroups recommenced on 10 August 2021. Workgroup Report will be presented to July 2022 Panel. Workgroup Consultation issued 14 April 2022 and closed 5pm on 17 May 2022 with 28 non-confidential responses (and 1 confidential response) received. CMP315/CMP375 Workgroup Report was going to be presented to May 2023 CUSC Panel. However, although 2 of the solutions are fully developed, there is one new solution that became a WACM at the Workgroup meeting on 2 May 2023 and this needs further development - timescales (given the requirement for further data from the Transmission Owners). The CMP315/CMP375 Workgroup Report was intended to be issued to the July 2023 CUSC Panel, however a new timeline was approved at the July 2023 CUSC Panel to allow for additional solution refinement. The CMP315/CMP375 Workgroup completed their Workgroup Vote on 16 August 2023, the Workgroup Report was issued to the October 2023 CUSC Panel. The October 2023 CUSC Panel agreed that the Workgroup had met its Terms of Reference and that it could proceed to Code Administrator Consultation. To ensure that industry have sufficient time to consider the Consultation it will be issued on 10 November 2023 until 5pm on 15 December 2023. The Code Administrator Consultation was issued on 10 November 2023 until 5pm on 15 December 2023 and received 17 Non confidential responses and 0 Confidential responses. At the January 2024 CUSC Panel, the Panel recommended by majority that the CMP315 Original solution better facilitate the CUSC Applicable Objectives to complete their recommendation vote. The Final Modification Report was sent to Ofgem on 07 February 2024. CMP315 had an expected decision date of 30 September 2024 as per Ofgem's published update on 2 May 2024. CMP315 had an expected decision date of 30 September 2024 which has now changed to 29 November 2024 as per EDD update from Ofgem on 02 September 2024. CMP315 expected decision date of 07 February 2025 (previously 29 November 2024) as per Ofgem's update at the December 2024 CUSC Panel. (06/03/2025) CMP315 expected decision date is to be confirmed | n/a | PeakGen | 2019-04-16 | High impact on all Users who pay TNUoS charges, NESO, Transmission Owners and Offshore Transmission Owners | Standard Governance (Workgroup) | STC | No | n/a | n/a | n/a | n/a | n/a | 2023-10-19 | 10/11/2023 - 15/12/2023 | n/a | n/a | 2024-01-26 | 2024-02-07 | TBC | TBC | 2025-05-07
CMP316 | TNUoS Charging Methodology for Co-located Generation | Charging arrangements for Generation sites which comprise multiple technology types within one Power Station (“co-located”) | Pending Authority Decision | The Panel met on 26 April 2019 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 20 June 2019.This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2021 Panel, some Panel members noted that there has been greater interest in co-location over the previous 2-3 months and a Panel Member believed more sites will be re-purposed in the near future. Therefore, the June 2021 Panel agreed to change the priority from "Medium" to Medium to High". Workgroups re-commenced 27 September 2021 and Workgroup Consultation was issued 7 February 2022 and closed 5pm on 28 February 2022 with 8 non-confidential responses received. August 2022 Panel agreed that the Terms of Reference have been met and agreed for CMP316 to proceed to Code Administrator Consultation (but delay by a month so it can be run at this same time as the consequential Modification (CMP397). The consequential Modification (CMP397) was presented to September 2022 Panel and Panel agreed for this to proceed straight to Code Administrator Consultation. Code Administrator Consultation was issued at the same time as the CMP397 Code Administrator Consultation and was run from 4 October 2022 to 5pm on 1 November 2022 and 2 responses were received. Draft Final Modification Report was presented to November 2022 Panel for Panel recommendation vote. 3 Panel Members noted that changes to the legal text for CMP316 WACM1 are required as the legal text does not reflect the intent of CMP316 WACM1. Therefore Panel, under CUSC 8.23.4(iv), asked for the Workgroup to be re-formed (timing TBC) to update the legal text for CMP316 WACM1 and at the same time update the worked example (Annex 8) as to how CMP316 WACM1 works, which will help industry understanding. Panel will need confirmation that Workgroup have agreed the above and then a 2nd Code Administrator Consultation (full 15 Working Days given the extent of the Legal Text changes) will be issued specifically on the updates to CMP316 WACM1. Following conclusion of the 2nd Code Administrator, the Draft Final Modification Report will be re-presented to Panel for their recommendation vote. Given its interaction with CMP316, the CMP397 recommendation vote will also be delayed to when the CMP316 Draft Final Modification Report is re-presented to Panel. The March CUSC Panel 2024 agreed that the Workgroup had completed the required changes to the CMP316 WACM1 legal text and Annex 8 to progress to the Second Code Administrator Consultation was published to industry 25 March 2024 and will close at 5pm on 24 April 2024. The Second DFMR was submitted to the May CUSC Panel for Panel recommendation vote. At the May 2024 CUSC Panel, the Panel recommended by majority that WACM1 better facilitates the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 12 June 2024; CMP316 has an expected decision date of 24 January 2025 ( previously 29 November 2024). On the 13 December 2024 the Authority were unable to form an opinion and have sent back the FMR to Panel for a full review of the legal text for both the Original and WACM1 to be conducted. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status and confirm the new timeline in the February Panel. On the Special CUSC Panel on the 14 February 2025, the Panel agreed that CMP316 should be placed as high priority in the Prioritisation Stack and be progressed alongside the current urgent modifications. The third Code Administrator Consultation will be presented to the June CUSC Panel to agree the send back Terms of Reference have been met. The CUSC Panel agreed on 27 June that following the send back decision, the CMP316 has met the Terms of Reference and can proceed to its Second Code Administrator Consultation which opened on 30 June and will close on 28 July. (11/08/2025) The Panel recommended unanimously that the Original and WACM1 better facilitated the Applicable CUSC Objectives. The Panel has recommended unanimously that the WACM1 is implemented. The Second Final Modification Report was submitted to the Authority on 08 August 2025. | High | NESO | 2019-04-16 | Medium impact on Co-located Generators; Low Impact on NESO | Standard Governance (Workgroup) | None | No | 7 | 8 | 1 | 1 | 1 | 2022-08-26 | First: 04/10/2022 to 01/11/2022 Second: 25/03/2024 to 24/04/2024 Third: 30/06/2025 to 28/07/2025 | 2 (First Code Administrator Consultation), 4 (Second Code Administrator Consultation) | Yes | First: 25/11/2022 Second: 31/05/2024 | Frist: 12/06/2024 / Second: 08/08/2025 | 13/12/2024 /Second May 2026 | TBC | 2026-05-05
CMP328 | Connections Triggering Distribution Impact Assessment | Establish the process when any connection triggers a Distribution impact assessment. | Workgroup Stage | The Panel met on 13 December 2019 and agreed that it goes to a Workgroup. Workgroup meetings were held between 5 August 2020 and 8 September 2021 (note this was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed). Final Modification Report was sent to Ofgem on 10 November 2021 and Ofgem confirmed at November 2021 Panel that no decision would made on this until they have received the equivalent STC Modification. Final Modification Report was issued to Ofgem 6 April 2022 (Final Modification Report for the associated STC change (CM078) was issued to Ofgem on 7 June 2022). On 14 February 2023, Ofgem sent back the CMP328 Final Modification Report for further work and directed CUSC Panel to revise and resubmit the CMP328 Final Modification Report. February 2023 Panel agreed for the Workgroup to be re-formed to address each of Ofgem's concerns and agreed in principle (following the assessment by the Workgroup) that a Code Administrator Consultation is needed to be run before it is re-presented to Panel for Recommendation Vote). They also agreed to place this as Medium to High in the prioritisation stack. Workgroup to review send-back Terms of Reference TBC. SPEN requested to be the new Proposer for CMP328 following SSE's withdrawal as proposer of the modification on 16 April 2024. Ahead of any future Workgroup meetings the ESO and the new Proposer will work to establish the new timeline to answer the deficiencies within the Sendback letter. Awaiting for CMP434 to process and address legal text to reflect DIA initiated around Gate 2. October 2024 CUSC Panel prioritised as Low, therefore no work will take place on this modification until further notice. The Panel will be reviewing the status of this modification in the January 2025 Panel. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. (18/02/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification remained low priority. | Low | Scottish and Southern Energy Power Distribution Limited | 2019-11-28 | Medium Impact on Distribution Network Operators and NESO; Low Impact on New Transmission connected Users | Standard Governance (Workgroup) | STC (CM078) DCUSA (DCP 392) | No | [5 empty] | 2021-09-24 | 27/09/2021 to 18/10/2021 and 10/07/2023 to 07/08/2023 |  |  | 29/10/2021 and 17/08/2023 | 10/11/2021 and 07/09/2023 | TBC (Send-Back 14/02/2023) | TBC | 2025-05-07
CMP330/CMP374 | Allowing new Transmission Connected parties to build Connection Assets greater than 2km in length | To amend the definition of Connection Assets in section 14 of the CUSC to allow cable and overhead line lengths over 2km to be contestable where agreed between the Transmission Owner and the User. | Pending Authority Decision | The Panel met on 13 December 2019 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 21 September 2020 (note this was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed). At June 2020 Panel, Panel determined that the priority of this was Medium to High. CMP330 Workgroup Consultation launched on 26 January 2021 and closed 5pm on 16 February 2021 with 10 responses received and following this, the Proposer sought to widen the defect to cover the wider area of contestability and therefore raised CMP374 and sought to amalgamate this with CMP330. The Panel met on 28 May 2021 to discuss CMP374 and agreed that it goes to a Workgroup. They also agreed to amalgamate CMP374 with CMP330. A CMP330/CMP374 Workgroup Consultation was run between 17 December 2021 and 17 January 2022 and there were 8 non-confidential responses. Workgroup Report was presented to April 2023 Panel and Panel agreed that the Terms of Reference have been met and agreed for CMP330/CMP374 to proceed to Code Administrator Consultation. The Code Administrator Consultation was published on 1 June 2023 and closed at 5pm on 29 June 2023, 6 non-confidential responses were recieved. At the July 2023 CUSC Panel, Panel recommended unanimously that the Proposer’s solution and WACM1 better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 10 August 2023. CMP330/CMP374 had an expected decision date of 08 March 2024 as per Ofgem's update to the August 2023 CUSC Panel. CMP330/CMP374 had an expected decision date of 08 May 2024 (previously 08 March 2024) as per Ofgem's published update on 29 January 2024. CMP330/CMP374 had an expected decision date of 31 July 2024 (previously 08 May 2024) as per Ofgem's update to the May 2024 CUSC Panel on 31 May 2024. CMP330/CMP374 does not have an expected decision date as it is depended on the sendback FMR of CMP414 and CM079 (previously 31 July 2024) as per Ofgem's update to the August 2024 CUSC Panel. (06/03/2025) This modification expected decision date is to be confirmed. | n/a | Energy Potential Limited | 2019-11-28 | High Impact on New Transmission connected Users and Transmission Owners | Standard Governance (Workgroup) | STC (CM079) CUSC (CMP414) | No | n/a | n/a | n/a | n/a | n/a | 2023-04-20 | 01/06/2023 to 29/06/2023 | n/a | n/a | 2023-07-20 | 2023-08-10 | TBC Subject to CMP414 send back | TBC | 2025-03-18
CMP331 | Option to replace generic Annual Load Factors (ALFs) with site specific ALFs | To provide new generators with the option to replace the generic Annual Load Factors (ALFs) used to determine their TNUoS charges with a user-provided ALF. | Rejected | The Panel met on 13 December 2019 and agreed that it goes to a Workgroup. Workgroup meetings commenced 22 September 2022. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. Panel on 29 April 2022 agreed for the priority to move from "Low" to "Low to Medium" on the basis that this has become more pressing for potential new connectees. An additional Terms of Reference (as proposed by the Workgroup) was approved at October 2022 Panel. Workgroup Report to be presented to February 2023 Panel - revised timeline was agreed at November 2022 Panel. Workgroup Consultation issued 12 December 2022 and closed 5pm on 11 January 2023 with 7 non-confidential responses received. Workgroup Report was presented to April 2023 Panel and Panel agreed that the Terms of Reference have been met and agreed for CMP331 to proceed to Code Administrator Consultation. The Code Administrator Consultation was published on 9 May 2023 and closed at 5pm on 31 May 2023, with 3 non-confidential responses received. The June 2023 CUSC Panel recommended by majority that the Proposer’s solution is implemented. The Final Modification Report was sent to Ofgem on 12 July 2023. The expected decision date, provided at the August 2023 CUSC Panel, was 29 September 2023. The expected decision date, provided at the September 2023 CUSC Panel, was 30 October 2023 (previously 29 September 2023). [06/11/2023] On 30 October 2023, the Authority rejected CMP331. | n/a - hidden from tracker | Energy Potential Limited | 2019-11-28 | Medium Impact on New Transmission connected generators; Low Impact on Existing Transmission connected generators and ESO | Standard Governance (Workgroup) | None | No | [5 empty] | 2023-04-20 | 09/05/2023 to 31/05/2023 |  |  | 2023-06-22 | 2023-07-12 | 2023-10-30 | Rejected | 2024-01-30
CMP337 | Impact of DNO Contributions on Actual Project Costs and Expansion Factors | To allow Distribution Network Operators to contribute to the cost of new transmission assets, and allow this contribution to be netted off from the Transmission Owner’s actual project costs in a way which maintains the exact pro-rating of costs between local and wider TNUoS charge elements as is currently in place, | Implemented | The Panel met on 31 January 2020 and asked for clarity on a number of issues (notably the impact on wider TNUoS) before determining whether this should proceed to Workgroup or Code Administrator Consultation. The Panel then met on 28 February 2020 and agreed that it goes to a Workgroup (joint CMP337/CMP338 Workgroup). On 9 March 2020, Proposer requested Urgent treatment of CMP337/CMP338 and on 18 March 2020 Panel considered this request for urgency. The unanimous view of the CUSC Panel was that CMP337/CMP338 met Ofgem’s Urgency criteria and Ofgem granted Urgency on 1 April 2020. Final Modification Report was sent to Ofgem on 3 June 2020 and Ofgem decision approving the Original proposal was received 3 July 2020. [08/04/2024] Implemented 1 April 2024. | n/a - hidden from tracker | SSE | 2020-01-16 | Medium Impact on Distribution Network Operators, Transmission Owners, Remote Island Generators (Shetland, Western Isles and Orkney); Low Impact on ESO and all Users who pay Generation TNUoS | Standard Governance (Workgroup) | None | No | [5 empty] | 2020-05-19 | 2020-05-22 |  |  | 2020-05-29 | 2020-06-03 | 2020-07-03 | 2024-04-01 | 2024-07-17
CMP338 | Impact of DNO Contributions on Actual Project Costs and Expansion Factors – New Definition of Cost Adjustment | Introduce a new definition of “Cost Adjustment” in the CUSC to give effect to CMP337 | Implemented | The Panel met on 31 January 2020 and asked for clarity on a number of issues (notably the impact on wider TNUoS) before determining whether this should proceed to Workgroup or Code Administrator Consultation. The Panel then met on 28 February 2020 and agreed that it goes to a Workgroup (joint CMP337/CMP338 Workgroup). On 9 March 2020, Proposer requested Urgent treatment of CMP337/CMP338 and on 18 March 2020 Panel considered this request for urgency. The unanimous view of the CUSC Panel was that CMP337/CMP338 met Ofgem’s Urgency criteria and Ofgem granted Urgency on 1 April 2020. Final Modification Report was sent to Ofgem on 3 June 2020 and Ofgem decision approving the Original proposal was received 3 July 2020. [08/04/2024] Implemented 01 April 2024. | n/a - hidden from tracker | SSE | 2020-01-16 | Medium Impact on Distribution Network Operators, Transmission Owners, Remote Island Generators (Shetland, Western Isles and Orkney); Low Impact on ESO and all Users who pay Generation TNUoS | Standard Governance (Workgroup) | None | No | [5 empty] | 2020-05-19 | 2020-05-22 |  |  | 2020-05-29 | 2020-06-03 | 2020-07-03 | 2024-04-01 | 2024-07-17
CMP341 | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Enables parties to be derogated from specific CUSC obligations in order to conduct small-scale, time-limited live trials of innovative technologies, connections, products or services | Workgroup Stage | The Panel met on 27 March 2020 and agreed that it goes to a Workgroup (joint workgroup with the equivalent Grid Code Modification (GC0140) due to the level of crossover between the 2 Modifications). Workgroup meetings have not yet commenced. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the quarterly prioritisation deep-dive (at Panel on 28 April 2023), no case was presented to change the priority. At the quarterly prioritisation deep-dive atthe July 2023 Panel, no case was presented to change the priority. October 2024 CUSC Panel prioritised as Low, therefore no work will take place on this modification until further notice. The Panel will be reviewing the status of this modification in the January 2025 Panel. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. (18/02/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there is no change to this priority status. | Low | NESO | 2020-03-12 | Medium Impact on CUSC Parties, CUSC Panel, CUSC Code Administrator and Parties facing barriers to innovation | Standard Governance (Workgroup) | Grid Code (GC0140) | No | [5 empty] | TBC | TBC |  |  | TBC | TBC | TBC | TBC | 2025-03-18
CMP344 | Clarification of Transmission Licensee revenue recovery and the treatment of revenue adjustments in the Charging Methodology | Clarifies that the allowed revenue for Transmission Owners recovered from Transmission Users under the Charging Methodologies is fixed for each onshore price control period for onshore transmission licensees and at the point of asset transfer for OFTOs. | Rejected | The Panel met on 29 May 2020 and agreed that it goes to a Workgroup. Workgroup meetings were held between 3 September 2020 and 24 November 2020.At June 2020 Panel, Panel determined that the priority of this was High. Final Modification Report was sent to Ofgem on 12 January 2021 requesting a decision by 25 January 2021 to meet an Implementation Date of 1 April 2021. However, Ofgem advised they were unable to make a decision by 25 January 2021 and sent back CMP344 on 5 May 2021 as they required further clarity on which OFTO costs the Proposal applies to and they need quantitative information regarding how the change impacts each set of network users. May 2021 Panel agreed for the Workgroup to be re-formed to address each of Ofgem's concerns and agreed in principle (following the assessment by the Workgroup) that a Code Administrator Consultation is needed to be run before it is re-presented to Panel for Recommendation Vote). They also agreed to place this as Medium to High in the prioritisation stack. Workgroups on how to address Terms of Reference agreed by Panel (to address Ofgem's send-back) were held 9 September 2021 and 31 October 2022 (following completion of Independent analysis to show the benefit). At December 2022 Panel, Chair of the CMP344 Workgroup presented how Workgroup had addressed the Terms of Reference set the Panel on 28 May 2021 (to address Ofgem's send-back on 5 May 2021). The Panel expressed no concerns with the approach taken and the Code Administrator Consultation was issued on 16 December 2022 and closed 5pm on 17 January 2023 with 5 non-confidential responses and 1 confidential response received. Draft Final Modification Report was presented to January 2023 Panel for recommendation vote. The Panel by majority recommended that the Original solution is implemented. Final Modification Report was issued to Ofgem on 8 February 2023. CMP344 had an expected decision date of 06 October 2023 (previously 29 September 2023) as per Ofgem's update to the August 2023 CUSC Panel. CMP344 had an expected decision date of 08 December 2023 (previously 29 September 2023) as per Ofgem's update to the September 2023 CUSC Panel. CMP344 had an expected decision date of 05 February 2024 (previously 26 January 2024) as per Ofgem's update published on 29 January 2024. The Authority sent back CMP344 on 12 February 2024 due to deficiencies in the Second Final Modification Report and Annexes. The February 2024 CUSC Panel agreed that the Workgroup should be reconvened ahead of a Second Code Administrator Consultation.The updated timeline was approved at the April 2024 CUSC Panel. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings, external analysis will be completed and the ESO will continue to work on addressing the Send Back deficiencies in preparation for the next Workgroup meeting. October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there is no change to this priority status. On 28 March 2025 at the CUSC Panel the Terms of Refence were determined to have have been met and the modification could proceed to Code Administrator Consultation. The Third Code Administrator Consultation was issued on 12 May and closed at 5pm on 03 June with 2 non-confidential responses. The third Draft Modification Report will be presented to the June CUSC Panel. (03/07/2025) The CUSC Panel on 27 June recommended by majority that the Original better facilitated the objectives than the baseline. The Final Modification Report will be sent to Ofgem on 09 July 2025. 01.05.2026 Authority Rejected modification. | Medium | RWE | 2020-05-13 | High impact on Transmission Owners, Transmission Users including Generators and Suppliers; and a Medium impact on the ESO | Standard Governance (Workgroup) | None | No | n/a | n/a | n/a | n/a | n/a | 2020-11-27 | First: 01/12/2020 to 22/12/2020 Second: 16/12/2022 to 17/01/2023 Third: 12/05/2025 to 03/06/2025 | 3rd CAC - 2 |  | First: 08/01/2021 Second: 19/01/2023 Third: 27/06/2025 | First FMR: 12/01/2021 Second FMR: 08/02/2023 Third FMR: 09/07/2025 | First Send back: 05/05/2021 Second Send Back: 12/02/2024 Final: December 2025 | TBC | 2026-05-05
CMP375 | Enduring Expansion Constant & Expansion Factor Review | Seeks to amend the calculation of the Expansion Constant & Expansion Factors to better reflect the growth of and investment in the National Electricity Transmission System (NETS) | Pending Authority Decision | The Panel met on 26 April 2019 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 5 September 2019. This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 (rather than be formally amalgamated) with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. Workgroups recommenced on 10 August 2021. Workgroup Report will be presented to July 2022 Panel. Workgroup Consultation issued 14 April 2022 and closed 5pm on 17 May 2022 with 28 non-confidential responses (and 1 confidential response) received. CMP315/CMP375 Workgroup Report was going to be presented to May 2023 CUSC Panel. However, although 2 of the solutions are fully developed, there is one new solution that became a WACM at the Workgroup meeting on 2 May 2023 and this needs further development - timescales (given the requirement for further data from the Transmission Owners). The CMP315/CMP375 Workgroup Report was intended to be issued to the July 2023 CUSC Panel, however a new timeline was approved at the July 2023 CUSC Panel to allow for additional solution refinement. The CMP315/CMP375 Workgroup completed their Workgroup Vote on 16 August 2023, the Workgroup Report was issued to the October 2023 CUSC Panel. The October 2023 CUSC Panel agreed that the Workgroup had met its Terms of Reference and that it could proceed to Code Administrator Consultation. To ensure that industry have sufficient time to consider the Consultation it will be issued on 10 November 2023 until 5pm on 15 December 2023. The Code Administrator Consultation was issued on 10 November 2023 until 5pm on 15 December 2023 and received 17 Non confidential responses and 0 Confidential responses. At the January 2024 CUSC Panel, the Panel recommended unanimously that the CMP375 Original solution, and by majority, that WACM2 better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 07 February 2024. CMP375 had an expected decision date of 30 September 2024 as per Ofgem's published update on 2 May 2024. CMP375 had an expected decision date of 30 September 2024 which has now changed to 29 November 2024 as per EDD update from Ofgem on 02 September 2024. CMP375 expected decision date of 07 February 2025 (previously 29 November 2024) as per Ofgem's update at the November 2024 CUSC Panel. (06/03/2025) This modification expected decision date is to be confirmed. | n/a | ESO | 2021-06-10 | High impact on all Users who pay TNUoS charges, NESO, Transmission Owners and Offshore Transmission Owners | Standard Governance (Workgroup) | STC | No | n/a | n/a | n/a | n/a | n/a | 2023-10-19 | 10/11/2023 - 15/12/2023 | n/a | n/a | 2024-01-26 | 2024-02-07 | TBC | TBC | 2025-05-08
CMP376 | Inclusion of Queue Management process within the CUSC | Seeks to implement the queue management process into CUSC including introducing a right for the Electricity System Operator (ESO) to terminate contracted projects which are not progressing against agreed milestones | Implemented | The Panel met on 30 July 2021 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 28 October 2021. Panel on 30 July 2021 placed this as Medium to High in the prioritisation stack given the extensive work already done on "Queue Management" and that the process will be used across industry imminently. The Workgroup on 28 February 2022 was postponed as the Workgroup had provided extensive feedback particularly on the practicality of the proposed milestones that needed to be considered further by the ESO Connections team. CUSC Panel were advised that it was prudent to postpone Workgroups will be paused until September 2022 to allow the ESO Connections team to fully take into account the feedback received and ensure the solution had been fully thought through. Despite this “pause”, Panel agreed that this still “Medium to High” in the prioritisation stack. Industry webinar held 27 July 2022 where ESO Connections team talked through the changes they have made to the Queue Management guidelines following the feedback received and provide stakeholders with an opportunity to ask questions/provide feedback on the new document. Workgroups restarted on 6 September 2022 and Workgroup Report will be presented to February 2023 Panel. Workgroup Consultation was issued on 25 November 2022 and closed 5pm on 23 December 2022 with 31 non-confidential responses and 2 confidential responses received. March 2023 Panel agreed that the Workgroup have met their Terms of Reference. Code Administrator Consultation was issued on 3 April 2023 and closed 5pm on 4 May 2023 with 23 non-confidential responses (including 1 late response) and 1 confidential response received. The May 2023 CUSC Panel unanimously recommended that the Original, WACM1, WACM5 and WACM10, and by majority, the other proposed Solutions better facilitated the CUSC Applicable Objectives. The Final Modification Report was issued to the Authority on 07 June 2023. A decision was expected on 15 September 2023. as per Ofgem's latest published expected decision dates (as at 05 July 2023). CMP376 had an expected decision date of 10 November 2023 (previously 15 September 2023) as per Ofgem's update to the September 2023 CUSC Panel. [14/12/2023] The Authority approved the Original solution on 13 November 2023 - Implemented 27 November 2023. | n/a - hidden from tracker | ESO | 2021-07-15 | High impact on ESO, Transmission Owners, Offshore Transmission Owners, and all Users wanting to utilise or connect to the National Electricity Transmission System;, Low impact on Distribution Network Operators | Standard Governance (Workgroup) | STC? | No | [5 empty] | 2023-03-23 | 03/04/2023 to 04/05/2023 |  |  | 2023-05-18 | 2023-06-07 | 2023-11-13 | 2023-11-27 | 2024-02-27
CMP379 | Determining TNUoS demand zones for transmission-connected demand at sites with multiple Distribution Network Operators (DNOs) | Seeks to clarify how TNUoS demand zones and therefore TNUoS demand tariffs and charges should be determined for transmission-connected demand users who connect at the boundaries of multiple DNO areas | Implemented | The Panel met on 24 September 2021 and agreed that it goes to a Workgroup. Workgroup meetings have not yet commenced. Panel on 24 September 2021 placed this as "Low to Medium" in the prioritisation stack as they considered this has a low materiality and a decision is not needed until end December 2022 (now November 2023). Workgroup Consultation opened 23 September 2022 and closed 5pm on 14 October 2022 with 2 non-confidential responses received. Workgroup Report was presented to December 2022 Panel. The Panel agreed that the Terms of Reference have been met and agreed for CMP379 to proceed to Code Administrator Consultation. Code Administrator Consultation was published on 4 January 2023 and closed on 1 February 2023 with no responses received. February 2023 Panel recommended unanimously that the CMP379 Original should be implemented. Final Modification Report was sent to Ofgem on 8 March 2023. The Authority issued a send back on 09 June 2023, citing discrepancies between the Proposer's solution section of the Final Modification Report and the legal text. The June CUSC Panel approved for a second Code Administrator Consultation which ran from 05 July 2023 until 5pm 26 July 2023, no responses were recieved. The second Draft Final Modification Report was submitted to the August 2023 Panel. The August 2023 CUSC Panel recommended unanimously that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 07 September 2023. [08/04/2024] On 27 October 2023, the Authority approved the Original solution and it was implemented on 01 April 2024. | n/a - hidden from tracker | ESO | 2021-09-09 | Medium impact on Generators, Transmission-connected demand users, Suppliers and ESO | Standard Governance (Workgroup) | None | No | [5 empty] | 2022-12-08 | First CAC: 04/01/2023 to 01/02/2023 Second CAC: 05/07/2023 to 26/07/2023 |  |  | First Vote: 16/02/2023 Second Vote: 25/08/2023 | First FMR: 08/03/2023 Second FMR: 07/09/2023 | Send Back: 30/06/2023 Decision: 27/10/2023 | 2024-04-01 | 2024-07-29
CMP385 | Improvements to Securities and Liabilities provisions within CUSC | In the view of the Proposer, CUSC Section 15 is need of a review and the Energy Networks Association have identified a number of issues that may have an impact on securities and liabilities for Generators and Demand Users. CMP385 seeks to address these issues. | Withdrawn | The Panel met on 25 March 2022 and raised concerns predominantly on the scope of the issue and invited the Proposer (under CUSC 8.19.2) to further develop CMP385 before presenting this and/or additional Modifications to a subsequent meeting of the CUSC Panel. [28/04/2023] On 27 March 2023, Proposer notified Code Admin that they no longer wish to be Proposer of CMP385. CUSC 8.16.10 defines the process for withdrawal and industry were notified on 27 March 2023 and had until 5pm on 3 April 2023 to express their wish to become the new Proposer. As no-one expressed a wish to become the new Proposer by 5pm on 3 April 2023, Panel, on 28 April 2023, were asked under CUSC 8.16.10(b) to agree to the withdrawal of CMP385 - Panel agreed. | n/a - hidden from tracker | Scottish Hydro Electric Power Distribution Plc | 2022-03-10 | High Impact on Generators and Demand Users connecting to the National Electricity Transmission System, Distribution Network Operators, ESO; Medium Impact on Transmission Owners | Standard Governance (Workgroup) | STC | No | [5 empty] | Withdrawn | Withdrawn |  |  | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2024-01-29
CMP392 | Transparency and legal certainty as to the calculation of TNUoS in conformance with the Limiting Regulation | Under CMP391 a definition of “Charges for Physical Assets Required for Connection” which reflects the Limiting Regulation has been added to the CUSC. CMP392 seeks to provide stakeholders with legal certainty and transparency of the methodology including the calculation and the output of the calculation. | Implemented | The Panel met on 30 May 2022 and agreed that it goes to a Workgroup. They also considered the associated request for urgency. The majority view of the CUSC Panel was that CMP392 did not meet Ofgem’s Urgency criteria and Ofgem (on 7 June 2022) decided that CMP392 should not be progressed on an urgent basis. 1st Workgroup held 9 August 2022. ESO's "Calculation of the Generator TNUoS Adjustment Tariff for the purposes of the Limiting Regulation – Guidance for 2023/24" was published 2 February 2023. Workgroup held 17 February 2023 to discuss the differences between the Guidance and the proposed CMP392 Original. Workgroup Consultation ran from 12 April 2023 to 5pm on 5 May 2023 with 6 non-confidential responses received. An updated timeline was approved at the June 2023 CUSC Panel. The Workgroup Report was presented at the July 2023 CUSC Panel. Panel agreed that the Workgroup had met it's Terms of Reference and the Code Administrator Consultation ran from 04 August until 04 September 2023. The Code Administrator Consultation received six responses, the Draft Final Modification Report was issued to the September 2023 CUSC Panel for complete their recommendation vote. The September 2023 CUSC Panel recommended unanimously that the Proposer’s Original solution and WACM2, and by majority that WACM1 better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 13 October 2023. The September 2023 CUSC Panel recommended unanimously that the Proposer’s Original solution and WACM2, and by majority that WACM1 better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 13 October 2023. CMP392 had an expected decision date of 29 February 2024 (previously 31 January 2024) as per Ofgem's published update on 29 January 2024. CMP392 has an expected decision date of 30 April 2024 (previously 29 February 2024) as per Ofgem's published update on 23 February 2024. On 01 May 2024 the Authority approved WACM2 which will be implemented on 01/04/2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | SSE Generation | 2022-05-27 | NESO, Generators liable for TNUoS with consequential effect on Suppliers. | Standard Governance (Workgroup) | None | No | n/a | n/a | n/a | n/a | n/a | 2023-07-28 | 04/08/2023 to 25/08/2023 | n/a | n/a | 2023-09-28 | 2023-10-13 | 2024-05-01 | 2025-04-01 | 2025-05-06
CMP393 | Using Imports and Exports to Calculate Annual Load Factor for Electricity Storage | This modification proposes to alter the definition of Annual Load Factor (ALF) with respect to electricity storage, taking into account imports as well as exports. Here, ‘electricity storage’ refers to all storage that has booked Transmission Entry Capacity (i.e., pumped and battery). | Rejected | The Panel met on 24 June 2022 and agreed that it goes to a Workgroup. Panel agreed that CMP393 will be placed as “Medium” in the prioritisation stack as although there could be a high materiality and complexity (given the analysis required), some Panel Members noted it may be prudent to wait for the TNUoS Taskforce to meet and agree high-level principles. On balance, Panel agreed a "Medium" priority. Workgroups commenced on 2 September 2022. Workgroup Report to be presented to July 2023 Panel. Workgroup Consultation issued 12 May 2023 and closed 5pm on 2 June 2023, with 5 non confidential responses recieved. The Workgroup Report was scheduled to be presented to the July 2023 CUSC Panel, however an updated timeline was submitted for the August 2023 CUSC Panel. A new timeline and amended terms of reference was approved by the August 2023 CUSC Panel. The updated timeline was approved by the February 2024 CUSC Panel for approval. The Workgroup completed their vote on 05 March 2024 and the Workgroup Report was submitted to the March 2024 CUSC Panel, where the Panel agreed that the modification could progress to Code Administrator Consultation.The Code Administrator Consultation was published on 03 April 2024 and will close on 01 May 2024. The Draft Final Modification was submitted to the May CUSC Panel for Panel recommendation vote. At the May 2024 CUSC Panel, the Panel recommended by majority that the Proposer’s solution better better facilitates the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 17 June 2024. [30/09/2024] On 30 September 2024, the Authority rejected the proposed modification. | n/a - hidden from tracker | Zenobe | 2022-06-09 | High impact on Storage Operators, Generators, Transmission Owners, NESO, Parties Liable for TNUoS | Standard Governance (Workgroup) | CUSC (CMP405) | No | [5 empty] | 2024-03-14 | 03/04/2024 to 01/05/2024 |  |  | 2024-05-31 | 2025-06-17 | 2024-09-30 | NA | 2025-03-31
CMP396 | Re-introduction Of BSUoS on Interconnector Lead Parties | Seeks to re-introduce BSUoS on Interconnector Lead Parties to reflect BSUoS is an energy management cost and not a transmission access charge. | Rejected | The Panel met on 16 August 2022 and agreed that it goes to a Workgroup. They also considered the associated request for urgency. The majority view of the CUSC Panel was that CMP396 did not meet Ofgem’s Urgency criteria and Ofgem, on 19 August 2022, did not grant Urgency. As urgency was not granted, Panel, on 26 August 2022, discussed prioritisation and placed as "Medium to High" in the prioritisation stack because there appears to be direct impact on competition and the end consumer. However, the Panel agreed that independent legal advice needs to be commissioned first as important to determine whether or not this proposed change is legally permissible. Panel also set a revised Terms of Reference on this basis and requested that the 1st Workgroup develop and agree the request for legal opinion which would then be issued to an independent KC. Once the QC opinion has been finalised, this will be issued to Panel, who would then revise Terms of Reference and review current “Medium to High” priority. Workgroup met 24 November 2022 to agree questions to be asked of the independent legal firm. These were issued to the independent legal firm on 2 December 2022. Workgroup met with independent legal firm on 17 January 2023 to clarify the ask. Legal advice was issued to Workgroup on 28 March 2023, discussed with Workgroup 14 April 2023 to ensure understanding and give opportunity for Workgroup to seek clarification and was shared with CUSC Panel on 20 April 2023. CUSC Panel on 26 May 2023 requested that the Proposer attend a future CUSC Panel to discuss how to progress the modification. Following the Proposer’s presentation the June CUSC Panel approved for the modification to be progressed to a Code Administrator Consultation, dates to be confirmed. The draft Code Administrator Consultation was issued to the October 2023 CUSC Panel ahead of being published to industry. The Code Administrator Consultation was issued on 27 October 2023 and closed at 5pm 17 November 2023, there were 7 non confidential responses and the Draft Final Modification Report was issued to the December 2023 CUSC Panel. The December 2023 CUSC Panel recommended unanimously that the Proposer’s solution did not better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 05 January 2024. CMP396 had an expected decision date of 16 February 2024 as per Ofgem's published update on 29 January 2024. [19/07/2024] On 19 July 2024, the Authority rejected the proposed modification. | n/a - hidden from tracker | Saltend Cogeneration Company Ltd | 2022-08-11 | High impact on Customers, Suppliers and Generators; Medium impact on NESO | Standard Governance (straight to CAC) | None | No | [5 empty] | N/A - Straight to Code Administrator Consultation | 27/10/2023 to 17/11/2023 |  |  | 2023-12-15 | 2024-01-05 | 2024-07-19 | NA | 2024-10-31
CMP397 | Consequential changes required to CUSC Exhibits B and D to reflect CMP316 (Co-Located Generation Sites) | CMP316 makes changes to Section 14 of the CUSC. CMP397 facilitates CMP316 and proposes consequential changes to CUSC Exhibits B & D | Pending Authority Decision | The Panel met on 30 September 2022 and agreed that it goes straight to Code Administrator Consultation. Code Administrator Consultation was issued at the same time as the CMP316 Code Administrator Consultation and was run from 4 October 2022 to 5pm on 1 November 2022 and no responses were received. Draft Final Modification Report was presented to November 2022 Panel for Panel recommendation vote. 3 Panel Members noted that changes to the legal text for CMP316 WACM1 are required as the legal text does not reflect the intent of CMP316 WACM1. Therefore Panel, under CUSC 8.23.4(iv), asked for the Workgroup (date TBC) to be re-formed to update the legal text for CMP316 WACM1 and at the same time update the worked example (Annex 8) as to how CMP316 WACM1 works, which will help industry understanding. Panel will need confirmation that Workgroup have agreed the above and then a 2nd Code Administrator Consultation (full 15 Working Days given the extent of the Legal Text changes) will be issued specifically on the updates to CMP316 WACM1. Following conclusion of the 2nd Code Administrator, the Draft Final Modification Report will be re-presented to Panel for their recommendation vote. Given its interaction with CMP316, the CMP397 recommendation vote will also be delayed to when the CMP316 Draft Final Modification Report is re-presented to Panel. The Draft Final Modification was submitted to the May CUSC Panel for Panel recommendation vote. At the May 2024 CUSC Panel, the Panel recommended unanimously that the Proposer’s solution better better facilitates the CUSC Applicable Objectives. CMP397 expected decision date of 24 January 2025 (previously 29 November 2024). (06/05/2025) The expected Authority decision date is 30 September 2025. | n/a | NESO | 2022-08-15 | Low impact on Co-located Generators and NESO | Standard Governance (straight to CAC) | CUSC (CMP316) | No | n/a | n/a | n/a | n/a | n/a | N/A - Straight to Code Administrator Consultation | 04/10/2022 to 01/11/2022 | n/a | n/a | 2024-05-31 | 2023-08-09 | EDD May 2026 | TBC | 2026-05-05
CMP398 | GC0156 Cost Recovery mechanism for CUSC Parties | GC0156 will place new obligations, within the Grid Code, upon CUSC Parties who are not contracted with the ESO as Restoration Service Providers. CMP398 proposes to introduce a codified cost recovery mechanism to prevent the affected parties being commercially disadvantaged by the implementation of the new obligations | Implemented | The Panel met on 30 September 2022 and agreed it goes to a Workgroup, which will be run in parallel with GC0156. Workgroup Consultation was opened on 3 January 2023 and closed 5pm on 24 January 2023 with 7 non-confidential responses received. March 2023 Panel agreed that the Workgroup have met their Terms of Reference. Code Administrator Consultation was aligned with that for GC0156 and ran 2 May 2023 until 9 June 2023, there were 4 non-confidential responses and 0 confidential responses. The June 2023 CUSC Panel recommended by majority that the Proposer’s solution, WACM1 and WACM2 better facilitate the CUSC Applicable Objectives. The Final Modification Report was be sent to Ofgem on 11 July 2023. CMP398 had an expected decision date of 06 October 2023 as per Ofgem's update to the August 2023 CUSC Panel. CMP398 had an expected decision date of 31 October 2023 (previously 06 October 2023) as per Ofgem's update to the September 2023 CUSC Panel. CMP398 had an expected decision date of 15 November 2023 (previously 31 October 2023) as per Ofgem's update published on 13 October 2023. CMP398 had an expected decision date of 30 January 2024 (previously 15 November 2023) as per Ofgem's update published on 14 November 2023. CMP398 had an expected decision date of 29 February 2024 (previously 30 January 2024) as per Ofgem's update published on 29 January 2024 [14/03/2024] The Authority approved WACM1 on 29 February 2024 and this was implemented on 14 March 2024. | n/a - hidden from tracker | SSE Generation | 2022-08-15 | High impact on Suppliers and Generators | Standard Governance (Workgroup) | Grid Code (GC0148 and GC0156), CUSC (CMP412), SQSS (GSR032), STC (CM089 and STCP PM0128) | No | [5 empty] | 2023-03-23 | 02/05/2023 to 09/06/2023 |  |  | 2023-06-29 | 2023-07-11 | 2024-02-29 | 2024-03-14 | 2024-06-17
CMP402 | Introduction of Anticipatory Investment (AI) principles within the User Commitment Arrangements | In response to Ofgem’s final decision on Anticipatory Investment (AI) dated 18 October 2022, changes to the current User Commitment provisions as detailed within CUSC Section 15 are required to introduce the AI principles for offshore generators connecting at different times to non-radial offshore transmission network | Workgroup Stage | The Panel met on 25 November 2022 and agreed that it goes to a Workgroup. Workgroup Consultation was issued on 24 May 2023 and closed 21 June 2023, and received 5 non-confidential responses. The Workgroup Report was scheduled to be presented to the July 2023 CUSC Panel, however an updated timeline was approved for the Workgroup Report to be presented at the August 2023 CUSC Panel. A new timeline was approved by the August 2023 CUSC Panel for approval. The Workgroup Report was scheduled to be issued to the September 2023 CUSC Panel, however an updated timeline was approved at the September 2023 CUSC Panel for the Workgroup Report to be submitted to the October 2023 CUSC Panel. The Workgroup Report was scheduled to be issued to the October 2023 CUSC Panel, however the Proposer provided a progress update on the clarity required on the solution including analysis to justify the numbers being codified into the CUSC, the work required on the new WACMs to the October 2023 CUSC Panel. An updated timeline was presented to the December 2023 CUSC Panel. The December 2023 CUSC Panel approved an updated timeline, including for a second Workgroup Consultation to be issued. The next Workgroup meeting will be scheduled once the Proposer has confirmed next steps with The Authority. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings, the Proposer will be developing a new solution. The Proposer reached out to Workgroup members on 13/06/24 with a solution update requesting feedback. October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification remained medium priority. (08/09/2025) In the postponed 03 September Panel, the Panel moved this modification prioity to low. | Low | NESO | 2022-11-10 | High impact on NESO, Offshore Generators, Offshore Transmission Owners, Consumers | Standard Governance (Workgroup) | CUSC (CMP411) | No | [5 empty] | TBC | TBC |  |  | TBC | TBC | TBC | Q3 2024 | 2025-03-18
CMP403 | Introducing Competitively Appointed Transmission Owners & Transmission Service Providers (Section 14) | Seeks to introduce the concept of Competitively Appointed Transmission Owners and Transmission Service Providers for the purposes of introducing Early Competition for the design, build and ownership of Onshore Transmission assets. | Implemented | The Panel met on 25 November 2022 and agreed that it goes straight to Code Administrator Consultation. Code Administrator Consultation is planned to be run at same time as Code Administrator Consultation for associated Grid Code Modification (GC0159) - the timeline for this was uncertain due to delays in the related legislation. An updated timeline for CMP403 and CMP404 was approved at the March 2024 CUSC Panel. The Draft Final Modification was submitted to the May CUSC Panel for Panel recommendation vote.At the May 2024 CUSC Panel, the Panel recommended by majority that the Proposer’s solution better better facilitates the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 11 June 2024. CMP403 had an expected decision date of 30 September 2024 as per Ofgem's update to the August 2024 CUSC Panel. CMP403 expected decision date of 31 January 2025 (previously 30 September 2024) as per Ofgem's update to the November 2024 CUSC Panel. On 25 March 2025 the Authority approved the Original Solution which will be implemented on 08/04/2025. (17/04/2025) On 08 April 2025 this modification was implemented. | n/a | NESO | 2022-11-10 | Low impact on NESO, Transmission Owners, Competitively Appointed Transmission Owners, Generators and Transmission System Operators. | Standard Governance (straight to CAC) | Grid Code (GC0159), STC (CM086/CM087) and SQSS (GSR031) | No | n/a | n/a | n/a | n/a | n/a | N/A - Straight to Code Administrator Consultation | 28/03/2024 to 29/04/2024 | n/a | n/a | 2024-05-31 | 2024-06-11 | 2025-03-25 | 2025-04-08 | 2025-03-28
CMP404 | Introducing Competitively Appointed Transmission Owners & Transmission Service Providers (Section 11) | Seeks to introduce the concept of Competitively Appointed Transmission Owners and Transmission Service Providers for the purposes of introducing Early Competition for the design, build and ownership of Onshore Transmission assets. | Implemented | The Panel met on 25 November 2022 and agreed that it goes straight to Code Administrator Consultation. Code Administrator Consultation is planned to be run at same time as Code Administrator Consultation for associated Grid Code Modification (GC0159) - the timeline for this was uncertain due to delays in the related legislation. An updated timeline for CMP403 and CMP404 was approved at the March 2024 CUSC Panel. The Code Administrator Consultation was published on 28 March 2024 and closed 29 April 2024, it recieved one non-confidential response. The Draft Final Modification was submitted to the May CUSC Panel for Panel recommendation vote. At the May 2024 CUSC Panel, the Panel recommended by majority that the Proposer’s solution better better facilitates the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 11 June 2024. CMP404 had an expected decision date of 30 September 2024 as per Ofgem's update to the August 2024 CUSC Panel . CMP404 expected decision date of 31 January 2025 (previously 30 September 2024) as per Ofgem's update to the November 2024 CUSC Panel. On 25 March 2025 the Authority approved the Original Solution which will be implemented on 08/04/2025. (17/04/2025) On 08 April 2025 this modification was implemented. | n/a | NESO | 2022-11-10 | Low impact on NESO, Transmission Owners, Competitively Appointed Transmission Owners, Generators and Transmission System Operators. | Standard Governance (straight to CAC) | Grid Code (GC0159), STC (CM086/CM087) and SQSS (GSR031) | No | n/a | n/a | n/a | n/a | n/a | N/A - Straight to Code Administrator Consultation | 28/03/2024 to 29/04/2024 | n/a | n/a | 2024-05-31 | 2024-06-11 | 2025-03-25 | 2025-04-08 | 2025-03-28
CMP405 | TNUoS Locational Demand Signals for Storage | Seeks to separate out the demand Year Round locational signals from Peak Security locational Signals and charge (reward) Storage which imports during times other than Triads | Workgroup Stage | The Panel met on 25 November 2022 and agreed that it goes to a Workgroup (in parallel with CMP393). 1st Workgroup was held 13 January 2023. A new timeline was approved by the August 2023 CUSC Panel. The November 2023 CUSC Panel approved the submitted change to the Terms of Reference. The December 2023 CUSC Panel approved the submitted updated timeline. A timeline update was approved by the April 2024 CUSC Panel. The October 2024 CUSC Panel prioritised as Low, therefore no work will take place on this modification until further notice. On 17 December 2024 the Proposer requested the status for this modification be changed to urgent. A Special SQSS Panel was held on the 10 January to dicuss. The Panel by majority agreed that CMP405 met the Authority’s Urgency criteria (a), and therefore recommended urgent treatment. Panel’s recommendation was sent on 10 January 2025 seeking an Authority decision. On the 20 January 2025 the Authority rejected the requested change of governance route from Standard to Urgent. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there is no change to this priority status. On 28 March 2025 the CUSC Panel discussed at length and in detail the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as low on the prioritsation stack. (08/09/2025) In the postponed 03 September Panel, the Panel agreed to keep this modification as low priority. | Low | SSE Generation | 2022-11-10 | High impact on Generators (i.e. Storage), Transmission System Operators, Transmission Owners | Standard Governance (Workgroup) | CUSC (CMP393) | No | [5 empty] | TBC | TBC |  |  | TBC | TBC | TBC | TBC | 2025-11-17
CMP408 | Allowing consideration of a different notice period for BSUoS tariff settings | Following the approval of CMP361 WACM3, of an ex-ante fixed BSUoS tariff with a 9-month notice and 6-month fix, this modification seeks to amend the notice period to a 3-month notice period. | Implemented | The Panel met on 27 January 2023 and agreed that it goes to a Workgroup. Given the high materiality and industry interest, Panel believed a High priority was appropriate. Workgroup Consultation was issued on 27 April 2023 and closed 5pm on 22 May 2023, with 1 confidential and 7 non-confidential. Workgroup Report was due to be presented to June 2023 CUSC Panel, but additional time is required to finalise the legal text and Workgroup Report content ahead of being issued to the CUSC Panel. The Workgroup Report was issued to the July 2023 CUSC Panel. The Panel agreed that the Terms of Reference have been met and agreed for CMP408 to proceed to Code Administrator Consultation. The Code Administrator Consultation was issued alongside the CMP415 Code Administrator Consultation, which ran from 16 August until 5pm 13 September 2023. The Code Administrator Consultation received 7 non confidential (and 0 confidential) responses, the Draft Final Modification Report was issued to the September 2023 CUSC Panel to complete the Panel recommendation vote. The September 2023 CUSC Panel recommended by majority that the Proposer’s solution does not better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 13 October 2023. No confirmed expected decision date has been provided by the Authority due to ongoing conversations with DESNZ. CMP408 had an expected decision date of 09 September 2024 as per Ofgem's published update on 02 May 2024. CMP408 had an expected decision date of 30 September 2024 (previously 09 September) as per Ofgem's published update on 02 September 2024. CMP408 had an expected decision date of 30 October 2024 (previously 30 September 2024) as per Ofgem's update to the September 2024 CUSC Panel. On 30 OCtober 2024 the Authority approved the Original solution. Implementation date 01 April 2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2023-01-12 | High impact on Final Demand Users, Suppliers and NESO | Standard Governance (Workgroup) | CUSC (CMP361 / CMP362) | No | n/a | n/a | n/a | n/a | n/a | 2023-07-21 | 16/08/2023 to 13/09/2023 | n/a | n/a | 2023-09-28 | 2023-10-13 | 30/10/2024 | 2025-04-01 | 2025-03-18
CMP410 | Payment Timescales for Monthly Payments | Seeks to update payment timescales for monthly payments where invoices are issued late. | Implemented | The Panel met on 24 February 2023 and agreed that it goes straight to Code Administrator Consultation. Code Administrator Consultation was opened on 28 February 2023 and closed 5pm on 21 March 2023 with no responses received. Panel unanimously agreed to implement CMP410. [16/05/2023] This was implemented 16 May 2023 as no appeals were received in the Appeals Window from 14 April 2023 to 5pm on 9 May 2023 | n/a - hidden from tracker | National Grid ESO | 2023-02-09 | Low impact on ESO and CUSC Parties | Self Governance (straight to CAC) | None | No | [5 empty] | N/A - Straight to Code Administrator Consultation | 28/02/2023 to 21/03/2023 |  |  | 2023-03-23 | 14/04/2023 to 09/05/2023 | N/A as Self-Governance | 2023-05-16 | 2024-01-29
CMP411 | Introduction of Anticipatory Investment (AI) within the Section 14 charging methodologies. | Seeks to introduce Anticipatory Investment (AI) and a mechanism for the recovery of AI costs within the Section 14 charging methodologies | Implemented | The Panel met on 24 February 2023 and agreed that it goes to a Workgroup. Workgroups commenced 3 April 2023. Panel believed this should be prioritised alongside CMP402 (as this also relates to Anticipatory Investment) and therefore a Medium to High priority was agreed. The Workgroup Consultation opened on 16 June 2023 and ran until 5pm on 07 July 2023, and received 5 non-confidential responses. A new timeline was approved by the August 2023 CUSC Panel for approval. The Workgroup Report was scheduled to be issued to the September 2023 CUSC Panel, however an updated timeline was approved at the September 2023 CUSC Panel for the Workgroup Report to be submitted to the October 2023 CUSC Panel. The Workgroup Report was submitted to the October 2023 CUSC Panel, where the Panel agreed the modification can progress to Code Administrator Consultation. The Code Administrator Consultation ran from 06 November 2023 until 27 November 2023.Tthe Draft Final Modification Report will be issued to the December 2023 CUSC Panel. The December CUSC Panel recommended unanimously that the Proposer’s solution better facilitated the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 05 January 2024. On 28 March 2024 the Authority approved the Original solution to be implemented on 01 April 2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2023-02-09 | High impact on ESO, Offshore Generators, Offshore Transmission Owners, Demand customers | Standard Governance (Workgroup) | CUSC (CMP402) | No | n/a | n/a | n/a | n/a | n/a | 2023-10-19 | 06/11/2023 to 27/11/2023 | n/a | n/a | 2023-12-15 | 2023-01-03 | 28/03/2024 | 2025-04-01 | 2025-03-18
CMP412 | CMP398 Consequential Charging Modification | Seeks to facilitate the implementation of CMP398 and proposes a small change to Section 14 (BSUoS) to ensure that any validated costs arising via the CMP398 solution are recovered (as happens today with black start costs via BSUoS. | Implemented |  | n/a - hidden from tracker | SSE Generation | 2023-02-09 | Low impact on Generators, Suppliers, and Customers | Standard Governance (straight to CAC) | Grid Code (GC0148 and GC0156), CUSC (CMP398), SQSS (GSR032), STC (CM089 and STCP PM0128) | No | [5 empty] | N/A - Straight to Code Administrator Consultation | 02/05/2023 to 09/06/2023 |  |  | 2023-06-22 | 2023-07-11 | TBC | TBC | 2024-06-17
CMP413 | Rolling 10-year wider TNUoS generation tariffs | Seeks to introduce an obligation on the ESO to publish generation tariffs for a rolling 10-year duration and provide the clarity to Users and developers on commercial decisions to support delivery of low carbon infrastructure (across generation and network) at least cost for consumers. | Rejected | [30/09/2024] On 30 September 2024 the Authority rejected the modification | n/a - hidden from tracker | EDF Energy | 2023-03-16 | High impact on Generators, Suppliers, NESO, Demand Users, Consumers | Standard Governance (Workgroup) | None | No | [5 empty] | 2024-02-15 | 26/02/2024 to 18/03/2024 |  |  | 2024-04-26 | 2024-05-08 | 30/09/2024 | NA | 2025-03-31
CMP414 | CMP330/CMP374 Consequential Modification | Seeks to enact the Workgroup solution from CMP330/CMP374, by updating Exhibit B, Section 2 and Section 11 of the CUSC | Workgroup Consultation | The April CUSC Panel agreed that CMP414 should follow Standard Governance and proceed to Code Administrator Consultation. The Code Administrator Consultation was published on 1 June 2023 and closed at 5pm on 29 June 2023, received 4 non-confidentail responses. The Draft Final Modification Report was presented to the July 2023 CUSC Panel. The Panel has recommended unanimously that the Proposer’s solution is implemented. The Final Modification Report was sent to Ofgem on 10 August 2023. CMP414 had an expected decision date of 08 May 2024 (previously 08 March 2024) as per Ofgem's published update on 29 January 2024. The Authority sent back CMP414 on 08 July 2024 due to deficiencies in the Final Modification Report and Annexes. The Authority sent back for CMP414 will be presented at the July 2024 CUSC Panel. The July 2024 CUSC Panel agreed that the Workgroup should be reconvened ahead of a Second Code Administrator Consultation.The TOR were approved at the July 2024 CUSC Panel. Timeline approved by September 2024 Panel. Prioirty was also discussed and agreed to be changed to medium-high. This has not changed the progression of this modification as the moment due to the Hiatus. The October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. Second Workgroup Nominations opened from 06/01/2024 to 27/01/2025. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there is no change to this priority status. In the postponed 03 September Panel, the Panel moved this modification to high priority. A new timeline will be presented to Panel in October Panel with Workgroups to begin. In the September CUSC Panel, the Panel approved the new timeline. 05/05/2026 Workgroup Consultation opened on 24 April and closes 18 May. | High | NESO | 2023-04-13 | Medium impact on Generators, Transmission Owner and NESO | Standard Governance (Workgroup) | CUSC (CMP330/ CMP374) and STC (CM079) | No | [5 empty] | 2026-06-18 | First: 01/06/2023 to 29/06/2023 Second: 29/06/2026 to 20/07/2026 |  |  | First: 20/07/2023 Second: 27/08/2026 | First: 10/08/2023 Second: 10/09/2026 | Send back: 08 July 2024 Second: TBC | As per CMP330/CMP374 | 2026-05-05
CMP415 | Amending the Fixed Price Period from 6 to 12 months | This modification is a consequential modification for CMP408, which looks at a change to a definition in Section 11. Amending the Fixed Price Period from 6 months to 12 months. | Implemented | Proposal issued to the July 2023 CUSC Panel. The July 2023 Panel unanimously agreed that CMP415 should follow the Standard governance and proceed to a joint CMP408 & CMP415 Workgroup ahead of progressing to Code Administrator Consultation. The Panel agreed the Terms of Reference for the Workgroup. The Workgroup met on 02 August 2023 to discuss the WACM and complete the Workgroup Vote. The Workgroup Report would be issued to Panel 16 07 August 2023 and if they agree that the Terms of Reference have been met The Code Adminstrator Consultation is anticipated to run 16 August until 5pm 13 September 2023. The Workgroup Report was issued to Panel on 07 August 2023 and following some minor amends the Code Adminstrator Consultation was issued on 16 August and ran until 5pm 13 September 2023. The Code Administrator Consultation received 6 non confidential (and 0 confidential) responses, the Draft Final Modification Report was issued to the September 2023 CUSC Panel to complete the Panel recommendation vote. The September 2023 CUSC Panel recommended unanimously that the Proposer’s Original solution and by majority that WACM1 do not better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 13 October 2023. No confirmed expected decision date has been provided by the Authority due to ongoing conversations with DESNZ. CMP415 had an expected decision date of 09 September 2024 as per Ofgem's published update on 02 May 2024. CMP415 had an expected decision date of 30 September 2024 (previously 09 September) as per Ofgem's published update on 02 September 2024. CMP415 has an expected decision date of 30 October 2024 (previously 30 September 2024) as per Ofgem's update to the September 2024 CUSC Panel. On 30 September 2024 the Authority approved WACM1 to be implemented on 01 April 2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2023-07-11 | High impact Final Demand Users, Suppliers, NESO | Standard Governance (Workgroup) | CUSC (CMP361 / CMP362) and CMP408 | No | n/a | n/a | n/a | n/a | n/a | 2023-08-07 | 16/08/2023 to 13/09/2023 | n/a | n/a | 2023-09-28 | 2023-10-13 | 30/10/2024 | 2025-04-01 | 2025-03-18
CMP416 | Amending the Fixed Price Period from 6 to 12months with two seasonal tariffs | This modification is a consequential modification for CMP408 which looks at a change to a definition in Section 11, amending the Fixed Price Period from 6 months to 12 months with two seasonal tariffs. | Proposal Rejected | Proposal issued to the July 2023 CUSC Panel. [02/08/2023] The July CUSC 2023 Panel unanimously agreed that CMP416 was substantially the same effect as CMP415 and therefore directed the Panel Secretary to reject the CMP416 proposal as obligated under Section 8.16.6 of the CUSC. | n/a - hidden from tracker | National Grid ESO | 2023-07-11 | High impact Final Demand Users, Suppliers, Electricity System Operator | N/A | N/A | No | [5 empty] | N/A | N/A |  |  | N/A | N/A | TBC |  | 2024-01-29
CMP417 | Extending principles of CUSC Section 15 to all Users | This modification looks to extend the principles of CUSC Section 15 “User Commitment Methodology” to Users on Final Sums methodology, resulting in all Users being on the User Commitment Methodology. This will introduce equitable treatment across User groups and reduce barriers to entry as a User’s security amount will better reflect the transmission liabilities they impose should they cancel connection or reduce capacity | Code Administrator Consultation | Proposal issued to the July 2023 CUSC Panel. The July 2023 CUSC Panel unanimously agreed that CMP417 should follow the Standard Governance Route and proceed to Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Workgroup Nominations opened on 01 August 2023 and closed 29 August 2023. The first Workgroup was scheduled for 06 September 2023. Updated Terms of Reference were approved by the September 2023 CUSC Panel. Due to the Proposer changed their solution and a STC modification also required to progress this modification, a revised timeline was approved at the November 2023 CUSC Panel. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings,the Proposer and Connections SME will complete additional detailed worked examples and verification through a subgroup. October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel.On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there is no change to this priority status. On 28 March 2025 CUSC Panel discussed at length and in detail the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as high on the prioritsation stack. Workgroups are in progress. On 19 January CMP417 Workgroup Consultation opened and closed on 09 February. [05/05/2026] At the CUSC Panel held on 24 April, the Panel agreed that the Terms of Reference have been met and agreed for CMP417 to proceed to Code Administrator Consultation. The Code Administrator Consultation will be published on 28 April, and this will close on 20 May 2026. | High | NESO | 2023-07-12 | High impact on NESO, Distribution Network Operators (DNOs), Transmission Owners (TOs), Users who remain on Final Sums methodology (Distributed connected Demand, Transmission connected Demand and DNOs where work is not triggered by an Embedded Generator (EG) e.g. asset replacement) | Standard Governance (Workgroup) | STC and STCP | No | 12 | 13 | 2 | 0 | 0 | 2026-04-16 | 28/04/2026 - 19/05/2026 | TBC | TBC | 2026-06-26 | 2026-06-30 | TBC | 10 WD after Authority approval | 2026-05-05
CMP418 | Refine the allocation of Dynamic Reactive Compensation Equipment (DRCE) costs at OFTO transfer | Modification of the DRCE cost allocation for offshore wind farms.The proposal seeks to socialise DRCE costs through wider TNUoS charges. Instead of the current system where offshore wind farm generators both (i) provide upfront capital costs for the DRCE before transferring to OFTO and (ii) cover the cost of DRCE via the offshore local circuit tariff for the lifetime of the project. | Rejected | Proposal issued to the August 2023 CUSC Panel. The Panel unanimously agreed that CMP418 should follow the standard governance route and proceed to a Workgroup. The Panel drafted, but did not approve, the Terms of Reference for the Workgroup. Workgroup Nominations opened on 29 August 2023 and were due to close on 19 September 2023. Workgroup Nominations were extended until 27 September 2023. The updated timeline issued to the October 2023 CUSC Panel was approved. A request to update the modification title and terms of reference was approved by November 2023 CUSC Panel for approval. The Workgroup Consultation was issued on 02 January 2024 and closed at 5pm on 22 January 2024, it recieved 6 non confidential responses. The Workgroup Report was issued to the February 2024 CUSC Panel, the Panel agreed that the Workgroup had met their Terms of Reference and could proceed to Code Administrator Consultation. The Code Adminstrator Consultation was published on 29 February 2024 and closed 5pm 21 March 2024. The Code Administrator Consultation received 3 non confidential (and 0 confidential) responses.The Draft Final Modification Report was issued to the April 2024 CUSC Panel to complete the Panel recommendation vote. The Panel has recommended by majority that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 08 May 2024. The Authority sent back CMP418 on 30 September 2024 due to deficiencies in the Final Modification Report. The Authority send back will be presented at the October 2024 CUSC Panel for discussion.The October 2024 Panel unanimously agreed that the CMP418 FMR should be rewritten and clarified, followed by the Workgroup verifying that the updates reflect previous discussions before a second Code Administrator Consultation is issued to Industry.On 29 January 2025 CMP418 ran its Second Code Administrator Consultation which closed on 19 February 2025. In the February CUSC Panel, the Panel recommended by majority that the Proposer's solution better facilitites the CUSC applicable objectives.The Final Modification Report was sent to Ofgem on 11 March. The expected decision date for this modification is 11 July. (06/08/2025) On 04 August 2025 the Authority Rejected this modification. | n/a | Ocean Winds | 2023-08-02 | Medium Impact: Offshore Wind Farm Generators | Standard Governance (Workgroup) | N/A | No | n/a | n/a | n/a | n/a | n/a | 2024-02-15 | Second 29/01/2025 to 19/02/2025 - First 29/02/2024 to 21/03/2024 | n/a | n/a | Second 28/02/2025 - First 26/04/2024 | Second 11/03/2025 First 06/05/2024 | Send back - 30/09/2024. Rejected = 04/08/2025 | N/A | 2025-05-08
CMP419 | Generation Zoning Methodology Review | To review the existing generation zoning methodology to incorporate offshore assets connected as part of the Holistic Network Design (HND) to enable the wider tariff to be applied to offshore generators. This modification seeks to also revisit the issue of zoning further to the expectations set out as part of the Authority decision on CMP324 and CMP325. | Workgroup Stage | Proposal issued to the August 2023 CUSC Panel. The Panel unanimously agreed that CMP419 should follow the standard governance route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Workgroup Nominations opened on 30 August 2023 and closed 20 September 2023. Workgroup Nominations closed on 20 September 2023, the first Workgroup meeting held on 12 October 2023. The updated terms of reference was approved at the October 2023 CUSC Panel. The updated timeline submitted to the January 2024 CUSC Panel was approved. The updated timeline submitted to the April 2024 CUSC Panel was approved. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings, the new Proposer will take on the feedback from the Workgroup and review the scope of the modification and will feedback to the Workgroup once this has been finished. Proposer is continuing to consider how to best progress the modification.The October 2024 CUSC Panel prioritised as High, therefore Workgroup activity will start before the end of January 2025. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed Given the complexity of the defect, the potential for several alternative solutions and the advantage of an early decision on re-zoning for investors, this was placed as “Medium to High” in the prioritisation stack. (08/09/2025) In the postponed 03 September Panel, the Panel moved this modification prioity to low. | Low | NESO | 2023-08-10 | High impact: NESO and parties liable for TNUoS charges. | Standard Governance (Workgroup) | None | No | 15 | TBC | 0 | 0 | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-04-01 | 2025-11-17
CMP420 | Treatment of BSUoS Revenue Recovery and creation of a BSUoS Fund | This modification will codify Over and Under recovery in terms of when this will be returned to or recovered from Industry and any inflation applied to the Over or Under recovery to leave appropriate Parties whole. | Withdrawn | Proposal issued to the September 2023 CUSC Panel and the Panel unanimously agreed that CMP420 should follow the standard governance route and proceed to a Workgroup. The Panel drafted, but did not approve, the Terms of Reference for the Workgroup. Workgroup nominations will run 04 October 2023 and close 5pm on 25 October 2023. The November 2023 CUSC Panel approved the Terms of Reference for the Workgroup. Workgroup meetings commenced from 16 November 2023. An updated terms of reference was approved by the January 2023 CUSC Panel. The Workgroup Consultation was published on 21 March 2024 and will close 19 April 2024. The Proposer withdrew their support for modification on 08 May 2024 and industry were invited to adopt the modification by 15 May 2024. As no Parties came forward the modfication the Proposer's request to withdraw. CMP420 was presented to the May 2024 CUSC Panel and under CUSC 8.16.10(c) the Panel to make a decision on whether to the withdraw the modification. [19/06/2024]The Panel agreed to the withdrawal of the modification under CUSC 8.16.10(c) at the May 2024 CUSC Panel. | n/a - hidden from tracker | SSE | 2023-09-14 | Medium impact: Suppliers | Standard Governance (Workgroup) | None | No | [5 empty] | n/a | n/a |  |  | n/a | n/a | n/a | n/a | 2024-09-18
CMP421 | CUSC Section 14 – Housekeeping changes update | This CUSC modification aims to make minor amendments to CUSC Section 14 | Proposal Rejected | [07/11/2023] Panel Secretary rejected due to further reasoned opinion as to meeting the appropriate governance routes under provision 8.16.5, further details were provided to the October 2023 CUSC Panel who did not reverse the Panel Secretary’s decision to refuse the submission. | n/a - hidden from tracker | ESO | 2023-10-12 | Low Impact: CUSC signatories and ESO | N/A | N/A | N/A | [5 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | 2024-01-29
CMP422 | CUSC Non-Charging Housekeeping changes update | This CUSC modification aims to make minor amendments to CUSC Sections and Exhibits. | Proposal Rejected | [07/11/2023] Panel Secretary rejected due to further reasoned opinion as to meeting the appropriate governance routes under provision 8.16.5, further details were provided to the October 2023 CUSC Panel who did not reverse the Panel Secretary’s decision to refuse the submission. | n/a - hidden from tracker | ESO | 2023-10-12 | Low Impact: CUSC signatories and ESO | N/A | N/A | N/A | [5 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | 2024-01-29
CMP423 | Generation Weighted Reference Node | This modification proposes to switch from a demand weighted Reference Node to a generation weighted Reference Node instead. | Pending Authority Decision | Proposal issued to the October 2023 CUSC Panel. The October 2023 CUSC Panel unanimously agreed that CMP423 should follow the Standard governance route and proceed to a Workgroup. The Panel did not approve the Terms of Reference for the Workgroup. Workgroup nominations closed on 21 November 2023 and Workgroup meetings commenced from 22 January 2024. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings,the ESO will continue with the required further analysis, develop the legal text and share the transport model with the Workgroup members that have signed the software license agreement. The October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. On 17 December 2024 the Proposer requested the status for this modification be changed to urgent. A Special CUSC Panel was held on the 10 January 2025 to review and approve. The Panel by majority agreed that CMP423 did not meet the Authority’s Urgency criteria, and therefore did not recommend urgent treatment. Panel’s recommendation was sent to the Authority on 10 January 2025. On the 20 January 2025 the Authority rejected the requested change of governance route from Standard to Urgent. Standard timeline was presented at the CUSC January Panel. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed due to the complexity and technical aspects of the defect, alongside the amount of time the TNUoS Task Force had already contributed to the development of the solution, the Panel considered modification should be prioritised as ‘Medium to High’. (09/06/2025) The Workgroup Consultation was issued on 28 May and will close on 19 June. On 26 September 2025 the CUSC Panel , the Panel agreed that the Terms of Reference have been met and agreed for CMP423 to proceed to Code Administrator Consultation. The Code Administrator Consultation will be published on 09 October, and this will close on 31 October 2025. The Draft Final Modification Report will be presented to Panel on 28 November 2025. (02/12/2025) The Panel recommended by majority that the Proposer’s solution better facilitates the CUSC Applicable Objectives. The Final Modification Report will be sent to Ofgem on 09 December 2025 | High | SSE | 2023-10-12 | High impact: Generation and Demand Users | Standard Governance (Workgroup) | None | No | 23 | N/A | N/A | 0 | 0 | TBC | 09/10/2025 to 31/10/2025 | 1900-01-11 | No | 2025-11-28 | 2025-12-09 | TBC | 2026-04-01 | 2025-05-08
CMP424 | Amendments to Scaling Factors used for Year Round TNUoS Charges | This modification seeks to introduce a mechanism which sets a lower limit on the variable generation scaling factors used for the purpose of Year-Round Background tariff calculation. This is to address a defect in current methodology which, without any change, we expect to calculate negative scaling factors within the next few years. | Implemented | Proposal issued to the October 2023 CUSC Panel. The Panel unanimously agreed that CMP424 should follow the Standard governance route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Workgroup nominations were extended until 02 January 2024, with Workgroup meetings commencing from 24 January 2023. The Workgroup Consultation was issued on 07 March 2024 and closed on 27 March 2024. The Workgroup Report was submitted to the April 2024 CUSC Panel agreed the Workgroup have met their Terms of Reference and to proceed to Code Administrator Consultation.The Code Administrator Consultation opened on 30/04/2024 and closed on 22/05/24. The DFMR was issued to the June Panel for them to complete their recommendation vote. The FMR was submitted to Ofgem on 09 July 2024. CMP424 has an expected decision date of 06 September 2024 as per Ofgem's update to the August 2024 CUSC Panel. The Authority approved the Original solution on 06 Spetember 2024 and will be implemented 01 April 2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2023-10-12 | Medium impact: Generators, Transmission System Operators, Interconnectors | Standard Governance (Workgroup) | SQSS | No | n/a | n/a | n/a | n/a | n/a | 2024-04-18 | 30/04/2024 to 22/05/2024 | n/a | n/a | 2024-06-20 | 2024-07-09 | 2024-09-06 | 2025-04-01 | 2025-05-08
CMP425 | Billing Demand Transmission Residual By Site | This modification is to provide clarity within the CUSC on how the residual demand charges should be divided between multiple Suppliers at one Connection Site. | Implemented | Proposal issued to the October 2023 CUSC Panel requesting urgency. The October 2023 CUSC Panel by majority recommended that CMP425 met Ofgem’s Urgency criteria and therefore recommended urgent treatment. Panel’s recommendation was sent on 27 October 2023 seeking an Ofgem decision, the Panel recommended that CMP425 proceed to a Workgroup. The Panel did not approve the Terms of Reference for the Workgroup in the Panel meeting. The Authority have granted Urgency for CMP425 and agreed with the timeline put forward by the October 2023 CUSC Panel on 02 November. Workgroup nominations closed on 06 November 2023 and Workgroup meetings commenced on 07 November 2023. The Panel approved the Terms of Reference for the Workgroup via email. The Workgroup Consultation ran from 10 November 2023 and closed on 15 November, recieved 7 non confidential responses. The Workgroup Report was issued to the November 2023 CUSC Panel. The November 2023 CUSC Panel agreed that the Workgroup had met their Terms of Reference and that the modification could progress to Code Administrator Consultation. The Code Administrator Consultation ran from 24 November 2023 until 29 November 2023 and recieved 05 responses. On 06 December 2023 the CUSC Panel recommended that Proposer’s Original solution by majority better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 06 December 2023. [08/01/2024] The Authority approved the Original solution on 13 December 2023, and directed that the Original solution should be made with effect from 01 April 2023 (00:00-00:30). The CUSC was updated on 20 December 2023. | n/a - hidden from tracker | Nissan | 2023-10-24 | High impact: parties on demand sites with multiple TO points that may wish to have separate Suppliers. Low impact: ESO’s billing. | Standard Governance (Workgroup)- Urgent | None | No | [5 empty] | 2023-11-22 | 24/11/2023 to 29/11/2023 |  |  | 2023-12-06 | 2023-12-06 | 2023-12-13 | 01/04/2023 (CUSC updated 20/12/2023) | 2024-04-08
CMP426 | TNUoS charges for transmission circuits identified for the HND to add capacity across boundaries | To consider the cost recovery for circuits being classified as boundary reinforcement within the Holistic Network Design (HND). Ensuring the purpose and function of circuits classified as boundary reinforcement are considered when determining the appropriate TNUoS tariff and users the costs are recovered from. | Workgroup Stage | Proposal issued to the December 2023 CUSC Panel. The December 2023 CUSC Panel unanimously agreed that CMP426 should follow the Standard governance route and proceed to a Workgroup. The Panel approved the Terms of Reference for the Workgroup. Workgroup nominations closed on 12 January 2024 and Workgroup meetings commenced from 05 February 2024. Ahead of the CUSC Panel approving the reconvening of Workgroup meetings, the ESO is completing further analysis which will be available early Summer 2024. October 2024 CUSC Panel prioritised the modification as High. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel will review the modification status in the February Panel. (18/02/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as Medium in the prioritisation stack. | Medium | NESO | 2023-11-30 | Medium impact on NESO and parties liable for TNUoS charges. | Standard Governance (Workgroup) | None | No | [5 empty] | TBC | TBC |  |  | TBC | TBC | TBC | 2025-04-01 | 2025-11-17
CMP427 | Update to the Transmission Connection Application Process for Onshore Applicants | This modification proposes that a Letter of Authority (LoA) should be required for new Onshore Transmission Connection Applications. | Implemented | Proposal issued to the December 2023 CUSC Panel. The December 2023 CUSC Panel unanimously agreed that CMP427 met Ofgem’s Urgency criteria and therefore recommended urgent treatment. Panel’s recommendation was sent on 15 December 2023 seeking an Ofgem decision by 5pm on 21 December 2023. The Panel recommended that CMP427 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. The Authority granted Urgency for CMP427 and agreed with the timeline put forward by the December 2023 CUSC Panel on 20 December 2023. Workgroup nominations closed on 05 January 2024 and Workgroup meetings commenced on 09 January 2024. The Workgroup Consultation ran from 22 January 2024 and closed at 5pm on 26 January 2024, it recieved 21 non-confidential responses. The Workgroup Report was issued to the Special February 2024 CUSC Panel. The Special February 2024 CUSC Panel agreed that the Terms of Reference have been met and agreed for CMP427 to proceed to Code Administrator Consultation. The Code Administrator Consultation was published on 12 February 2024 and closed on 16 February 2024. The Code Administrator Consultation recieved 11 non-confidential responses and 1 confidential response, the Draft Final Modification Report was issued to the February 2024 CUSC Panel who concluded that in order to complete the Panel Recommendation Vote, the Proposer should update the legal text to align with the solution outlined in the Code Administrator Consultation document and gain agreement from the Workgroup ahead of a Second Code Administrator Consultation being issued to industry. The Second Code Administrator Consultation was run from 28 February 2024 to 12pm 04 March 2024 and received 5 non-confidential responses and 0 confidential responses. The Second Draft Final Modification Report was issued to the Special March 2024 CUSC Panel on 06 March 2024. The Panel recommended unanimously that the Proposer’s solution, WACM1, WACM2 and WACM3 better facilitate the CUSC Applicable Objectives and the Final Modification Report was submitted to The Authority on 06 March 2024. [08/04/2024] The Authority approved the Original solution on 15 March 2024 and was implemented on 28 March 2024. | n/a - hidden from tracker | ESO | 2023-12-13 | High impact on ​​Generators, DNO, Demand Users, ESO​. | Standard Governance (Workgroup)- Urgent | None | No | [5 empty] | 2024-02-07 | First: 12/02/2024 to 16/02/2024 Second: 28/02/2024 to 04/03/2024 |  |  | 2024-03-06 | 2024-03-06 | 2024-03-15 | 2024-03-28 | 2024-07-29
CMP428 | User Commitment liabilities for Onshore Transmission circuits in the Holistic Network Design | To define the User Commitment liabilities for generators connected to circuits being classified as onshore transmission within the Holistic Network Design (HND). This is to ensure that the purpose and function of circuits classified as onshore transmission are considered when determining which users are responsible for the associated liabilities. | Implemented | Proposal issued to January 2024 CUSC Panel. The January 2024 CUSC Panel by majority agreed that CMP428 should follow the Standard governance route and proceed to the Workgroup formed for CMP426. The Panel agreed the Terms of Reference for the Workgroup. The next Workgroup meeting is scheduled for 13 February 2024. The Proposer requested requesting urgency at the February 2024 CUSC Panel. The Panel, by majority, recommended that CMP428 met Ofgem’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 26 February 2024 seeking an Ofgem decision by 5pm on 29 February 2024. The Panel recommended that CMP428 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. The Authority granted Urgency on 29 February 2024. The Workgroup Consultation was issused on 14 March 2024 and closed on 21 March 2024. The Workgroup Consultation recieved 6 non-confidential (0 confidential) responses. The Workgroup Report was issued to the Special April 2024 CUSC Panel, and the CUSC Panel agreed whether that Terms of Reference have been met and agree for CMP428 to proceed to Code Administrator Consultation. [29/04/2024] The Code Administrator Consultation was issued on 15 April 2024 and closes 5pm 18 April 2024 and received 7 non-confidential responses and 0 confidential responses. The Draft Final Modification Report was issued to the April 2024 CUSC Panel, to complete the Panel recommendation vote. The Panel recommended unanimously that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 26 April 2024. [19/06/2024] The Authority made the decision to approve CMP428 on 11 June 2024. CMP428 was implemented on Friday 14 June 2024. | n/a - hidden from tracker | ESO | 2024-01-11 | Medium impact on National Grid ESO, Offshore Generators and Consumers. | Standard Governance (Workgroup)- Urgent | None | No | [5 empty] | 2024-04-09 | 15/04/2024 to 18/04/2024 |  |  | 2024-04-26 | 2024-04-26 | 2024-06-11 | 2024-06-14 | 2024-09-18
CMP429 | Typographical and formatting updates following the implementation of CMP376 (Inclusion of Queue Management process within the CUSC) | This modification aims to make minor amendments highlighted through the implementation process on CMP376 | Implemented | Proposal issued to January 2024 CUSC Panel. The Panel unanimously agreed that CMP429 should follow the Fast Track Self Governance route and be implemented on 06 March 2024. [06/03/2024] As no industry parties came forward during the appeals window which ran 06 February 2024 until 5pm 27 February 2024, the modification was implemented on 06 March 2024. | n/a - hidden from tracker | ESO | 2024-01-11 | Low impact on all CUSC Signatories and the ESO | Fast Track self-governance | None | No | [5 empty] | NA | NA |  |  | 2024-01-26 | 06/02/2024 to 27/02/2024 | NA | 2024-03-06 | 2024-06-19
CMP430 | Adjustments to TNUoS Charging from 2025 to support the Market Wide Half Hourly Settlement (MHHS) Programme’ | This Modification looks to amend CUSC Section 14 to rectify defects relating to demand locational Transmission Network Use of System (TNUoS) charging that will become apparent during the Migration Phase of the Market Wide Half Hourly Settlement (MHHS) Programme, taking place between April 2025 and October 2026. | Implemented | Proposal issued to February 2024 CUSC Panel. The Panel unanimously recommended that CMP430 met Ofgem’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 26 February 2024 seeking an Ofgem decision by 5pm on 29 February 2024. Workgroup meetings commenced from 06 March 2024. The Authority granted Urgency on 29 February 2024.The Workgroup Consultation was published on 17 April 2024 and closed on 24 April 2024. The Authority approved a new timeline on the 20 May 2024 and this was presented to the May CUSC Panel.Workgroup Report was presented at the July CUSC Panel. The Workgroup Report was submitted to the July 2024 CUSC Panel. The Panel members agreed the Workgroup have met their Terms of Reference and can proceed to Code Administrator Consultation. Code Administrator Consultation published on 31 July 2025 and closed on 12 August 2024. DFMR was submitted to the August Panel. At the August 2024 CUSC Panel the Panel recommended unanimously that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 23 August 2024. CMP430 had an expected decision date of 30 September 2024 as per Ofgem's EDD update to the 02 September 2024. On 26 September 2024 the Authority approved the Original solution which will be implemented on 01 April 2025. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2024-02-16 | High Impact: Suppliers, Embedded Generators, Transmission connected Demand, NESO | Standard Governance (Workgroup)- Urgent | None | No | n/a | n/a | n/a | n/a | n/a | 2024-07-26 | 31/07/2024 to 12/08/2024 | n/a | n/a | 30/082024 | 2024-08-30 | 2024-09-26 | 2025-04-01 | 2025-05-08
CMP431 | Adjustments to TNUoS Charging from 2025 to support the Market Wide Half Hourly Settlement (MHHS) Programme (Non-Charging)’ | This Modification looks to amend the CUSC Section 3 ‘Use of System’ and Section 11 ‘Interpretations and Definitions’ to rectify defects relating to demand locational Transmission Network Use of System (TNUoS) charging that will become apparent during the Migration Phase of the Market Wide Half Hourly Settlement (MHHS) Programme, taking place between April 2025 and October 2026. | Withdrawn | Proposal issued to February 2024 CUSC Panel. The Panel unanimously recommended that CMP431 met Ofgem’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 26 February 2024 seeking an Ofgem decision by 5pm on 29 February 2024. Workgroup meetings commenced from 06 March 2024. The Authority granted Urgency on 29 February 2024. The Workgroup Consultation was published on 17 April 2024 and closed on 24 April 2024. The Authority approved a new timeline on the 20 May 2024 and this was presented at the May CUSC Panel. The Proposer withdrew their support for modification on 11 July 2024 and industry were invited to adopt the modification by 18 July 2024, no Parties came forward and it was submitted to the July 2024 CUSC Panel for official withdrawal. [26/07/2024] The Panel agreed to the withdrawal of the modification under CUSC 8.16.10(c) at the July 2024 CUSC Panel. | n/a - hidden from tracker | NESO | 2024-02-16 | High Impact: Suppliers, Embedded Generators, Transmission connected Demand, NESO | Standard Governance (Workgroup)- Urgent | None | No | [5 empty] | NA | NA |  |  | NA | NA | NA | 2024-07-26 | 2024-10-31
CMP432 | Improve “Locational Onshore Security Factor” for TNUoS Wider Tariffs | This modification seeks to improve the cost reflectivity of the “Locational Onshore Security Factor” used in calculating Wider TNUoS tariffs, in order for charges to better reflect the way Transmission Owners plan for a secure future network based on the Security and Quality of Supply Standard requirements. | Rejected | Proposal issued to March 2024 CUSC Panel. The March 2024 CUSC Panel unanimously agreed that CMP432 should follow the Standard Governance route and proceed to a Workgroup. Following the Panel approving the Terms of Reference and timeline for the Workgroup, Workgroup nominations were opened 9 April 2024 and closed on 02 May 2024. The October 2024 CUSC Panel prioritised CMP432 as Medium, therefore Workgroup activity was due to start from Spring 2025. On 17 December 2024 the Proposer requested the status for this modification be changed to urgent. A Special CUSC Panel wad held on the 10 January 2025 to review and approve. The Panel by majority agreed that CMP432 met the Authority’s Urgency criteria (a), and therefore recommended urgent treatment. Panel’s recommendation was sent on 10 January 2025 seeking an Authority decision. On the 20 January 2025 the Authority have granted Urgency for CMP432. On 28 April 2025 the Panel agreed the Workgroup met its Terms of Reference and could proceed to Code Administrator Consultation. This opened on 28 April, closed 06 May and received 21 non-confidential responses and 1 confidential response. (15/02/2025) On 15 May a Special CUSC Panel was held where the Panel recommended by majority that the Proposer’s solution is not implemented and the Panel recommended by majority that the Original does not better facilitate the Applicable CUSC Objectives. The Final Modification Report was submitted to the Authority on 15 May 2025 for a decision. On 7 November the Authority rejecteded this modification. | High | SSE | 2024-03-11 | High impact on Generators and Suppliers | Standard Governance (Workgroup)- Urgent | None | No | 13 | 22 | 0 | 0 | 0 | 2025-04-14 | 28/04/2025 - 06/05/2025 | 22 | No | 2025-05-15 | 2025-05-15 | 2025-11-07 | N/A | 2025-05-15
CMP433 | Optimised Transmission Investment Cost model (OpTIC) | OpTIC replaces the Transport component of the Transport and Tariff (T&T) model with an economic market model that reflects proposed network investment, creating charges that aim to leave a market participant in the expected position that they would have been in had they been operating in a zonal wholesale market with assumed optimal network investment | Workgroup Stage | Proposal issued to April 2024 CUSC Panel. The April 2024 CUSC Panel unanimously agreed that CMP433 should follow the Standard Governance route and proceed to a Workgroup. The Panel did not approve the Terms of Reference for the Workgroup. Workgroup Nominations were issued on 13 May 2024 and closed on the 04 June 2024. October 2024 CUSC Panel prioritised as Medium, therefore Workgroup activity will start from Spring 2025. Workgroup nominations were re-opened to recruit additional Workgroup members and observers. This will run from 13 January to 3 February. (18/02/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed there was no change to this modification status. | Medium | Scottish Power | 2024-04-11 | High impact on Suppliers, Generators and Demand customers | Standard Governance (Workgroup) | None | No | [5 empty] | 2026-02-19 | 2025-03-05 |  |  | 2026-04-24 | 2026-05-07 | 2027-08-31 | 2028-04-01 | 2025-05-08
CMP434 | Implementing Connections Reform | The current connections process is not enabling the timely connection of projects to meet net zero. A wholesale revision is needed to the connections process to meet those targets and the needs of project developers and consumers. This proposal introduces new processes and definitions that will update the existing processes and enable projects that are most ready to progress more rapidly to connection. | Implemented | Proposal issued to April 2024 CUSC Panel. The Panel unanimously agreed that CMP434 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 29 April 2024 seeking an Authority decision by 5pm on 01 May 2024. The Panel recommended that CMP434 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. The Authority approved urgency on the 02 May 2024 and Workgroup convened from the 07 May 2024. The amended Terms of Reference were presented to the May CUSC Panel. The amended Terms of Reference were approved at the May CUSC Panel., The Workgroup Consultation was published on 25 July 2024 and closed on 06 August 2024. The next Workgroup meeting is on 19/08/2024.The Workgroup Report was submitted to the November Special CUSC Panel. The Panel members agreed the Workgroup have met their Terms of Reference and can proceed to Code Administrator Consultation. Code Administrator Consultation published on 08 November 2024 and closed on 26 November 2024. Draft Final Modification Report was submitted to the December Special CUSC Panel on 20 December 2024. The Panel recommended unanimously that the Original, WACM3, WACM4 and WACM6 better facilitated the Applicable CUSC Objectives and by majority that WACM1, WACM2, WACM5, and WACM7 better facilitated the Applicable CUSC Objectives. By majority the Panel recommended that WACM6 (3 out of 8 votes) best met the Applicable CUSC Objectives.The Final Modification Report was submitted to the Authority on 20 December. (17/04/2025) On 15 April 2025 the Authority approved WACM2 and directed this modification should be implemented on 10 June 2025. | n/a | NESO | 2024-04-19 | High impact: Transmission Owners, Interconnectors, Generators, Demand, Distribution Network Operators, Independent Distribution Network Operators, NESO and Consumers | Standard Governance (Workgroup)- Urgent | STC (CM095) | No | n/a | n/a | n/a | n/a | n/a | 2024-11-05 | 11/11/2024 - 26/11/2024 | n/a | n/a | 2024-12-20 | 2024-12-20 | 2025-04-15 | 2025-06-10 | 2025-05-08
CMP435 | Application of Gate 2 Criteria to existing contracted background | The related “Implementing Connection Reform” Modification introduces new processes and definitions that will update the existing processes and enable new applicants with more ready projects to progress more rapidly to connection. Gate 2 is a key component of the update; however, the size and rate of growth of the connections queue means that significant action is required as soon as possible to reduce the current queue so that viable projects can be connected more quickly and so that the benefits of our proposed Connections Reform model can be delivered earlier. This Modification seeks to address this by applying a project milestone / criteria (‘Gate 2’) to all existing contracted parties before they are provided with confirmed connection dates and locations | Implemented | Proposal issued to April 2024 CUSC Panel. The Panel unanimously agreed that CMP435 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 29 April 2024 seeking an Authority decision by 5pm on 01 May 2024. The Panel recommended that CMP434 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup.The Authority approved urgency on the 02 May 2024 and Workgroup convened from the 07 May 2024. The amended Terms of Reference were presented to the May CUSC Panel. The amended Terms of Reference were approved at the May CUSC Panel.,the Workgroup Consultation was published on 25 July 2024 and closed on 06 August 2024.The Workgroup Report was submitted to the November Special CUSC Panel. The Panel members agreed the Workgroup have met their Terms of Reference and can proceed to Code Administrator Consultation. Code Administrator Consultation published on 08 November 2024 and closed on 26 November 2024. The Draft Final Modification Report was submitted to the December Special CUSC Panel on 20 December 2024. The Panel recommended by majority that the Original and WACM1 better facilitated the Applicable CUSC Objectives. By majority the Panel recommended that WACM1 (5 out of 8 votes) best met the Applicable CUSC Objectives. The Final Modification Report was submitted to the Authority on 20 December. On 15 April 2025 the Authority approved the Original solution and directed this modification should be implemented on 10 June 2025. | n/a | NESO | 2024-04-19 | High impact: Transmission Owners, Interconnectors, Generators, Demand, Distribution Network Operators, Independent Distribution Network Operators, NESO and Consumers | Standard Governance (Workgroup)- Urgent | STC (CM096) | No | n/a | n/a | n/a | n/a | n/a | 2024-11-05 | 11/11/2024 - 26/11/2024 | n/a | n/a | 2024-12-20 | 2024-12-20 | 2025-04-15 | 2025-06-10 | 2025-05-08
CMP436 | Update CUSC arrangements to replace the Electricity Arbitration Association (EAA) with the London Court of International Arbitration (LCIA) (Non-Charging) | The EAA is now defunct. This modification looks to replace the EAA and replace them with the LCIA from non-charging sections of the codes | Implemented | Proposal raised and submitted to the May 2024 CUSC Panel.At the May Panel meeting, the Panel unanimously agreed that CMP436 should follow the Standard Governance route and proceed to Code Administrator Consultation. This will run from 10 June 2024 to 10 July 2024.The Draft Final Modification Report was submitted to the July CUSC Panel.The Draft Final Modification Report was issued to the July 2024 CUSC Panel, to complete the Panel recommendation vote. The Panel recommended unanimously that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 07 August 2024. CMP436 had an expected decision date of 30 September 2024 as per Ofgem's update to the August 2024 CUSC Panel. CMP436 expected decision date of 12 February 2025 was (Previously 06 December 2024) as per Ofgem's published update on November 2024. CMP436 expected decision date is 'by the end of March'. Authority approved 20/03/2025 with implementation 10 working days later, 3 April 2025. [07/04/2025] This modification was implemented on 03 April 2025. | n/a | NESO | 2024-05-09 | Low impact on CUSC Users | Standard Governance (straight to CAC) | None | Yes | n/a | n/a | n/a | n/a | n/a | N/A | 10/06/2024 - 10/07/2024 | n/a | n/a | 2024-07-26 | 2024-08-07 | 2025-03-20 | 2025-04-03 | 2025-03-31
CMP437 | Update CUSC arrangements to replace the Electricity Arbitration Association (EAA) with the London Court of International Arbitration (LCIA) (Charging) | The EAA is now defunct. This modification looks to replace the EAA and replace them with the LCIA from non-charging sections of the codes | Implemented | Proposal raised and submitted to the May 2024 CUSC Panel. At the May Panel meeting, the Panel unanimously agreed that CMP437 should follow the Standard Governance route and proceed to Code Administrator Consultation. This ran from 10 June 2024 to 28 June 2024.The Draft Final Modification Report was issued to the July 2024 CUSC Panel, to complete the Panel recommendation vote. The Panel recommended unanimously that the Proposer’s solution better facilitate the CUSC Applicable Objectives. The Final Modification Report was sent to Ofgem on 07 August 2024. CMP437 had an expected decision date of 30 September 2024 as per Ofgem's update to the August 2024 CUSC Panel. CMP437 expected decision date of 12 February 2025 (Previously 06 December 2024) as per Ofgem's published update on November 2024. CMP437 expected decision date is 'by the end of March'. Authority approved 20/03/2025 with implementation 10 working days later, 3 April 2025. [07/04/2025] On 03 April 2025 this modification was implemented. | n/a | NESO | 2024-05-09 | Low impact on CUSC Users | Standard Governance (straight to CAC) | None | No | n/a | n/a | n/a | n/a | n/a | N/A | 10/06/2024 - 28/06/2024 | n/a | n/a | 2024-07-26 | 2024-08-07 | 2025-03-20 | 2025-04-03 | 2025-05-08
CMP440 | Re-introduction of Demand TNUoS locational signals by removal of the zero-price floor | This CUSC modification Proposal would remove the current zero price floor from the Transmission Network Use of System (TNUoS) locational demand tariff for Final Demand, thereby re-introducing a locational investment price signal across all of Great Britian(GB). The potential for negative prices and the perverse incentive for users to consume is removed by widening the period over which consumption is measured for charging against negative tariffs. | Pending Authority Decision | The Proposal was presented to the September 2024 CUSC Panel, where the Panel unanimously agreed that CMP440 should follow the Standard route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Workgroup Nominations were published to industry on 04 October until 01 November 2024.The October 2024 CUSC Panel prioritised the modification as High. Timeline was presented to the November 2024 CUSC Panel - Panel agreed to the proposed timeline. First Workgroup was planned for 08 January 2024. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel reviwed the modification status in the February Panel. Workgroup meetings in progress. (09.02.2026) The CUSC Panel agreed on 30 January 2026 that this modification may proceed to the Code Administration Consultation this ran from 09 February to 03 March. [01.04.2026] On 27 March , the CUSC Panel recommended unanimously that the Original and WACM1 better facilitated the Applicable CUSC Objectives. The Final Modification Report was sent to Ofgem on 10 April 2026. | High | RWE | 2024-08-14 | High impact: Suppliers | Standard Governance (Workgroup) | None None: SQSS; Yes No: No; n/a n/a: 6; N/A N/A: 2025-06-19 | 09/02/2026 - 03/03/2026 | 2 confidential responses and 6 non confidential | No | 2026-03-27 | 2026-04-09 | 2026-09-30 | 2027-04-01 | 2026-03-09
CMP441 | Reducing the credit risk of supplying non-embedded hydrogen electrolysers | This modification seeks to address a discrepancy in the timing in de-energising a non-embedded hydrogen electrolyser verses an embedded hydrogen electrolyser | Send Back | The Proposal was presented to the September 2024 CUSC Panel, where the Panel unanimously agreed that CMP441 should follow the Standard route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Post Panel feedback the Proposer updated their solution l requested a Straight to Code Administrator Consultation route at the October 2024 CUSC Panel. The October 2024 Panel agreed that the Proposer had updated their solution so that it could proceed straight to Code Administrator Consultation. The Code Administrator Consultation was published on 29 October 2024 and closed at 5pm on 19 November 2024. DFMR was presented to the December 2024 CUSC Panel. The Panel recommended unanimously that the Proposer’s Original solution is implemented. The Final Modification Report was submitted to the Authority on 23 December 2024. This modification expected decision date is 02/07/2025. On 28 July the Authority sent back this modification for Panel to consider its next steps. This will be presented to Panel on 22 August 2025. (08/09/2025) In the postponed 03 September Panel, the Panel moved this modification prioity to low. | Low | Statkraft | 2024-09-12 | Low impact: Customers, Suppliers and Transmission System Operators | Standard Governance (straight to CAC) | None | No | n/a | n/a | n/a | n/a | n/a | N/A | 29/10/2024 - 19/11/2024 | n/a | n/a | 2024-12-13 | 2024-12-23 | Send Back - 28/07/2025 | N/A | 2025-11-17
CMP442 | Introducing the option to fix Generator TNUoS charges | ​This modification gives Generators the opportunity to fix their wider Transmission Network Use of System (TNUoS) charges against the forecasted tariffs provided by NESO. | Workgroup Stage | Propsal was raised for the October CUSC 2024 Panel. The Panel unanimously agreed that CMP442 should follow the Standard Governance route and proceed to a Workgroup. The Panel did not approve the Terms of Reference for the Workgroup. As the October 2024 CUSC Panel prioritised as High. Timeline presented to the November 2024 CUSC Panel - Panel agreed to the proposed timeline. First Workgroup planned for 16 December 2024. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel reviewed the modification status in the February CUSC Panel. On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as medium on the prioritsation stack. | High | RWE | 2024-09-23 | High impact: ​​Generators, NESO and Suppliers​ | Standard Governance (Workgroup) | None | No | n/a | n/a | n/a | n/a | n/a | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2025-03-18
CMP443 | Removing references to “Fax” or “Facsimile” within the CUSC | This modification seeks to remove references to “fax” and “facsimile” from the CUSC in order to reflect both current and future methods of communication between relevant Users and the National Energy System Operator (NESO) due to the national decommissioning of the Public Switched Telephone Network (PSTN). | Implemented | The Propsal was presented at the October CUSC 2024 Panel, where Panel agreed that it could proceed straight to Code Administrator Consultation. The Code Administrator Consultation was published on 29 October 2024 and closed at 5pm on 19 November 2024. The October 2024 Panel agreed that the Proposer had updated their solution so that it could proceed straight to Code Administrator Consultation. The Code Administrator Consultation was published on 29 October 2024 and closed at 5pm on 29 November 2024. Draft Final Modification Report was presented to the December 2024 CUSC Panel. In the December 2024 CUSC Panel Panel members agreed that a Second Code Administrator Consultation should be held due to missing legal text in the first Code Administrator Consultation. The consultation opened 16 December 2024 to 17 January 2025. The Draft Final Modification Report was presented to Panel on 31 January 2025. The Panel has recommended unanimously that the Proposer’s solution better facilitates the CUSC Applicable Objectives. The Final Modification Report was sent to the Authority on 11 February 2025. On 14 March 2025 the Authority approved and directed that CMP443 be implemented. CMP443 will be implemented on 28 March 2025. [01/04/2025] On 28 March 2025 this modification was implemented. | n/a | NESO | 2024-10-08 | Medium impact Generators, Demand Users, Interconnectors, Distribution Network Operators, NESO | Standard Governance (straight to CAC) | STC and Grid Code | Yes | n/a | n/a | n/a | n/a | n/a | 2025-12-05 | First: 29/10/2024 - 29/11/2024. Second: 16/12/2024 - 17/01/2025 | n/a | n/a | 2025-01-31 | 2025-02-11 | 2025-03-14 | 2025-03-28 | 2025-03-31
CMP444 | CMP444 Introducing a cap and floor to wider generation TNUoS charges | This modification seeks to introduce a temporary cap and floor mechanism to wider generation TNUoS (Transmission Network Use of System) charges, to reduce investment uncertainty for generators and developers. | Rejected | Propsal was raised for the October CUSC 2024 Panel. The Panel majority agreed that CMP444 met the Authority’s Urgency criteria (a), and therefore recommended urgent treatment. Panel’s recommendation was sent on 25 October seeking an Authority decision which was granted on 31 October. The Panel recommended that CMP444 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. The Workgroup Consultation was published on 23 January and closed on 29 January 2025. In the Special CUSC Panel on the 07 March 2025, the Paenl agreed that CMP444 has met their terms of reference and can proceed to Code Administrator Consultation. The Code Administrator Consultation was open from 10 March 2025 and closed 14 March 2025.Draft Final Modification Report to be presented at the March CUSC Panel. The Final Modification Report was submitted to the Authority on the 28 March 2025. Expected decision date for CMP444 is end of July. The Authority are consulting on their minded-to decision to reject CMP444. This will run from 10 July to 11 August. (23/10/2025) On 23 October 2025 the Authority rejected CMP444. | High | NESO | 2024-10-21 | High Impact: Generators, Storage operators, NESO, Suppliers, Consumers​ | Standard Governance (Workgroup)- Urgent | None | No | 25 | 25 non-confidential /5 confidential | None | 14 | 8 | 2025-03-03 | 10/03/2025 - 14/03/2025 | n/a | n/a | 2025-03-28 | 2025-03-28 | 2025-10-01 | 2026-04-01 | 2025-03-28
CMP445 | CMP445 Pro-rating first year TNUoS for Generators | This modification asks the CUSC should be amended to ensure that Generators only pay TNUoS on a pro-rated basis from their Charging Date, during the first year of connection. | Draft Final Modification report | Proposal raised and was presented to the November 2024 CUSC Panel. Panel agreed that the modification met the Authority Urgency criteria (a) and recommended urgent treatment. Panel's recommendation was sent to the Authority on 29 November 2024 seeking an Authority decision by 5pm on 05 December 2024. The Authority didnt approved urgent treatment for CMP445 on the 06 December 2024. Non-urgent timeline was approved by the January CUSC Panel. The Panel reviewed the priority, agreed Terms of Reference and agreed the timeline for CMP445 in the January 2025 Panel. Upon receipt of the Authority Open Letter on 31 January: Outlining their approach to prioritisation of electricity transmission network charging modifications, Panel reviewed the modification status in the February Panel. On 28 March 2025, CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as high on the prioritsation stack. Workgroup meetings in progress. Workgroup consultation was issued on 25 July and will end on 22 August. Workgroup meetings in progress. [01/04/2026] The CUSC Panel agreed on 27 March that the Terms of Reference have been met and agreed for CMP445 to proceed to Code Administrator Consultation. The Code Administrator Consultation will be published on 07 April 2026, and this will close on 01 May 2026. | High | Ocean Winds | 2024-11-08 | High Impact: Generators, Transmission System Operators, Transmission Owners | Standard Governance (Workgroup)- Urgent | None | No | 7 | 8 | 3 | 3 | 2 | 2026-03-19 | 07/04/2026 to 01/05/2026 | 1900-01-08 | n/a | 2026-05-22 | 2026-06-06 | TBC | TBC | 2026-05-05
CMP446 | Increasing the lower threshold in England and Wales for Evaluation of Transmission Impact Assessment (TIA) | This proposal looks to raise the lower threshold at which an Evaluation of Transmission Impact Assessment (TIA) must be undertaken | Implemented | An urgent Proposal was raised on 14 January 2025. A Special CUSC Panel took place on 17 January 2025 whereby the Panel unanimously agreed that CMP446 met the Authority’s Urgency criteria (a), and therefore recommended urgent treatment. Panel’s recommendation was sent on 17 January 2025 . On 22 January 2025 the Authority granted Urgency for CMP446. The first Workgroup was scheduled for 24 January 2025. The Workgroup Consultation was published on 07 February and closed on 13 February. In the Special CUSC Panel on the 10 March 2025, the Paenl agreed that CMP446 has met their terms of reference and can proceed to Code Administrator Consultation. The Code Administrator Consultation was open from 10 March 2025 and closed 17 March 2025.Draft Final Modification Report to be presented at the March CUSC Panel. The Final Modification Report was submitted to the Authority on the 28 March 2025. Expected decision date for CMP446 is 12 May 2025. (14/05/2025) On 12 May 2025 the Authority approved WACM1 and this modification was implemented on 13 May 2025. | High | NESO | 2025-01-14 | High Impact on Transmission Owners, Distributed Connected Generators, Distribution Network Operators, Independent Distribution Network Operators, Electricity System Operator and Consumers | Standard Governance (Workgroup)- Urgent | CMP434/CMP435 | No | 15 | 22 | 0 | 7 | 5 | 2025-03-05 | 10/03/2025 - 17/03/2025 | 16 | No | 2025-03-28 | 2025-03-28 | 2025-05-12 | 2025-05-13 | 2025-05-14
CMP447 | Removal of designated strategic works from cancellation charges/securitisation | This proposal is a follow on to CMP428. CMP428 was limited in its scope to HND, and omitted some other relevant exclusions from attributable works. Also, the decision document on CMP428 suggested there could be a case of those who have fixed their attributable works, to adjust the fix for connectees where this mod would have benefited them had they not fixed, by removing the relevant element of their fix, the rest of the fix remaining as an intact fix. The principle otherwise remains firm that once fixed, attributable works cannot be adjusted | Implemented | The modification propasal was received on 17 January 2025 and presented to Panel in the CUSC Panel on 31 January 2025. The Panel unanimously agreed that CMP447 should follow the Standard Governance route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Nominations opened on 3 February and closed on 24 February. On 14 February 2025 at the Special CUSC Panel the Panel discussed the prioritisation of CUSC Modifications. This modifiaction was not selected as high priority modification. Panel will discuss the priorisation of this modification in CUSC Panel on 28 March. On the 28 March 2025 CUSC Panel, the Panel agreed to place CMP447 as Medium in the prioritisation stack. On 02 May the Panel considered industry feedback and agreed unaminously that CMP447 should be placed as high in the priority stack. A timeline will be presented in the 23 May Panel.At the Special CUSC Panel on 09 June, the Panel agreed that this modification name be changed from 'follow on modification to CMP428' to 'Removal of designated strategic works from cancellation charges/securitisation' and that this modificaiton met the Authority's ugency criteria and therefore recommend urgent treatment. Panel's recommendation was sent on 09 June seeking an Authority decision. On the 12 June 2025 the Authority ranted Urgency for CMP447. The Panel agreed that the Terms of Reference have been met and agreed for CMP447 to proceed to Code Administrator Consultation. The Code Administrator Consultation will be published on 19 September 2025, and this will close on 03 October 2025. A Special CUSC Panel was held on 21 October 2025 whereby the Panel recommended unanimously that the Original, WACM1, WACM2 and WACM3 better facilitated the Applicable CUSC Objectives. The Final Modification Report was submitted to the Authority on 21 October 2025. (21/01/2026) On 07 January the Authority approved CMP447 with an implementation date of 21 January. | High | NESO | 2025-01-17 | (medium) impact on Suppliers (low impact) and Generators (high impact on some) | Standard Governance (Workgroup) | CMP428 / STC CM094 | No | 23 | 27 Non Confidential/2 Confidential | 0 | 3 | 3 | 2025-09-18 | 19/09/2025 - 03/10/2025 | 17 Non Confidential/3 Confidential | 0 | 2025-10-15 | 2025-10-21 | 2026-01-07 | 2026-01-21 | 2025-06-18
CMP448 | Introducing a Progression Commitment Fee to the Gate 2 Connections Queue | This proposal establishes a framework to introduce an additional financial requirement on developers, that can be activated if required, to incentivise the timely removal of unviable projects from the connections queue and facilitate the more timely and efficient connection of viable projects. In doing so it will support progress towards clean power by 2030 (“CP30”) and net zero targets | Implemented | (18/02/2025) The modification proposal was raised as urgent and receivced on 7 February 2025. A Special CUSC Panel took place on 14 February 2025 whereby the Panel by majority agreed that CMP448 met the Authority's Urgency criteria (a), and therefore recommended urgent treatment. Panel's recommendation was sent on 14 February 2005 seeking an Authority decision by 5pm on 18 February 2025. On 20 February 2025 the Authority granted Urgency for CMP448. The first Workgroup is scheduled for 26 Febrruary 2025. Workgroup Consultation was issued on the 24 March 2025 and will close on the 07 April 2025. In the Special CUSC Panel on 09 June, the Paenl agreed that CMP448 had met their terms of reference and can proceed to Code Administrator Consultation. The Code Administrator Consultation will open 10 June and close 24 June. In the Special CUSC Panel on 04 July, the Panel recommended by majority that the Original and WACM1 better facilitated the Applicable CUSC Objectives. The Final Modification Report was sent to the Authority on 04 July. On 08 December the Authority directed that original proposal be implemented on 02 Janaury 2026. | High | NESO | 2025-02-07 | High Impact on Developers, Generators, Transmission System Operators, Interconnectors, Consumers | Standard Governance (Workgroup)- Urgent | CMP434/CMP435 | No | 56 | 36 | n/a | 8 | n/a | TBC | 10/06/2025 to 24/06/2025 |  |  | 2025-07-04 | 2025-07-04 | 2025-12-08 | 2026-01-02
CMP449 | Rectifications to pending 01 April 2025 implementation legal text | This proposal aims to correct legal text errors in modifications which have been approved by the Authority (CMP392, CMP408, CMP411, CMP424 and CMP430) which are due to be implemented on 01 April 2025. | Implemented | On the 28 February the CUSC Panel unaminously agreed that this modification should follow the Fast Track Self Governance route and for the Appeals Window to take place. The modification will be implemented on 01 April 2025 if no Appeals are received. [01/04/2025] On 01 April 2025 this modification was implemented. | n/a | NESO | 2025-02-13 | Postive impact on parties to the CUSC and NESO | Fast Track self-governance | CMP382, CMP408, CMP411, CMP424 and CMP430 | No | n/a | n/a | n/a | n/a | n/a | N/A | N/A | n/a | n/a | 2025-02-28 | 03/03/2025 to 24/03/2025 | N/A | 2025-04-01 | 2025-03-31
CMP450 | ​Introducing the definition of Dynamic Reactive Compensation Equipment (DRCE)​ in the CUSC | ​This modification seeks to introduce the definition of Dynamic Reactive Compensation Equipment (DRCE) in CUSC Section 11, aligning the definition to that included in the Grid Code | Rejected | The modification proposal was raised on 13 February 2025 and was presented to Panel on 28 February 2025. The Panel unanimously agreed that this modification should follow the Standard Governance route and proceed to Code Administrator Consultation. Code Administration Consultation was open on the 03 March and closed 24 March 2025. The Draft Final Modification Report was submitted to the April CUSC Panel. On 02 May the CUSC Panel recommended unanimously that the Original better facilities the Applicable CUSC Objectives. The Final Modificaiton Report will be submitted to the authority on 14 May 2025. On 14 May the Final Modification Report was submitted to the Authority for a decision. (06/08/2025) On 04 August 2025 the Authority rejected this modification | n/a | Ocean Winds | 2025-12-13 | ​Low impact​ | Standard Governance (straight to CAC) | CMP418 | No | n/a | n/a | n/a | n/a | n/a | N/A | 3/03/2025 to 24/03/2025 |  |  | 2025-05-02 | 2025-05-14 | 2025-08-04 | N/A | 2025-05-15
CMP451 | Suspending TNUoS payments when TOs and/or NESO has delayed connection date | The current TNUoS rules require a full year of TNUoS payments even if the connection is made part way through a year. Where a delay to connection date arises due to failure by the TOs and/or NESO to deliver capacity on time, it is not reasonable for a generator to be charged a full year TNUoS where capacity and energisation has been delayed. | Proposal Rejected | An urgent Proposal was raised on 19 February 2025. A Special CUSC Panel was scheduled for 24 February 2025. (24/02/2025) The Panel by majority agreed that CMP451 has substantially the same effect as Pending CUSC Modification Proposal CMP445 and directed the Code Administrator to reject the Proposal under CUSC clause 8.16.6. | TBC | Brockwell Energy | 2025-02-19 | Medium impact | TBC | None | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2025-04-10
CMP452 | Suspension of TNUoS Payments for generators connecting during the 2024/25 charging year | This modification would aim to defer the payments for Generators that connect to the transmission system during 2024/25 until there has been a decision on CMP445. Such deferral would follow a request by a Generator | Withdrawn | On 27 February 2025 an urgent Proposal was raised. A special CUSC Panel was scheduled for 4 March and reconvened on 5 March whereby the Panel unaminously agreed that this modificaton met the Authority's Urgency criteria (a), and therefore recommended urgent treatment. Panel's recommendation was sent on 05 March seeking an Authority decision by 5pm on 06 March. The Proposer withdrew their support for modification on 17 March 2025 and industry were invited to adopt the modification by 25 March 2025. If no Parties came forward the modification the Proposer's request to withdraw CMP452 will be presented to the March 2025 CUSC Panel. (28/03/2025) The Panel agreed to the withdrawal of the modification under CUSC 8.16.10(c) at the March 2025 CUSC Panel. |  | Brockwell Energy | 2025-02-27 | Medium impact on Generators that have or are planning to connect in the 2024/25 charging year. The impact will be zero to other parties and have no effect on the revenues of the TOs or NESO. While the impact is low overall, it would be a major impact on individual Generators. | Standard Governance (straight to CAC) - Urgent | CMP445 | No | n/a | n/a | n/a | n/a | n/a | n/a | 07/03/2025 - 11/03/2025 | n/a | n/a | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-17 | 2025-03-28
CMP453 | ​To Bill BSUoS on a net basis at BSC Trading Units | The move to gross billing of BSUoS means that customers forming part of a BSC Trading Unit are paying BSUoS when the net flows at the point of connection are exports, so the customers are not using the system and should not pay BSUoS. | Pending Authority Decision | Proposal raised on 30 April and will be presented to Panel on 23 May. On 23 May the Panel by majority agreed that CMP453 should follow the Standard governance route and proceed to a Workgroup. On 26 September 2025 The Panel agreed with the revised timeline for CMP453. The Panel also agreed that the Terms of Reference have been met and agreed for CMP453 to proceed to Code Administrator Consultation. The Code Administrator Consultation will be published on 29 September, and this will close on 20 October 2025. (06/11/2025) At the CUSC Panel On 31 October 2025 the Panel recommended by majority that the Proposer’s solution better facilitates the CUSC Applicable Objectives. The Final Modification Report will be sent to Ofgem on 11 November 2025. | High | Triton Power | 2025-04-30 | Medium impact on customers and suppliers. | Standard Governance (Workgroup) | None | No | 6 | 2 | 1 | none | none | 2025-09-18 | 29/09/2025 - 20/10/2025 | TBC | TBC | 2025-10-31 | 2025-11-11 | 2026-09-30 | 2027-04-01 | 2025-06-18
CMP454 | ​CMP434/CMP435 Section 11 Changes | Following The Authority’s decision on approving CMP434/CMP435 on 15 April 2025, two resultant definition changes are recommended to CUSC Section 11 to define to concepts of “Gated Offers” and “Variations Clause” as respectively used in the CMP434/CMP435. | Implemented | Proposal raised on 10 June and will be presented to the CUSC Panel on 27 . The Panel unanimously agreed that CMP454 should follow the Self Governance route and proceed to Code Administrator Consultation. This will run from 03 July to 31 July. The Draft Final Modification Report will be presented to Panel on 03 September. In the postone 03 September Panel, the Panel unanimously approved the Draft FInal Modification Report. The Appeals window is scheduled for 11 September to 02 October with Implementation on 07 October. | n/a | NESO | 2025-06-10 | Low impact on CUSC Schedule 1 Signatories and National Energy System Operator | Self Governance (straight to CAC) - Urgent | None | No | n/a | n/a | n/a | n/a | n/a | n/a | 03/07/2025 to 31/07/2025 | 2 | Yes | 2025-08-22 | 11/09/2025 - 02/10/2025 | n/a | 2025-10-07
CMP455 | ​Minor Amendments to the CUSC following implementation of CMP434/ CMP435 | Following The Authority’s decision on approving CMP434/CMP435 on 15 April 2025, a number of minor clarifications are suggested to CUSC Section 2, 6, 11, 18 and Exhibit U. | Implemented | Proposal raised on 10 June and will be presented to the CUSC Panel at 27 June. The Panel unanimously agreed that CMP455 should follow the Fast Track - Self Governance route. The appeals window opened on 30 June and close on 21 July. (06/08/2025) This modification was implemented on 22 July 2025. | n/a | NESO | 2025-06-10 | Low impact on CUSC Schedule 1 Signatories and National Energy System Operator | Fast Track self-governance | None | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 30/06/2025 to 21/07/2025 | n/a | 2025-07-22 | 2025-06-18
CMP456 | Cost recovery for legacy plant in relation to GC0168 | Implementation of GC0168 brings the obligation, on request, for existing plant to procure and submit EMT plant models. This is a considerable task for older plant with multiple discreet systems. The cost of this is significant and the benefit is not to the generator involved..This modification is to enable suitable cost recovery for the provision of such models. | Workgroup Consultation | Proposal raised on 19 June. CMP456 is linked to GC0168 'Submission of Electro Magnetic Transient (EMT) Models' which was delayed going to Code Administrator Consultation. Progression on GC0168 will affect CMP456 moving forward. Proposer to confirm whether CMP456 should be progressed on an urgent basis and then presented to CUSC Panel. A critical friend check has been carried out and will be presented in the CUSC Panel on 12 December requesting this be treated as an u​rgent modification to proceed under a timetable agreed by the Authority (with an Authority decision).​ On 19 December 2025 the Authority rejected that CMP466 should be progressed on an urgency basis and should follow the standard timeline set out in the Panel's letter. At the CUSC Panel held on 30 January, the Panel discussed that CMP456 should be assigned as a high priority. Majority of Panel members agreed that the unexpected financial impact to generators along with a simplistic solution meant this could be progressed quickly and align with GC0168. 05/05/2026 Workgroup Consultation opened on 23 April and closes 15 May. | High | RWE | 2025-06-19 | High impact on Generators and Suppliers | TBC | GC0168 | TBC | 4 | TBC | TBC | TBC | TBC | 2025-05-14 | 27/05/2026 - 17/06/2026 | TBC | TBC | 2025-07-31 | 2026-08-12 | TBC | TBC | 2026-05-05
CMP457 | Revision of the Obligatory Reactive Power Service (ORPS) | The rising cost of ORPS provision reflects the compensation rate for ORPS, being reflective of gas prices. The increasing shift away from gas to low carbon generation requires a re-evaluation of compensation principles rather than a simple updating of values. This update to the Connection and Use of System Code (CUSC) will incorporate the output from the ORPS project to introduce a fair and transparent payment methodology. | Workgroup Stage | Proposal raised on 11 July and presented to Panel on 25 July. The Panel gave the Proposer some feedback and will be brought back to the postponed 03 September to agree a governance route. In the postponed 03 September Panel, the Panel requested the modification be presented again in the October Panel due to a report being published on 25 September that can help with the solution development. (06/11/2025) In the Special CUSC Panel held on 21 October 2025 the CUSC Panel unanimously agreed that CMP457 should follow the Standard Governance route and proceed to a Workgroup. The Terms of Reference will be agreed at the CUSC Panel on 31 October 2025. Workgroup nominations opened on 23 October and will close on 13 November. October 2025 Update: Panel decided to place CMP457 as Medium priority and advised that key publications should be out before the Workgroups starts. | Medium | NESO | 2025-07-11 | High impact on all Generators that have agreed to be bound by the provisions of the Grid Code | Standard Governance (Workgroup) | None | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
CMP458 | Prorating of transmission residual demand charges | This proposal seeks to change the way Demand Residual is billed and enable customers that consume for part of a year to pay demand residual charges for only that part. | Proposal Withdrawn | Proposal raised on 6 August. In the Special CUSC Panel held on 14 August,the Panel were unable to consider the request for Urgency until further clarification on the charging methodology from NESO was provided. On 18 August the Proposer withdrew the modifiaction. The request for withdrawal will be discussed at the CUSC Panel held on 03 September. (08/09/2025) In the ponstponed 03 September Panel, the Panel agreed as no new proposer came foward, this modification can be withdrawn. | TBC | JG Pears | 2025-08-06 | Low impact on customers, suppliers and NESO | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
CMP459 | Charging TNUoS on a monthly basis | The proposal seeks to change charging TNUoS on a monthly basis rather than the current annual basis. | Proposal Rejected | (11/08/2025) Proposal raised on 6 August. In the Special CUSC Panel held on 14 August, the Panel by majority agreed that CMP459 has substantially the same effect as Pending CUSC Modification Proposal CMP445 and directed the Code Administrator to reject the Proposal under CUSC clause 8.16.6. | TBC | Brockwell Energy | 07/08/25025 | Medium impact on Generators. | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
CMP460 | Improving Transmission Connection Asset Charging | This modification proposes improvements to the framework for charging Transmission Connection Assets. The proposal seeks to socialise costs and cap customer contributions to create a more certain and fair charging methodology. | Workgroup Stage | Proposal raised on 08 August 2025. CMP460 will be presented to the CUSC Panel on 26 September. The Panel unanimously agreed that CMP460 should follow the Standard Governance route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. Nominations opened on 26 September and closed on 17 October. CMP460 proceeded to Workgroup Consultation which opened on 28 January 2026 and closed 18 February 2026. | High | Innova | 2025-08-08 | High impact on Transmission Owners, Distribution Network Owners, Generators, Demand Customers, Transmission System Operators | Standard Governance (Workgroup) | DCP461 |  | 18 | 26 | 0 | 0 | 0 | 2026-05-14 | 22/05/2026 - 15/06/2026 | TBC | TBC | 2025-07-31 | 2026-08-10 | 2026-09-30 | 2027-04-01
CMP461 | Rectifications to Legal Text following various implementations | This modificwstion aims to correct Legal Text errors found whilst carrying out implementations for the Authority approved modifications CMP434, CMP435, CMP443 & CMP454 and an internal review. | Implemented | Proposal raised on 16 October 2025. CMP461 was presented to the CUSC Panel whereby the Panel unanimously agreed that CMP461 should follow the Fast Track SelfGovernance route and be implemented. The Appeals window will open on 10 November and close 01 December. (02/12/2025) No appeals were received. CMP462 will be implemented on 08 December 2025. | n/a | NESO | 2025-10-16 | Low impact on parties to the CUSC and NESO | Fast Track self-governance | None | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 10/11/2025 - 01/12/2025 | n/a | 2025-12-08
CMP462 | Provision for Alternate Panel Members | This modification will give provision for the Code Administrator to run an expedited Alternate Election Process where the CUSC election process has not resulted in the election of Alternate Panel Members. | Implemented | Proposal raised on 24 October 2025 and presented to Panel on 31 October 2025. The Panel unanimously agreed that CMP462 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 31 October 2025 seeking an Authority decision by 5pm on 05 November 2025. On 7 November the Authority agreed that this modification progress on an urgent basis. CMP462 Code Administrator Consultation opened on 11 November and will close on 25 November. The Draft Final Modification Report will be presented to Panel on 12 December 2025. The Final Modification Report was sent to the Authority on 12 December 2025. (05.02.2026) The Authority approved CMP462 on 4 February 2026 and directed this modification be implemented into the CUSC on 11 February 2026. | High | NESO | 2025-10-24 | High impact on National Energy System Operator and CUSC Schedule 1 Parties | Standard Governance (straight to CAC) - Urgent | None | No | n/a | n/a | n/a | n/a | n/a | n/a | 11/11/2025 - 25/11/2025 | 3 | none | 2025-12-12 | 12.12.2025 | 2026-02-04 | 2026-02-11
CMP463 | Stabilising the Specific Onshore Expansion Factors from 1st April 2026 | The Price Control from April 2026 has led to large, unexpected increases in Specific Onshore Expansion Factors. This modification seeks to hold those Specific Expansion Factors at 2025/26 levels, similar to the CMP353 approach, ahead of a larger more fundamental review of TNUoS. | Implemented | Proposal raised on 31 October 2025 requesting urgency. A Special CUSC Panel was held on 14 November 2025. The Panel unanimously agreed that CMP463 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 14 November 2025 seeking an Authority decision by 5pm on 21 November 2025. The Panel recommended that CMP463 proceed to Code Administrator Consultation. On 19 November 2025 the Authority approved the urgency timeline. The Code Administator Consultation opened on 21 November - 25 November. The Final Modification Report will be presented to the CUSC Panel on 12 December 2025. The Final Modification Report was sent to the Authority on 12 December 2025. On 27 January 2026 the Authority approved CMP463 and directed this modification be implemneted on 01 April 2026. | High | SSE | 2025-10-31 | High impact on Generators | Self Governance (straight to CAC) | None | TBC | n/a | n/a | n/a | n/a | n/a | n/a | 21/11/2025 - 25/11/2025 | 8 | none | 2025-12-12 | 12.12.2025 | 2026-01-27 | 2026-04-01
CMP464 | Section 14 Corrections | Following a review of Legal Text, NESO have identified minor errors and improvements to CUSC Section 14. These are either errors which were present in approved legal text, or formatting, numbering or cross-reference errors introduced as a result of multiple implementations over time. | Implemented | Proposal raised on 12 November and will be presented to the CUSC Panel on 28 November 2025. The CUSC Panel agreed that further clarifications were needed on the proposed legal text. CMP464 will be discussed at the Panel meeting on 30 January 2026 where Panel will agree the Governance route and next steps. The Proposer of CMP464 will present the modification to Panel in the 27 February 2026 CUSC Panel. The Panel Panel unanimously agreed that CMP464 should follow the Fast Track - Self Governance route and proceed to be implemented. CMP464 went to industry for Appeals on 03 March and closed on 23 March with no Appeals received. This modification was implemented on 01 April 2026. | N/A | NESO | 2025-11-13 | On parties to the CUSC and NESO | Fast Track self-governance | None | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 03/03/2026 to 23/03/2026 | N/A | 2026-04-01
CMP465 | Construction Progression Milestones (M5-M8) Neutrality | Given the extension in the provision of the G2tWQ Connections offers till 2026 (from end 2025) this proposal seeks to give affected Users the option to be placed back to the position they would have been (in terms of M5-M8 milestones only) had this extension not occurred. | Withdrawn | Proposal raised on 13 November requencing urgency. A special CUSC Panel is scheduled for 21 November 2025 where the CUSC Panel will determine the governance route. The Panel by majority agreed that CMP465 met the Authority’s Urgency criteria (a) and (c) and therefore recommended urgent treatment. Panel’s recommendation was sent on 21 November 2025 seeking an Authority decision. On 09 December 2025 the Authority directed that CMP465 should not be progressed on an urgent basis. On 19 January the Proposer withdrew the modification with the justification that the Authority Decision to reject urgency and the Proposer's assessment that the current core defects have now been addressed by NESO in the updated guidance published on 23 December 2025 (particularly shown on page 19). A request for a new Proposer to adopt CMP465 opened on 15 January and will close on 23 January. The Panel will determine the next steps of the modification at the CUSC Panel on 30 January. (05.02.2026) On 30 January 2026 the Panel agreed to the withdrawal of CMP465 under CUSC 8.16.10(c). | Low | SSE | 2025-11-13 | Generators and demand | Standard Governance (straight to CAC) | None | TBC | TBC | n/a | n/a | n/a | n/a | n/a | TBC | TBC | TBC | TBC | TBC | TBC | TBC
CMP466 | CMP456 Consequential Charging Modification | GC0168 requires existing plan, upon request to obtain and submit Electro Magnetic Transient (EMT) models. This is a significant and costly challenge for older plant with complex systems and with little direct benefit to the Generator. This modification enables appropriate cost recovery. | Workgroup Consultation | Proposal raised on 13 November requencing urgency. A special CUSC Panel is scheduled for 21 November 2025 where the CUSC Panel will determine the governance route. The Proposal was presented at the CUSC Panel on 12 December whereby the Panel by majority agreed that CMP466 did not meet the Authority’s Urgency criteria (a) and therefore did not recommended urgent treatment. Panel’s recommendation was sent to the Authority on 12 December 2025 seeking an decision by 5pm on 19 December 2025. (21/01/2026) On 19 December 2025 the Authority rejected that CMP466 should be progressed on an urgency basis and should follow the standard timeline set out in the Panel's letter. The CUSC Panel carried out a deep dive of the prioritisation stack and the Panel agreed that similarly to CMP456, CMP466 should be assigned as a high priority. Majority of Panel members agreed that the unexpected financial impact to generators along with a simplistic solution meant this could be progressed quickly and align with GC0168. 05/05/2026 Workgroup Consultation opened on 23 April and closes 15 May. | High | RWE | 2025-12-02 | Generators and demand | Standard Governance (Workgroup) | CMP456 | TBC | 4 | TBC | TBC | TBC | TBC | 2025-05-14 | 27/05/2026 - 17/06/2026 | TBC | TBC | 2025-07-31 | 2026-08-12 | TBC | TBC | 2026-05-05
CMP467 | Removal of outdated references in CUSC (charging) | Proposal seeks to remove outdated references in CUSC to Seven Year Statement, Offshore Development Information Statement, and Electricity Ten Year Statement | Proposal Raised | Proposal raised on 25 February and will be presented to the CUSC Panel on 22 May due to incomplete legal text. | TBC | NESO | 2026-02-25 |  | Standard Governance (straight to CAC) | STC | TBC | N/A | N/A | N/A | N/A | N/A | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-04-27
CMP468 | Removal of outdated references in CUSC (non-charging) | Proposal Removes outdated references in CUSC to Seven Year Statement, Offshore Development Information Statement, and Electricity Ten Year Statement. | Proposal Raised | Proposal raised on 25 February and will be presented to the CUSC Panel on 22 May due to incomplete legal text. | TBC | NESO | 2026-02-25 |  | Standard Governance (straight to CAC) | STC | TBC | N/A | N/A | N/A | N/A | N/A | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-04-27
CMP469 | GC0186 Cost Recovery mechanism for CUSC Parties (non-charging) | The GC0186 modification will place new obligations within the Grid Code, upon Connection and Use of System Code (CUSC) Parties who are not contracted with the National Energy System Operator (NESO) as Restoration Service Providers. Therefore, a one-year time extension of the codified cost recovery mechanism is required to prevent the affected parties being commercially disadvantaged | Code Administrator Consultation | Proposal raised on 11 March and presented to the CUSC Panel on 27 March. The CUSC Panel agreed on 27 March that CM469 will be discussed at the April 2026 Panel meeting to allow further discussions between the Proposer and NESO. [05/05/2026] The CUSC Panel met on 24 April and by majority agreed that CMP469 should follow the Standard Governance route and proceed to Code Administrator Consultation. The Code Administrator Consultation opened on 27 April, and this will close on 19 May 2026. | N/A | SSE | 2026-03-11 | High Impact on Suppliers & Generators | Standard Governance (straight to CAC) | GC0168 | No | N/A | N/A | N/A | N/A | N/A | N/A | 27/04/2026 - 19/05/2026 | TBC | TBC | 2026-06-26 | 2026-07-07 | TBC | TBC | 2026-05-05
CMP470 | Introducing an Oversubscribed Technologies Commitment Fee | This modification seeks to introduce a floor on securities through an Oversubscribed Technologies Commitment Fee for all technologies which are oversubscribed relative to Clean Power 2030 capacity targets. | Workgroup Stage | Proposal raised on 20 March rquesting urgency. The CUSC Panel met on 27 March and by majority agreed that CMP470 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 27 March 2026 seeking an Authority decision by 5pm on 02 April 2026. Workgroup nominations opened on 30 March and closed 02 April. | Urgent | Field Energy | 2026-03-20 | High impact on generation developers and a Medium Impact on Transmission Owners | Standard Governance (Workgroup)- Urgent | None | No | 40 | 58 | TBC | TBC | TBC | TBC | 08/06/2026 - 15/06/2026 | TBC | TBC | 2026-06-26 | 2026-06-30 | TBC | TBC | 2026-05-05
CMP471 | Interim Contract Variation Process Ahead of CMP434 Gated Application Window | This modification proposes a temporary, limited amendment to the CUSC allowing Users to adjust elements of their NESO contracts before the first CMP434 Gated Application Window | Proposal Raised | Proposal raised on 23 March requesting urgency. The mod was presented to the CUSC Panel on 24 April 2026. The Panel did not agree the scope and defect were clear and requested this be returned. 14/05/2026 CMP471 will be presented to the CUSC Panel at a Special CUSC Panel on 15 May 2026. | TBC | Muirhall Energy Limited | 2026-03-23 | High impact on Generators, Transmission Owner, NESO | Standard Governance (straight to CAC) - Urgent | Grid Code | No | N/A | N/A | N/A | N/A | N/A | N/A | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-05-14
CMP472 | Large Embedded Generators (LEGs) Original Red Line Boundary (ORLB) Sharing Without Customer Consent | This proposal seeks to introduce a new clause in Section 17 of the CUSC to permit NESO to share the Original Red Line Boundary (ORLB) submitted by Large Embedded Generators (LEGs) with the relevant DNOs without requiring explicit customer consent. This change enables DNOs to independently and consistently verify distribution contract validity for LEGs applying for Gate 2 offers, ensuring that only projects with compliant and valid distribution arrangements progress through the gated connections process. | Code Administrator Consultation | Proposal raised on 09 April and will be presented to the CUSC Panel on 24 April 2026. [05/05/2026] The Panel unanimously agreed that CMP472 should follow the Standard Governance route and proceed to Code Administrator Consultation. The Code Administrator Consultation opened on 27 April, and this will close on 19 May 2026. | N/A | NESO | 2026-04-09 | Medium impact on Large Embedded Generators, NESO, DNOs | Standard Governance (straight to CAC) | This proposal is an effort in facilitating the effective implementation of the Connections Reform package (CMP 434) | No | N/A | N/A | N/A | N/A | N/A | N/A | 27/04/2025 - 19/05/2026 | TBC | TBC | 2026-06-19 | 2026-07-07 | TBC | TBC | 2026-05-05
CMP473 | Clarification of contract updates required with a Gate 2 Modification Offer | Updates to Existing Agreement appendices included within Gate 2 Modification Offers lack consistent treatment, particularly in relation to a network company causing a Completion Date delay. This modification intends to clarify which updates to Existing Agreements shall be implemented. | Pending Authority Decision | Proposal raised on 13 April requesting urgency. A Special CUSC Panel was held on 21 April 2026 to discuss governance route. The Panel by majority agreed that CMP473 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 21 April 2026 seeking an Authority decision by 5pm on 28 April 2026. The Panel recommended that CMP473 proceed to Code Administrator Consultation. Authority Decision still pending. | TBC | RWE | 2026-04-13 | High impact on Generators, Demand Customers, Transmission System Operators, Transmission Owners | Standard Governance (straight to CAC) - Urgent | None | No | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-05-05
CMP474 | Fixed BSUoS Price reset mechanism | Inclusion in the CUSC of a clear process for when BSUoS will be reset by NESO. | Workgroup Stage | Proposal raised on 14 April requesting urgency. A Special CUSC Panel was held on 21 April 2026 to discuss governance route. The Panel unanimously agreed that CMP474 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 21 April 2026 seeking an Authority decision by 5pm on 27 April 2026. The Panel recommended that CMP474 proceed to a Workgroup Panel and agreed the Terms of Reference for the Workgroup. 05/05/2026 On 27 April the Authority approved urgency, the first Workgroup took place on 30 April. | Urgent | Centrica | 2026-04-14 | High impact​ on Suppliers and a ​High impact​ on Transmission System Operators | Standard Governance (Workgroup)- Urgent | None | No | 7 | TBC | TBC | TBC | TBC | 2026-06-16 | 23/06/2026 - 29/06/2026 | TBC | TBC | 2026-07-10 | 2026-07-10 | EDD 17/07/2026 | 5 BD following Authority Decision | 2026-05-05
CMP475 | Amendment to BSUoS Tariff reset process | Amendment to the BSUoS Tariff Reset process as per CUSC. To enable NESO due to wider market conditions to reforecast the Fixed tariff Periods and if needed recover financial position of the Working Capital Fund | Workgroup Stage | Proposal raised on 15 April requesting urgency. A Special CUSC Panel was held on 21 April 2026 to discuss governance route. The Panel unanimously agreed that CMP475 met the Authority’s Urgency criteria (a) and therefore recommended urgent treatment. Panel’s recommendation was sent on 21 April 2026 seeking an Authority decision by 5pm on 27 April 2026. The Panel recommended that CMP475 proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. 05/05/2026 On 27 April the Authority approved urgency, the first Workgroup took place on 30 April. | Urgent | NESO | 2026-04-15 | High impact​ on anyone who is impacted by BSUoS, primarily Suppliers | Standard Governance (Workgroup)- Urgent | SQSS | No | 6 | TBC | TBC | TBC | TBC | TBC | 23/06/2026 - 29/06/2026 | TBC | TBC | 2026-07-10 | 2026-07-10 | EDD 17/07/2026 | 5 BD following Authority Decision | 2026-05-14
CMP476 | Correction to Section 15 of the CUSC | This modification corrects an unintended inconsistency in how the Global Asset Re-Use Factor is described in Section 15 of the CUSC compared how it is described in associated documents and applied in practice. | Proposal Raised | Proposal raised on 7 May requesting Self-Governance to proceed to Code Administrator Consultation and being presented to Panell on 22 May 2026. | TBC | NESO | 2026-05-07 | This modification is not expected to have a material impact on any party. | Self Governance (straight to CAC) | None | No | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-05-14
CMP477 | Facilitating Cross‑TO Area Connection Modifications | This modification enables cross‑Transmission Owner area connection change requests. | Proposal Raised | Proposal raised 13 May 2026 requesting urgency and will be presented at Panel on 15 May. | Urgent | SSE | 2026-05-13 | This modification is expected to have a medium impact on Generators and demand customers, NESO, Transmission Owners including (CATOs) and consumers | Standard Governance (Workgroup)- Urgent | STC | No | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-05-14
2026-05-14
Click to open Ofgem Implementation Timetable
Click to view the CUSC