## Cover
Navigation
How to use this document
Key of Regions and Project Maturity Levels
Beyond 2030 - Electricity Transmission Update - Onshore
Baseline - Onshore
Baseline - Offshore
June 2026
Beyond 2030 - Electricity Transmission Update
Comprehensive list of Onshore and Offshore network

## How to use this document
How to use this document
This workbook provides a list of all works identified as part of the Beyond 2030 - Electricity Transmission Update.
The appendix can be navigated by clicking on the workbook tabs below.
The System-Wide view provides a comprehensive list of the onshore and offshore works that have been considered in this network planning process, including our recommendations where approprate. This sheet also shows the optimal delivery dates for these works where appropriate, and can be filtered as required.
The Key of Regions shows the outline boundaries of the regions of Great Britian used in this document.
Comprehensive list of onshore and offshore options that formed part of our baseline in our assessment and have not been reassessed.
The recommendations outlined this workbook reflect our current and best view, based on information available today. As the development of these projects progresses towards delivery, more details will emerge and variations to the designs or delivery considerations may occur due to supply chain, network access, or other constraints. Further development will also be undertaken by relevant bodies and alternative options considered as appropriate. Therefore, these recommended delivery dates may be subject to change in future.
Our recommendations for wider works are as follows:
“Proceed - Critical”: This option is critical to our future planning. The option should be delivered on its earliest-in-service-date
“Proceed – Maintain”: This option is important and recommended and should be delievered up to three years after its earliest-in-service date.
“Hold”: This option is important and recommended for the future and should be delivered more than three eyars after it's earliest-in-service-date.
“Stop”: This option is not currently recommended within the optimal path of any scenario; delivery should be stopped and not be continued.
“Do not start”: This option is not currently recommended within the optimal path of any scenario; delivery work should not begin.
Further information on our recommendations can be found in "Annex 5 - Options Assessment" of our tCSNP2 Refresh methodology (https://www.neso.energy/document/357916/download).
More information on specific reinforcements can be found in the Beyond 2030 - Electricity Transmission Update publication and technical report

## Key
Regional maps
Project maturity levels

## Beyond 2030 ET Update
Return to Main Menu | Beyond 2030 Electricity Transmission Update - New Infrastructure and Upgrades
This is a comprehensive list containing details of all the onshore options assessed in the Beyond 2030 - Electricity Transmission Update. For further details on these options, please refer to our main publication and technical report on our website (https://www.neso.energy/publications/beyond-2030)
Code | Short description | TO | Type of Work | New or Existing infrastructure | Reinforcement type | Deteministic Earliest Delivery Date (EISD) | Earliest Optimal Delivery Date | HT - Optimal Delivery Date | EE - Optimal Delivery Date | HE - Optimal Delivery Date | FB - Optimal Delivery Date | Recommendation | Needs case | Previous recommendation | Context | Maturity Level | Env. | Com. | Del. & Ope. | Publication regions | Regions
ATRE | Reconductor Alverdiscott to Taunton 1 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | 2032 | 2033 | 2032 | 2033 | 2034 | Proceed (Maintain) | This option provides capability uplift across the boundary SC1. It is optimal in each of the four pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Amber | Amber | Green | South West | South West
BFPC | Installation of Power Flow control devices on Bramley to Fleet 400kV double circuit | NGET | Wider | Existing network upgrade | Power flow control | 2034 | 2034 | 2036 | 2035 | 2034 | 2036 | Proceed (Maintain) | BFPC provides capability uplift across the boundaries SC1, SC1.5, SC2 and SC3. It is needed in all pathways. This option helps manage power flows across the South. It is needed on its earliest delivery date in one pathway. | Hold | BFPC was identified in a previous options assessment but not recommended in Beyond 2030. | 1 - Scoping | Red | Amber | Green | South East | South East
BHN1 | New 400kV double circuit from north west Scotland to central belt Scotland | SSENT, SPT | Wider | New onshore circuit | New onshore circuit | 2038 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North Scotland; Central and Southern Scotland | Scotland
BHSC | Installation of Power Flow control devices on the Yorkshire to East Midland new 400kV circuit | NGET | Wider | Existing network upgrade | Power flow control | 2034 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | East Midlands
BQNC | New 400kV circuit between West Midlands and South East England | NGET | Wider | New onshore circuit | New onshore circuit | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | West Midlands
BRQB | Installation of Power Flow control devices on new 400kV circuit across East Midlands | NGET | Wider | New infrastructure | Power flow control | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | Proceed (Critical) | This option reinforces the boundaries B9 and LE1. BRQB is needed on its earliest delivery date in all four pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Amber | Green | MIdlands | East Midlands
BUUP | Burwell Main substation upgrade | NGET | Wider | Existing network upgrade | Substation upgrade | 2029 | 2031 | 2031 | 2031 | 2031 | 2031 | Proceed (Maintain) | BUUP uplifts the capability of the boundary LE1. BUUP is needed in all pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Green | Green | Central England and East of England | Central England
BWQB | Installation of Power Flow control devices onto Burwell to Walpole 400kV double circuit | NGET | Wider | New infrastructure | Power flow control | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | Proceed (Critical) | This option reinforces the boundaries B9 and LE1. It is needed in all pathways, maximising the capability of the existing network. This option is critical in all of the four pathways. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Amber | Green | Central England and East of England | Central England
CDRE | Reconductor Cellarhead to Drakelow 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2032 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | West Midlands
CETI | Circuit turn in and network reconfiguration within West Yorkshire area | NGET | Wider | Existing network upgrade | Substation upgrade | 2036 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
CLCU | Uprate cable section of Chilling to Lovedean 400kV circuit | NGET | Wider | Existing network upgrade | Substation upgrade | 2029 | 2031 | 2031 | 2031 | 2032 | 2033 | Proceed (Maintain) | CLCU reinforces the boundary SC1. It is optimal in all pathways. This option further utilises the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 2 - Strategic Optioneering | Green | Green | Green | South East | South East
CLN2 | New double circuit between North West England and Lancashire | NGET | Wider | New onshore circuit | New onshore circuit | 2040 | - | - | - | - | - | Alternative | CLN2/4 alternative options reinforce the boundaries B6 and B7a. They are only optimal in the Holistic Transition pathway, driven by renewable growth and significant north to south constraints. These are needed on their earliest delivery date but only one of CLN2 or CLN4 is required. Our analysis finds CLN4 more economic. The preferred option will be informed by further appraisal and consultation by National Grid Electricity Transmission. | Proceed (Critical) | CLN2 was recommended as part of Beyond 2030. It has since been further developed to confirm its scope, alongside potential alternatives. | 2 - Strategic Optioneering | Red | Red | Amber | North West | North West
CLN3 | New 400kV double circuit from North West England to Lancashire, following the coast, crossing Morecambe Bay | NGET | Wider | New onshore circuit | New onshore circuit | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 2 - Strategic Optioneering | Red | Red | Amber | North West | North West
CLN4 | New 400kV double circuit from North West England to Lancashire, following the coast | NGET | Wider | New onshore circuit | New onshore circuit | 2038 | 2038 | 2038 | - | - | - | Proceed (Critical) | CLN2/4 alternative options reinforce the boundaries B6 and B7a. They are only optimal in the Holistic Transition pathway, driven by renewable growth and significant north to south constraints. These are needed on their earliest delivery date but only one of CLN2 or CLN4 is required. Our analysis finds CLN4 more economic. The preferred option will be informed by further appraisal and consultation by National Grid Electricity Transmission. | Proceed (Critical) as CLN2 | N/A | 2 - Strategic Optioneering | Red | Red | Amber | North West | North West
CMCF | Reconductoring and reconfiguration of 400kV circuits bwtween Cellarhead, Dains and Macclesfield substations | NGET | Wider | Existing network upgrade | Reconductoring | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Green | Green | Midlands | North West
CMN3 | New double circuit from the South East of Scotland to the North West of England (Substation located South of Carlisle) | NGET, SPT | Wider | New onshore circuit | New onshore circuit | 2034 | - | - | - | - | - | Alternative | CMN3/CMN4, alternative options reinforce the boundaries B5, B6 and B7a as part of the onshore spine. CMN3/4 is optimal in all four pathways and is critical in one pathway. Whilst our analysis finds CMN4 more economic, only one of CMN3 or CMN4 is required. This will be decided by National Grid Electricity Transmission, following further appraisal and consultation. | Proceed (Maintain) | CMN3 was recommended through Beyond 2030. It has since been further developed to confirm its scope, alongside a potential alternative, and undergone consultation. | 3 - Design/development and consenting | Red | Red | Amber | Central and Southern Scotland | Scotland
CMN4 | New double circuit from the South East of Scotland to the North West of England (Substation located North of Carlisle) | NGET, SPT | Wider | New onshore circuit | New onshore circuit | 2034 | 2034 | 2035 | 2036 | 2034 | 2036 | Proceed (Maintain) | CMN3/CMN4, alternative options reinforce the boundaries B5, B6 and B7a as part of the onshore spine. CMN3/4 is optimal in all four pathways and is critical in one pathway. Whilst our analysis finds CMN4 more economic, only one of CMN3 or CMN4 is required. This will be decided by National Grid Electricity Transmission, following further appraisal and consultation. | Proceed (Maintain) as CMN3 | N/A | 3 - Design/development and consenting | Red | Red | Amber | Central and Southern Scotland | Scotland
CVUP | Clyde's Mill to Strathaven 400kV Reinforcement | SPT | Wider | Existing network upgrade | Uprating | 2032 | 2033 | 2035 | 2034 | 2033 | 2034 | Proceed (Maintain) | CVUP reinforces the boundaries B5 and B6. It is needed in all pathways. This option further utilises the capability of the existing network. | Hold | CVUP was previously recommended as part of Beyond 2030. | 2 - Strategic Optioneering | Green | Amber | Amber | Central and Southern Scotland | Scotland
CWSC | Installation of Power Flow control devices on Cottam to West Burton 400kV double circuit | NGET | Wider | Existing network upgrade | Power flow control | 2034 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Green | Green | Midlands | East Midlands
DBHW | Re-profile existing circuits between Dounreay, Loch Buidhe, and Beauly | SSENT | Wider | Existing network upgrade | Thermal upratiing | 2033 | - | - | - | - | - | Stop | N/A | New | N/A | 2 - Strategic Optioneering | Amber | Amber | Green | North Scotland | Scotland
DBRE | Re-conductor existing circuits between Dounreay, Loch Buidhe, and Beauly | SSENT | Wider | Existing network upgrade | Reconductoring | 2035 | 2041 | - | - | 2041 | 2041 | Hold | This option provides capability uplift across the boundary B0. DBRE is needed in two pathways, maximising the capability of the existing network. | New | This is a newly identified option by Scottish and Southern Electricity Networks Transmission. | 1 - Scoping | Red | Amber | Amber | North Scotland | Scotland
DCR4 | Reconductor Carrington to Daines 400kV single circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | Enabling only - no recommendation | N/A | 2 - Strategic Optioneering | Green | Green | Green | Midlands | North West
DTQB | Installation of Power Flow control devices along Drax to Thornton 400kV double circuit | NGET | Wider | New infrastructure | Power flow control | 2033 | - | - | - | - | - | Stop | N/A | New | N/A | 2 - Strategic Optioneering | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
EGL5 | New offshore HVDC link between North East Scotland and Lincolnshire | NGET, SSENT | Wider | New offshore circuit | New offshore circuit | 2035 | 2035 | 2035 | - | 2037 | 2036 | Proceed (Maintain) | EGL5 enables north to south transfers from Scotland through a new subsea cable. It is needed in three of the four pathways, reducing the need for additional onshore reinforcement. EGL5 is needed on its earliest delivery date in one pathway. | Previously recommended through coordinated offshore design as AC3 and AC4 | This option was previously established through the coordinated offshore design, as AC3 and AC4. | 3 - Design/development and consenting | Amber | Amber | Red | North Scotland | Scotland
EGL6 | New offshore HVDC link between North East Scotland and the South East of England | NGET, SSENT | Wider | New offshore circuit | New offshore circuit | 2041 | 2041 | - | - | 2041 | 2041 | Proceed (Maintain) | This option enables north to south power flows via a new offshore link. It is critical in two pathways. In the Falling Behind pathway, EGL6 is driven by interconnector exports across the south coast. | Previously recommended through coordinated offshore design as R-Link | This option was originally recommended through the coordinated offshore design, as R-link. | 1 - Scoping | Red | Amber | Red | North Scotland; South East | Scotland; South East
EGL8 | New offshore HVDC link between North East Scotland and North East England | NGET, SSENT | Wider | New offshore circuit | New offshore circuit | 2040 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North Scotland; North East and Yorkshire | Scotland; North East and Yorkshire
EGOS | Operational tripping scheme on the East Coast | NGET | Wider | Existing network upgrade | Operational option | 2032 | 2033 | 2033 | 2033 | 2033 | 2033 | Proceed (Maintain) | EGOS provides capability uplift across the boundaries B9 and LE1. It is optimal in all four pathways, maximising the capability of the existing network. This option helps ensure an operable, reliable network, managing power flows from two eastern offshore links. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Green | Amber | Central England and East of England | East
ESC3 | New 400kV substation and power flow control devices within West Yorkshire region | NGET | Wider | New infrastructure | New substation | 2033 | 2038 | 2038 | 2038 | 2039 | 2041 | Hold | This option provides capability uplift across the boundaries B7a and B8. ESC3 is needed in all four pathways, maximising the capability of the existing network. | Proceed (Critical) as ESCF | A similar option was originally recommended in Beyond 2030, as ESCF. | 2 - Strategic Optioneering | Green | Amber | Green | North East and Yorkshire | North East and Yorkshire
EWD1 | New East to West ultra high voltage direct current (UHVDC) network utilising AC routes within North England | NGET | Wider | New onshore circuit | UHVDC link | 2044 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | Midlands | North West
EWDC | New East to West ultra high voltage direct current (UHVDC) network within North England | NGET | Wider | New onshore circuit | UHVDC link | 2044 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North East and Yorkshire | North East and Yorkshire
FBN1 | New 400kV route between North East England and North Yorkshire with new substations at both end | NGET | Wider | New onshore circuit | New onshore circuit | 2041 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Amber | North East and Yorkshire | North East and Yorkshire
FBN2 | New 400kV route between North East England and North Yorkshire with new substations at Northeast England only | NGET | Wider | New onshore circuit | New onshore circuit | 2040 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Amber | North East and Yorkshire | North East and Yorkshire
FSRE | Reconductor Feckenham to Seven Springs 1 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | West Midlands
FSU1 | Harker to Stella West upgrade from 275kV to 400kV | NGET | Wider | New onshore circuit | New onshore circuit (Uprating) | 2035 | 2037 | 2038 | 2037 | 2038 | 2038 | Proceed (Maintain) | This option reinforces the boundaries B6 and B7a, removing and replacing the existing 275kV circuit. It is optimal in each of the four pathways. This option supports power flows from the Anglo-Scottish border towards other upgrades along the east coast. | Proceed (Critical) | FSU1 was previously recommended as part of Beyond 2030. | 2 - Strategic Optioneering | Red | Red | Amber | North West; North East and Yorkshire | North West; North East and Yorkshire
FWR1 | Reconductor Feckenham to Walham 1 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2032 | 2033 | - | 2033 | 2033 | - | Proceed (Maintain) | This option uplifts the capability of the boundaries B9 and SW1. It is optimal in two pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. A similar option, FWRE, was previously identified but not recommended in Beyond 2030. | 1 - Scoping | Amber | Amber | Green | MIdlands | West Midlands
GBNC | New 400kV circuit between Yorkshire and Humber region | NGET | Wider | New onshore circuit | New onshore circuit | 2041 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Green | North East and Yorkshire | North East and Yorkshire
HGNC | Harburn to Gala North 400kV Reinforcement | SPT | Wider | New onshore circuit | New onshore circuit | 2035 | 2035 | 2035 | 2036 | 2035 | 2036 | Proceed (Critical) | As part of the onshore spine from the north of Scotland to the north of England, HGNC reinforces the boundaries B5 and B6. HGNC is optimal in all four pathways and is critical in two pathways. | Proceed (Maintain) | This option was originally recommended in Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Amber | Central and Southern Scotland | Scotland
HNRE | Reconductor Hawthorn Pit to Norton 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2030 | - | - | - | - | - | Stop | N/A | Enabling only - no recommendation | N/A | 2 - Strategic Optioneering | Green | Amber | Green | North East and Yorkshire | North East and Yorkshire
HONC | New 400kV circuit between County Durham and North Yorkshire - Stage 2 | NGET | Wider | New onshore circuit | New onshore circuit | 2039 | - | - | - | - | - | Stop | N/A | Stop | N/A | 1 - Scoping | Red | Red | Amber | North East and Yorkshire | North East and Yorkshire
IMHW | Hotwire and substation cable uprate of Iron Acton to Melksham 275kV double circuit | NGET | Wider | Existing network upgrade | Thermal upratiing | 2033 | 2033 | 2039 | 2034 | 2033 | 2034 | Proceed (Critical) | This option reinforces the boundary SW1. It is needed in all pathways. This option further utilises the capability of the existing network in the South West. IMHW is critical in one pathway. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Green | Green | South West | South West
JTHW | Hotwire route between Thurcroft and West Melton | NGET | Wider | Existing network upgrade | Thermal upratiing | 2029 | 2033 | 2033 | 2033 | 2033 | 2033 | Hold | JTHW reinforces the boundary B8. It is needed in each of the four pathways. This option further utilises the capability of the existing network. | Proceed (Maintain) | This option was recommended in Beyond 2030. | 2 - Strategic Optioneering | Green | Green | Green | North East and Yorkshire | North East and Yorkshire
KENC | New 400kV circuit within North Yorkshire | NGET | Wider | New onshore circuit | New onshore circuit | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Green | North East and Yorkshire | North East and Yorkshire
LBNC | New 400kV circuit between East Midlands and East of England | NGET | Wider | New onshore circuit | New onshore circuit | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Amber | Midlands | East Midlands
LCU2 | Kincardine North - Harburn - Currie 400kV Reinforcement | SPT | Wider | Existing network upgrade | Uprating | 2035 | 2035 | 2035 | 2036 | 2035 | 2036 | Proceed (Critical) | This option uplifts the capability of the boundaries B5 and B6. It is optimal in each of the four pathways. This option further utilises the capability of the existing network. It is needed on its earliest delivery date in two pathways. | Hold | LCU2 was recommended in Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Amber | Central and Southern Scotland | Scotland
LFQB | New power flow control device in West Midlands | NGET | Wider | New infrastructure | Power flow control | 2036 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Maintain) | This option provides capability uplift across the boundaries B8, B9 and NW4. It is needed in all pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Amber | Amber | Green | Midlands | West Midlands
LGSC | Installation of Power Flow control devices across Northeast Lincolnshire network | NGET | Wider | Existing network upgrade | Power flow control | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Green | Amber | Amber | Midlands | East Midlands
LQUP | Upgrade of the exsiting Quad Boosters to higher ratings at Legacy 400kV substation | NGET | Wider | Existing network upgrade | Power flow control | 2036 | 2036 | 2038 | 2036 | 2038 | 2036 | Proceed (Critical) | This option reinforces the boundaries B8 and NW4. It is needed in all four pathways. This option further utilises the capability of the existing network. LQUP is critical in two of the four pathways. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Amber | Green | Wales | Wales
LRN7 | New 400kV double circuit from South Lincolnshire to East Leicestershire with two new substations. Reconductor one circuit of Cottam to Grendon 400kV route between new substation in East Leicestershire and Grendon substation | NGET | Wider | New onshore circuit | New onshore circuit | 2033 | 2036 | 2036 | 2036 | 2036 | 2036 | Proceed (Maintain) | This option provides capability uplift across the boundaries B9 and LE1. LRN7 is optimal in all pathways. It helps move power away from the east coast, where a significant amount of generation capacity is connected, relieving network bottlenecks in the region. | Proceed (Critical) as LRN6 | A similar option was previously recommended in Beyond 2030, as LRN6. Since then, further development has been carried out to refine its scope per LRN7. | 2 - Strategic Optioneering | Amber | Amber | Amber | Central England and East of England | East Midlands
LTR1 | Reconductor Lackenby to Thornton 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2034 | 2034 | 2038 | 2034 | 2034 | 2036 | Proceed (Critical) | LTR1 uplifts the capability of the boundary B7a. It is needed in each of the four pathways and is critical in two pathways. This option further utilises the capability of the existing network, reinforcing the network in combination with other options. | Proceed (Critical) as LTRE | This option was recommended as part of Beyond 2030, as LTRE. | 2 - Strategic Optioneering | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
LTRE | Reconductor and tower reinforcement on Lackenby to Thornton 400kV double circuit route | NGET | Wider | Existing network upgrade | Reconductoring | 2034 | - | - | - | - | - | Stop | N/A | Proceed (Critical) | N/A | 2 - Strategic Optioneering | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
LYN1 | New 400kV route between Lancaster and North Yorkshire | NGET | Wider | New onshore circuit | New onshore circuit | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Red | Amber | Midlands | North West
LYN2 | New 400kV route between Lancaster and North Yorkshire with new substations at North Yorkshire | NGET | Wider | New onshore circuit | New onshore circuit | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Red | Amber | Midlands | North West
MRU1 | Mersey Ring Upgrade Stage 1: 275kV to 400kV upgrade with new tower and bigger conductor for future network needs | NGET | Wider | Existing network upgrade | Uprating | 2037 | - | - | - | - | - | Stop | N/A | Hold | N/A | 2 - Strategic Optioneering | Amber | Amber | Amber | North West | North West
MRU2 | Mersey Ring Upgrade Stage 2: 275kV to 400kV upgrade retaining existing tower | NGET | Wider | Existing network upgrade | Uprating | 2039 | 2039 | 2039 | - | - | - | Proceed (Maintain) | This option reinforces the boundaries B6 and B7a. MRU2 is critical in the Holistic Transition pathway, increasing the capability of the existing network alongside other options in the north west of England. | Hold | This option was previously recommended through Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Amber | North West | North West
MRU3 | Mersey Ring Upgrade Stage 1: 275kV to 400kV upgrade retaining existing tower | NGET | Wider | Existing network upgrade | Uprating | 2036 | 2038 | 2038 | - | - | - | Proceed (Maintain) | This option reinforces the boundaries B6 and B7a. MRU3 is only optimal in the Holistic Transition pathway. It maximises the capability of the existing Mersey Ring, in combination with CLN2/4, MRU2 and NES1. Considering MRU3 is required for the delivery of MRU2, this option was provided a Proceed (Maintain) signal. | Hold as MRU1 | This option was previously recommended in Beyond 2030, as MRU1. | 2 - Strategic Optioneering | Amber | Amber | Amber | North West | North West
MSRE | Reconductoring Macclesfield to Stalybridge 400kV circuit route | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | North West
MWN1 | New 400kV circuit between West Midlands and South West England | NGET | Wider | New onshore circuit | New onshore circuit | 2037 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Maintain) | MWNC/1 alternative options reinforce the boundaries B8, B9 and NW4, in combination with UWNC. They are optimal in each of the four pathways. Only one of MWNC or MWN1 is needed, depending on potential customer connections in Wales. The preferred alternative will be decided through further industry engagement and analysis. | Proceed (Critical) as PSNC | These alternatives are developments of the southern section of PSNC, which was recommended in Beyond 2030. | 2 - Strategic Optioneering | Red | Red | Amber | Wales; Midlands | Wales; West Midlands
MWNC | New 400kV circuit between West Midlands and South West England via Mid Wales | NGET | Wider | New onshore circuit | New onshore circuit | 2038 | - | - | - | - | - | Alternative | MWNC/1 alternative options reinforce the boundaries B8, B9 and NW4, in combination with UWNC. They are optimal in each of the four pathways. Only one of MWNC or MWN1 is needed, depending on potential customer connections in Wales. The preferred alternative will be decided through further industry engagement and analysis. | Proceed (Critical) as PSNC | These alternatives are developments of the southern section of PSNC, which was recommended in Beyond 2030. | 2 - Strategic Optioneering | Red | Amber | Amber | Wales; Midlands | Wales; West Midlands
NBNC | New 400kV circuit within South Yorkshire | NGET | Wider | New onshore circuit | New onshore circuit | 2038 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
NES1 | Series compensation strategy 1 across the North of England transmission network | NGET | Wider | Existing network upgrade | Power flow control | 2034 | 2038 | 2038 | - | - | - | Hold | NES1 reinforces the boundary B6. It is only optimal in the Holistic Transition pathway. This option further utilises the capability of the existing network and provides benefit in combination with CLN2/4, MRU2 and MRU3. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Amber | Red | Amber | North West | North West
NES2 | Series compensation strategy 2 across the North of England transmission network | NGET | Wider | Existing network upgrade | Power flow control | 2034 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Red | Amber | North West | North West
NEUP | North East ring 275kV to 400kV upgrade | NGET | Wider | Existing network upgrade | Uprating | 2038 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Amber | North East and Yorkshire | North East and Yorkshire
NHDC | New ultra high voltage direct current (UHVDC) network between North East England and Hertfordshire | NGET | Wider | New onshore circuit | UHVDC link | 2043 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North East and Yorkshire | North East and Yorkshire
NHNC | Combination of new and replacement 400kV double circuit from North East Scotland to central belt Scotland | SSENT, SPT | Wider | New onshore circuit | New onshore circuit | 2038 | 2038 | 2038 | 2038 | - | 2038 | Proceed (Critical) | NHNC provides capability uplift across the boundaries B1a, B2, B4, B5 and B6. This is part of the onshore spine from the north of Scotland. NHNC is needed on its earliest delivery date in three pathways, moving the power generated from offshore wind in the north of Scotland further south. | Proceed (Critical) | This option was recommended in Beyond 2030. | 1 - Scoping | Red | Red | Red | North Scotland | Scotland
NLSC | Installation of Power Flow control devices on the North Wales to West Midlands new 400kV circuit | NGET | Wider | Existing network upgrade | Power flow control | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Green | Wales; Midlands | Wales; West Midlands
NOR6 | Reconductor and tower replacement on Norton to Osbaldwick 400kV double circuit route | NGET | Wider | Existing network upgrade | Reconductoring | 2035 | - | - | - | - | - | Stop | N/A | Proceed (Critical) | N/A | 1 - Scoping | Green | Amber | Green | North East and Yorkshire | North East and Yorkshire
NOR7 | Reconductor Norton to Osbaldwick 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | Proceed (Critical) | NOR7 reinforces the boundary B7a. It is optimal in each of the four pathways, maximising the capability of the existing network. NOR7 is critical in all four pathways and forms part of a combination of options upgrading the network along the east coast. | Proceed (Critical) as NOR6 | A similar option was originally recommended in Beyond 2030, as NOR6. | 1 - Scoping | Green | Amber | Green | North East and Yorkshire | North East and Yorkshire
NWD1 | New ultra high voltage direct current (UHVDC) network partly utilising AC route between North West England and Buckinghamshire | NGET | Wider | New onshore circuit | UHVDC link | 2041 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | Midlands | North West
NWDC | New ultra high voltage direct current (UHVDC) network between North West England and Buckinghamshire | NGET | Wider | New onshore circuit | UHVDC link | 2041 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | Midlands | North West
OENC | New 400kV double circuit within North Yorkshire | NGET | Wider | New onshore circuit | New onshore circuit | 2038 | - | - | - | - | - | Stop | N/A | Stop | N/A | 1 - Scoping | Amber | Amber | Amber | North East and Yorkshire | North East and Yorkshire
PCR2 | Reconductor and tower replacement on Carrington to Penwortham and Padiham to Penwortham 400kV circuits | NGET | Wider | Existing network upgrade | Reconductoring | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Green | Midlands | North West
RWUP | Uprate cable section of Ratcliffe On Soar to Willington East 2 400kV circuit | NGET | Wider | Existing network upgrade | Substation upgrade | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | Proceed (Critical) | RWUP uplifts the capability of the boundary B8. It is critical in all four pathways. This option further utilises the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Green | Green | Green | MIdlands | East Midlands
SCR1 | Reconductor Cottam to Staythorpe 1 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Green | Amber | Green | Midlands | East Midlands
SENS | New 400kV substation within South West region | NGET | Wider | New infrastructure | New substation | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Critical) | SENS provides capability uplift across the boundaries B8, B9 and SW1. It is needed on its earliest delivery date in all pathways, maximising the capability of the existing network. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Amber | Red | Green | South West | South West
SGRE | Reconductor Grendon to Sundon 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2030 | 2033 | 2033 | 2033 | 2033 | 2033 | Proceed (Maintain) | This option uplifts the capability of the boundaries B9 and LE1. SGRE is needed in all pathways, maximising the capability of the existing network and supporting the transmission of electricity south towards Greater London. | Proceed (Critical) | This option was originally recommended through Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Green | Central England and East of England | Central England
SHNC | New double circuit within West Midlands | NGET | Wider | New onshore circuit | New onshore circuit | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 2 - Strategic Optioneering | Amber | Red | Amber | Midlands | West Midlands
SMRE | Reconductor Minety to Severn Springs 1 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | South West | South West
SNRE | Reconductor Spennymoor to Norton 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | Proceed (Critical) | This option reinforces the boundaries B6 and B7a. SNRE is needed in all four pathways, maximising the capability of the existing network. This option is critical in one pathway. | Hold | This option was originally recommended in Beyond 2030, but a subsequent change control process found SNRE not to be optimal. | 1 - Scoping | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
SPRE | Reconductor Spennymoor to Stella West 400kV double circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | Proceed (Critical) | SPRE provides capability uplift across the boundaries B6 and B7a. It is optimal in all four pathways. This option further utilises the capability of the existing network. SPRE is critical in one of the four pathways and also forms part of the east coast upgrades. | Hold | SPRE was recommended in Beyond 2030, but a subsequent change control process found it was not optimal. | 1 - Scoping | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
SRRE | Reconductoring the Ratcliffe On Soar to Staythorpe 400kV circuit | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | East Midlands
STNS | New 400kV substation within East Midlands region | NGET | Wider | New infrastructure | New substation | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Midlands | East Midlands
TDP4 | Installation of Power Flow control devices along Drax to Thornton 400kV double circuit | NGET | Wider | Existing network upgrade | Power flow control | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | Proceed (Critical) | TDP4 reinforces the boundaries B7a and B8. It is optimal in all pathways. This option further utilises the capability of the existing network and is critical in all pathways. | Enabling only - no recommendation | TDP4 was recommended through Beyond 2030. | 1 - Scoping | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
TMC2 | Reconductor Thorpe Marsh leg of Drax to Keadby to Thorpe Marsh 400kV circuit and Keadby 400kV substation running arrangement update | NGET | Wider | Existing network upgrade | Reconductoring | 2031 | 2036 | 2038 | 2036 | 2038 | 2038 | Hold | TMC2 uplifts the capability of the boundaries B7a and B8. TMC2 is needed in all four pathways. This option further utilises the capability of the existing network. | Hold | TMC2 was previously recommended as part of Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
TMC3 | Reconductor and tower replacement on Thorpe Marsh leg of Drax to Keadby to Thorpe Marsh 400kV circuit and Keadby 400kV substation running arrangement update | NGET | Wider | Existing network upgrade | Reconductoring | 2035 | - | - | - | - | - | Stop | N/A | New | N/A | 2 - Strategic Optioneering | Amber | Amber | Green | North East and Yorkshire | North East and Yorkshire
TMCF | Thorpe Marsh substation reconfiguration | NGET | Wider | Existing network upgrade | Substation upgrade | 2035 | 2035 | 2038 | 2035 | 2038 | 2038 | Proceed (Critical) | TMCF provides capability uplift across the boundaries B7a and B8. TMCF is needed in each of the four pathways. This option is critical in one pathway. | Proceed (Maintain) | TMCF was recommended through Beyond 2030. | 2 - Strategic Optioneering | Amber | Green | Green | North East and Yorkshire | North East and Yorkshire
TMPC | Installation of Power Flow control devices along Thorpe Marsh to West Melton 1 275kV circuit​ | NGET | Wider | Existing network upgrade | Power flow control | 2031 | - | - | - | - | - | Stop | N/A | Proceed (Critical) | N/A | 2 - Strategic Optioneering | Green | Amber | Green | North East and Yorkshire | North East and Yorkshire
TWN1 | New Wymondley to Waltham Cross 400 kV double circuit and Waltham Cross to Warley 275 kV to 400 kV upgrades | NGET | Wider | New onshore circuit | New onshore circuit | 2036 | - | - | - | - | - | Alternative | TWNC/1 alternative options uplift the capability of the boundary LE1, supporting power flows into and around Greater London. They are optimal in three pathways. Whilst we find TWNC more economic, only one of TWNC or TWM1 is required. The preferred option will be decided through further development, considering potential resilience requirements and the need for a new substation at Waltham Cross. | Proceed (Maintain) as TWNC | This option was recommended as part of Beyond 2030. It has since been further developed to confirm its scope, with a potential alternative. | 1 - Scoping | Red | Red | Amber | Central England and East of England | Central England
TWNC | New Wymondley to Waltham Cross 400kV double circuit and Waltham Cross to Warley 275kV to 400kV upgrades | NGET | Wider | New onshore circuit | New onshore circuit | 2036 | 2038 | - | 2038 | 2038 | 2038 | Proceed (Maintain) | TWNC/1 alternative options uplift the capability of the boundary LE1, supporting power flows into and around Greater London. They are optimal in three pathways. Whilst we find TWNC more economic, only one of TWNC or TWM1 is required. The preferred option will be decided through further development, considering potential resilience requirements and the need for a new substation at Waltham Cross. | Proceed (Maintain) | This option was recommended as part of Beyond 2030. It has since been further developed to confirm its scope, with a potential alternative. | 2 - Strategic Optioneering | Red | Red | Amber | Central England and East of England | Central England
UWNC | New double circuit from North Wales to West Midlands | NGET | Wider | New onshore circuit | New onshore circuit | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Critical) | This option provides capability uplift across the boundaries B8 and NW4. It is needed on its earliest delivery date in all pathways. UWNC supports an offshore link from Scotland (WCD4) and enables power flows from the north of Wales to the West Midlands. | Proceed (Critical) as PSNC | Similarly, UWNC is an evolution of the northern section of PSNC, as recommended in Beyond 2030. | 2 - Strategic Optioneering | Red | Red | Amber | Wales; Midlands | Wales; West Midlands
WCD4 | New 2GW offshore HVDC link between Ayrshire and North Wales | NGET, SPT | Wider | New offshore circuit | New offshore circuit | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Critical) | This option reinforces the boundaries B6 and B7a, enabling north to south transfers via a new offshore link. WCD4 is optimal in all four pathways, combining with onshore reinforcement in Wales to move power further south. It is needed on its earliest delivery date in all pathways. | Proceed (Maintain) | This option was originally recommended in Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Red | Central and Southern Scotland | Scotland
WCD7 | New offshore HVDC link between Western Isles and North West England | NGET, SSENT | Wider | New offshore circuit | New offshore circuit | 2040 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North Scotland; North West | Scotland
WCD8 | New offshore HVDC link between Western Isles and North West England | NGET, SSENT | Wider | New offshore circuit | New offshore circuit | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North Scotland; North West | Scotland
WCN2 | New 400kV onshore reinforcement from Ayrshire to North West of England | NGET, SPT | Wider | New onshore circuit | New onshore circuit | 2036 | 2038 | - | - | 2038 | - | Proceed (Maintain) | This option reinforces the boundary B6 as well as local boundaries in the south west of Scotland designed to capture the impact of local power flows from demand and supply. It also facilitates potential customer connections in the south west of Scotland. WCN2 is optimal in the Hydrogen Evolution pathway. Considering its needs case in Beyond 2030 and potential to facilitate customer connections, WCN2 was provided a Proceed (Maintain) signal. | Proceed (Critical) | WCN2 was recommended in Beyond 2030. | 2 - Strategic Optioneering | Amber | Amber | Amber | Central and Southern Scotland; North West | Scotland; North West
WENC | Combination of new and replacement 400kV double circuit from north west Scotland to central belt Scotland via north east Scotland | SSENT, SPT | Wider | New onshore circuit | New onshore circuit | 2040 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Red | Red | North Scotland; Central and Southern Scotland | Scotland
WKDC | New offshore HVDC link between Yorkshire and South East of England | NGET | Wider | New offshore circuit | New offshore circuit | 2040 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Red | Amber | Red | Midlands | East Midlands
WLU1 | West London network upgrade and reconfiguration strategy 1 | NGET | Wider | New infrastructure | Uprating | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Amber | Central England and East of England | Greater London
WLU2 | West London network upgrade and reconfiguration strategy 2 | NGET | Wider | New onshore circuit | New onshore circuit (Uprating) | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Green | Central England and East of England | Greater London
WMU1 | West Midlands network upgrade and reconfiguration strategy 1 | NGET | Wider | Existing network upgrade | Uprating | 2039 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Amber | Midlands | West Midlands
WMU2 | West Midlands network upgrade and reconfiguration strategy 2 | NGET | Wider | Existing network upgrade | Uprating | 2035 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Amber | Midlands | West Midlands
WMU3 | New 400kV substation within West Midlands region and associated circuit reconfigurations | NGET | Wider | New onshore circuit | New onshore circuit (Uprating) | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | Proceed (Critical) | This option uplifts the capability of the boundaries B8, B9 and LE1. WMU3 is critical in all four pathways, maximising the capability of the existing network and involving a section of new circuit, which helps transfer power south to Greater London. | New | This is a newly identified option by National Grid Electricity Transmission, following Beyond 2030. | 1 - Scoping | Amber | Amber | Amber | Midlands | East Midlands
WYU1 | West Yorkshire network upgrade and reconfiguration strategy 1 | NGET | Wider | Existing network upgrade | Uprating | 2038 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Red | North East and Yorkshire | North East and Yorkshire
WYU2 | West Yorkshire network upgrade and reconfiguration strategy 2 | NGET | Wider | Existing network upgrade | Uprating | 2037 | - | - | - | - | - | Stop | N/A | New | N/A | 1 - Scoping | Amber | Amber | Amber | North East and Yorkshire | North East and Yorkshire

## Baseline - Onshore
Return to Main Menu | Beyond 2030 - Electricity Transmission Update - Onshore baseline
This is a list of all onshore options that formed part of the baseline for our assessment up to 2030. These options have not been reassessed. For the latest information on these options please contact the relevant TO. For all the offshore works contained in the offshore coordinated design please refer to the offshore tab. For further information on these options please visit our Pathway to 2030, Beyond 2030 and Clean Power 2030 webpages on our website. For more information on funding decisions please visit Ofgem's website: Accelerated Strategic Transmission Investment (ASTI) (https://www.ofgem.gov.uk/decision/decision-accelerating-onshore-electricity-transmission-investment) and tCSNP2 (https://www.ofgem.gov.uk/decision/funding-and-approval-framework-onshore-transitional-centralised-strategic-network-plan-2-projects-decision)
Code | Short description | TO | Type of Work | Reinforcement type | Earliest in Service Date (EISD)22 | Project maturity level | Last updated EISD and Maturity Level | Reason for baseline/Notes | Regions
AENC | New circuit in north East Anglia | NGET | Enabling work, Wider work | New onshore circuit | 2031 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England
ATNC | New circuit in south East Anglia | NGET | Enabling work, Wider work | New onshore circuit | 2031 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England
BBNC | New circuit between Beauly and Coachford (Blackhillock 2) | SHET | Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
BDUP | Upgrade the existing network to a higher voltage between Beauly and Denny | SPT;SHET | Enabling work, Wider work | Existing network upgrade | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
BFRE | Replace the conductors on the existing circuit between Bramley and Fleet with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2025 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | South West
BIDC | New offshore circuit between the Western Isles and Beauly | SHET | Enabling work | New offshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
BKUP | Upgrade the existing network to a higher voltage between Blackhillock and Kintore | SHET | Wider work | Existing network upgrade | 2034 | 3 - Design/development and consenting | 2026-06-01 | Delivery track status | North of Scotland
BLN4 | New circuit between Carnaig (Loch Buidhe) and Beauly | SHET | Enabling work, Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
BMM2 | Install new MSCs at Burwell Main | NGET | Wider work | Existing network upgrade | 2030 | 6 - Construction | 2024-09-01 | Required for CP30 | Central and East of England
BPNC | New circuit between Coachford (Blackhillock 2) and Peterhead | SHET | Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
BPRE | Reconductor the newly formed second Bramford to Braintree to Rayleigh Main circuit | NGET | Wider work | Existing network upgrade | 2028 | 1 - Scoping | 2024-09-01 | Required for CP30 | Central and East of England
BRRE | Reconductor remainder of Bramford to Braintree to Rayleigh route | NGET | Wider work | Existing network upgrade | 2025 | 6 - Construction | 2024-09-01 | Required for CP30 | Central and East of England
BTNO | New circuit between Bramford and Twinstead | NGET | Enabling work, Wider work | New onshore circuit | 2029 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England
BWRE | Replace the conductors on the existing circuit between Barking and West Ham with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2028 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | Greater London
CDHW | Cellarhead to Drakelow circuits thermal uprating | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | West Midlands
CDP1 | Add power control devices to the existing circuit between Cellarhead and Drakelow | NGET | Wider work | Existing network upgrade | 2027 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | West Midlands
CDP2 | Increase rating of power control devices installed on the existing circuit between Cellarhead and Drakelow | NGET | Wider work | Existing network upgrade | 2027 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | West Midlands
CDP3 | Further increase rating of power control devices installed on the existing circuit between Cellarhead and Drakelow | NGET | Wider work | Existing network upgrade | 2027 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | West Midlands
CGNC | New circuit between Creyke Beck and High Marnham | NGET | Wider work | New onshore circuit | 2031 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England
CTRE | Reconductor remainder of Coryton South to Tilbury circuit | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | South East
DFRE | Replace the conductors on the existing circuit between Drax and Fenwick Tee with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2029 | 6 - Construction | 2024-09-01 | Required for CP30 | North East and Yorkshire
DLUP | Upgrade the existing network between Windyhill, Lambhill and Denny North, including increasing elements to a higher voltage | SPT | Wider work | Existing network upgrade | 2029 | 4 - Planning/consenting | 2026-06-01 | Required for CP30 | Central and Southern Scotland
DNEU | Denny North 400/275 kV second supergrid transformer | SPT | Wider work | Existing network upgrade | 2026 | 6 - Construction | 2026-06-01 | Required for CP30 | Central and Southern Scotland
DREU | Generator circuit breaker replacement to allow Thornton to run a two-way split | NGET | Wider work | Existing network upgrade | Built | Built | 2024-09-01 | Required for CP30 | North East and Yorkshire
DSUP | Establish further connection capacity between Dounreay, Banniskirk (Spittal), and Thurso | SHET | Enabling work | Existing network upgrade | 2034 | 1 - Scoping | 2026-06-01 | Delivery track status | North of Scotland
DWNO | Upgrade existing circuits and establish a new route between Bonnybridge and Glenmavis | SPT | Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | Central and Southern Scotland
DWUP | Upgrade the circuit between Kincardine to Wishaw, including increasing elements to a higher voltage | SPT | Wider work | Existing network upgrade | 2029 | 4 - Planning/consenting | 2026-06-01 | Required for CP30 | North East and Yorkshire; Central and Southern Scotland
E2DC | New offshore HVDC link between Torness and Hawthorn Pit (Eastern Green Link 1) | NGET;SPT | Enabling work, Wider work | New offshore circuit | 2030 | 6 - Construction | 2024-09-01 | ASTI funding | North East and Yorkshire; Central and Southern Scotland
E4D3 | New offshore HVDC link between Peterhead and Drax (Eastern Green Link 2) | NGET;SHET | Enabling work, Wider work | New offshore circuit | 2029 | 4 - Planning/consenting | 2024-09-01 | ASTI funding | Yorkshire and the Humber; North of Scotland
E4L5 | New offshore HVDC link between Peterhead and the East Coast of England (Eastern Green Link 3) | NGET;SHET | Wider work | New offshore circuit | 2033 | 4 - Planning/consenting | 2024-09-01 | ASTI funding | East Midlands; North of Scotland
EBRE | Replace the conductors on the existing circuit between Enderby and Patford Bridge and East Claydon with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2030 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | East Midlands
EDEU | Upgrade the existing network to a higher voltage between Brinsworth and Chesterfield and Chesterfield and High Marnham. Develop new High Marnham and Chesterfield high voltage substations | NGET | Enabling work, Wider work | Existing network upgrade | 2029 | 3 - Design/development and consenting | 2024-09-01 | Required for CP30 | North East and Yorkshire; East Midlands
EDN2 | New circuit between Chesterfield and Ratcliffe-on-Soar | NGET | Wider work | New onshore circuit | 2031 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | East Midlands
EHRE | Replace the conductors on the existing circuit between Elvanfoot and Harker with higher capacity conductors | NGET;SPT | Wider work | Existing network upgrade | 2030 | 3 - Design/development and consenting | 2024-09-01 | Required for CP30 | North West; Central and Southern Scotland
ESC1 | New circuit between Elstree and St John’s Wood | NGET | Wider work | New onshore circuit | 2029 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | Greater London
ETRE | Upgrade the existing circuits between Eggborough and Thorpe Marsh to allow for more capacity | NGET | Enabling work | Existing network upgrade | 2029 | 1 - Scoping | 2024-09-01 | Required for CP30 | North East and Yorkshire
FHRE | Replace the conductors on the existing circuit between Feckenham and Hams Hall with higher capacity conductors | NGET | Enabling work | Existing network upgrade | TBC | 1 - Scoping | 2024-09-01 | Required for CP30 | West Midlands
FMR2 | Reconductor Feckenham to Minety 400kV Circuit | NGET | Enabling work | Existing network upgrade | 2029 | 1 - Scoping | 2024-09-01 | Required for CP30 | South West; West Midlands
GCHW | Carry out thermal upgrading on the existing circuit between Cottam and Market Harborough and Grendon | NGET | Wider work | Existing network upgrade | 2030 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | East Midlands
GWNC | New circuit between North Lincolnshire and South Lincolnshire border | NGET | Enabling work, Wider work | New onshore circuit | 2033 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England
HAE2 | Harker supergrid transformer 6 replacement | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | North West
HAEU | Harker supergrid transformer 5 and supergrid transformer 9A banking arrangement | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | North West
HBUP | Upgrade the existing network to a higher voltage at Bridgewater and replace the conductors on the existing circuit to Hinkley with higher capacity conductors | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | South West
HWUP | Upgrade the existing network to a higher voltage between Waltham Cross to Hackney | NGET | Wider work | Existing network upgrade | 2028 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central England and East of England
IFR1 | Replace the conductors on the existing circuit between Feckenham and Ironbridge with higher capacity conductors | NGET | Enabling work, Wider work | Existing network upgrade | 2028 | 1 - Scoping | 2024-09-01 | Required for CP30 | West Midlands
KCEU | Carry out thermal upgrading of the existing circuits between Creyke Beck, Keadby and Killingholme | NGET | Enabling work, Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | North East and Yorkshire
KCRE | Replace the conductors on the existing circuit between Cottam and Keadby with higher capacity conductors | NGET | Enabling work, Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | North East and Yorkshire
KKRE | Reconductor 30% of Kintore - Fetteresso - Alyth - Kincardine 400kV | SHET | Wider work | Existing network upgrade | 2033 | 6 - Construction | 2026-06-01 | Included in ECUP (RIIO T-2 Baseline) | Central and Southern Scotland
KWHW | Carry out thermal upgrading on the existing circuit between Keadby and West Burton | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | North East and Yorkshire; East Midlands
KWP2 | Increase rating of power control devices installed on the existing circuit between Keadby and West Burton | NGET | Enabling work, Wider work | Existing network upgrade | 2026 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | North East and Yorkshire
KWPC | Add power control devices to the existing circuit between Keadby and West Burton | NGET | Wider work | Existing network upgrade | 2026 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | North East and Yorkshire
LNRE | Replace the conductors on the existing circuit between Lackenby and Norton with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2030 | 1 - Scoping | 2024-09-01 | Required for CP30 | North East and Yorkshire
LPUP | Peterhead - Persley – Kintore - Kincardine 400kV Upgrade (was PPUP) | SHET | Wider work | Existing network upgrade | 2032 | 4 - Planning/consenting | 2026-06-01 | Delivery track status | North of Scotland
LWUP | Build a new substation north of Kincardine and connect this to Denny North | SPT | Wider work | Existing network upgrade | 2029 | 4 - Planning/consenting | 2026-06-01 | Required for CP30 | Central and Southern Scotland
MBRE | Replace the conductors on the existing circuit between Bramley and Melksham with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2025 | 6 - Construction | 2024-09-01 | Required for CP30 | South West
MRP2 | Additional power control devices at both Harker and Penwortham | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | Central and Southern Scotland
NBEU | Carry out thermal upgrading to Bramford and Norwich substations | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | Central and East of England
NBRE | Reconductor Bramford to Norwich double circuit | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | Central and East of England
NEMS | Install voltage support equipment within the North East region | NGET | Wider work | Existing network upgrade | 2030 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | North East and Yorkshire
NEP1 | Add power control devices to the existing circuits between Blyth and Tynemouth and Blyth and South Shields | NGET | Wider work | Existing network upgrade | 2027 | 6 - Construction | 2024-09-01 | Required for CP30 | North East and Yorkshire
NEPC | Power control device along Blyth to Tynemouth and Blyth to South Shields | NGET | Wider work | Existing network upgrade | 2027 | 6 - Construction | 2024-09-01 | Required for CP30 | North East and Yorkshire
NNNC | New circuit between New Deer and Greens | SHET | Enabling work | New onshore circuit | 2030 | 3 - Design/development and consenting | 2026-06-01 | Required for CP30 | North of Scotland
NOR4 | Reconductor a short span of the Norton-Osbaldwick 2 400 kV circuit | NGET | Wider work | Existing network upgrade | 2027 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 - This option will be further developed alongside NOR5 as an alternative to be superceded by NOR8 to meet requirements by 2030 | North East and Yorkshire
NOR5 | Reconductor a short span of the Norton-Osbaldwick 1 400 kV circuit | NGET | Wider work | Existing network upgrade | 2027 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 - This option will be further developed alongside NOR4 as an alternative to be superceded by NOR8 to meet requirements by 2030 | North East and Yorkshire
OPN2 | New circuit between Osbaldwick and Poppleton | NGET | Enabling work, Wider work | New onshore circuit | 2028 | 6 - Construction | 2024-09-01 | ASTI funding | North East and Yorkshire
PCR1 | Reconductoring of Carrington - Penwortham & Padiham - Penwortham 400kV circuits | NGET | Enabling work | Existing network upgrade | 2030 | 1 - Scoping | 2024-09-01 | Required for CP30 | North West
PEM1 | Install further voltage support equipment at Pelham | NGET | Wider work | Existing network upgrade | 2029 | 6 - Construction | 2024-09-01 | Required for CP30 | Central and East of England
PEM2 | Install voltage support equipment at Pelham | NGET | Wider work | Existing network upgrade | 2029 | 6 - Construction | 2024-09-01 | Required for CP30 | Central and East of England
PKUP | Upgrade and/or rebuild the circuits and equipment between Longside (Peterhead 2), Peterhead, Persley, Kintore, Fetteresso, Alyth, and Kincardine | SHET | Enabling work | Existing network upgrade | 2033 | 3 - Design/development and consenting | 2026-06-01 | Delivery track status | North of Scotland
PSDC | New offshore circuit between Banniskirk (Spittal) and Longside (Peterhead 2) | SHET | Enabling work, Wider work | New offshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | Required for CP30 | North of Scotland
PTC1 | Pentir to Trawsfynydd cable replacement | NGET | Enabling work, Wider work | New onshore circuit | 2029 | 4 - Planning/consenting | 2024-09-01 | ASTI funding | Wales
PTC2 | Pentir – Trawsfynydd 1 A220 circuit upgrades | NGET | Wider work | New onshore circuit | 2029 | 4 - Planning/consenting | 2024-09-01 | Recommended project alongside PTC1 (ASTI) | Wales
PTN2 | Further upgrades of new 400kV circuit within North Wales established under PTNO | NGET | Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2024-09-01 | Recommended project alongside PTNO (ASTI) | Wales
PTNO | A second transmission circuit on the existing Pentir to Trawsfynydd route | NGET | Enabling work, Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2024-09-01 | ASTI funding | Wales
PWMS | Install voltage support equipment at Penwortham | NGET | Wider work | Existing network upgrade | 2030 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | North West
RHM1 | Install voltage support equipment at Rye House | NGET | Wider work | Existing network upgrade | 2028 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | South East
RHM2 | Install further voltage support equipment at Rye House | NGET | Wider work | Existing network upgrade | 2028 | 2 - Strategic Optioneering | 2024-09-01 | Required for CP30 | South East
RTRE | Reconductor remainder of Rayleigh to Tilbury circuit | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 | South East
SCD1 | New offshore circuit between Suffolk and Kent | NGET | Enabling work, Wider work | New offshore circuit | 2031 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | Central and East of England; South East
SEEU | Reactive compensation protective switching scheme | NGET | Wider work | Existing network upgrade | 2025 | 6 - Construction | 2024-09-01 | Required for CP30 | South East
SER1 | Replace the conductors on the existing circuit between Elstree and Sundon with higher capacity conductors | NGET | Wider work | Existing network upgrade | Built | Built | 2026-06-01 | Required for CP30 - This option was superceded and delivered as SER3 | South East
SER2 | Replace the conductors on the existing circuit between Elstree and Sundon with higher capacity conductors and connect into the Elstree Substation | NGET | Wider work | Existing network upgrade | 2029 | 3 - Design/development and consenting | 2024-09-01 | Required for CP2030 - This option will be further developed as an alternative option SER4 | South East
SHETLAND | HNDFUE AC project: Shetland to Blackhillok | SHET | Wider work | New offshore circuit | 2035 | 3 - Design/development and consenting | 2026-06-01 | Delivery track status | North of Scotland
SHNS | New substation in the South Humber area | NGET | Wider work | New infrastructure | 2033 | 3 - Design/development and consenting | 2024-09-01 | SHNS is an enabling work for the ASTI schemes E4L5 & GWNC, these schemes must follow SHNS | Central and East of England
SLU4 | New circuit between Banniskirk (Spittal) and Carnaig (Loch Buidhe) | SHET | Enabling work, Wider work | New onshore circuit | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | North of Scotland
TGDC | New offshore HVDC link between East Scotland and the East of England (Eastern Green Link 4) | NGET;SPT | Wider work | New offshore circuit | 2034 | 4 - Planning/consenting | 2024-09-01 | ASTI funding | East Midlands; Central and Southern Scotland
TKRE | Carry out thermal upgrading on the existing circuits between Tilbury to Grain and Tilbury to Kingsnorth | NGET | Wider work | Existing network upgrade | 2029 | 3 - Design/development and consenting | 2024-09-01 | ASTI funding | South East
TKUP | New circuit from Kintore to Emmock (Tealing) and upgrade elements of the existing Emmock to Westfield and Alyth to Emmock circuits | SPT;SHET | Wider work | Existing network upgrade | 2030 | 4 - Planning/consenting | 2026-06-01 | ASTI funding | Central and Southern Scotland; North of Scotland
VERE | Replace the conductors on the existing circuit between Strathaven and Elvanfoot with higher capacity conductors | SPT | Wider work | Existing network upgrade | 2030 | 5 - Consents approved | 2026-06-01 | Required for CP30 | Central and Southern Scotland
VSRE | Replace the conductors on the existing circuit between Strathaven and Smeaton with higher capacity conductors | SPT | Wider work | Existing network upgrade | 2027 | 6 - Construction | 2026-06-01 | Required for CP30 | Central and Southern Scotland
WRRE | Replace the conductors on the existing circuit between West Burton and Ratcliffe-on-Soar with higher capacity conductors | NGET | Wider work | Existing network upgrade | 2029 | 3 - Design/development and consenting | 2024-09-01 | Required for CP30 | East Midlands
WSEU | Thermal upgrade for Sundon and Wymondley 400 kV substation | NGET | Wider work | Existing network upgrade | 2025 | 6 - Construction | 2024-09-01 | Required for CP30 | South East
WYTI | Connect the existing circuit between Pelham and Sundon that passes Wymondley substation into the substation | NGET | Wider work | Existing network upgrade | 2028 | 3 - Design/development and consenting | 2024-09-01 | Required for CP30 | South East

## Baseline - Offshore
Beyond 2030 - Electricity Transmission Update - Offshore baseline
This is a list of all offshore options that formed part of the baseline for our assessment in the Beyond 2030 - Electricity Transmission Update. For all the onshore options please refer to the onshore tab. For more information on the Hollistic Network Design and latest updates visit our website: https://www.neso.energy/publications/beyond-2030/holistic-network-design-offshore-wind
HND | Interface point 1 | Interface point 2 | Type of Work | Reinforcement type | Earliest in Service Date (EISD) | Technology type | Capacity | Number of cables | Regions
Celtic Sea | FW1 | Camarthenshire | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | South West England
Celtic Sea | FW2 | Baglan Bay | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1500 | 2 | South West England
Celtic Sea | FW3 | Pyworthy | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | South West England
HND | SW_E1a_1 | Hawthorn Pit | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1500 | 2 | North East Scotland/England & South East England
HND | SW_NE7_1 | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1500 | 2 | North East Scotland
HND | PA_2 | Blyth | Offshore - Onshore | New offshore circuit | N/A | HVDC 525 kV XLPE pair with metallic return | 1800 | 2 | North East Scotland/England
HND | SW_NE4_1 | New Deer | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | North East Scotland
HND | R4_3 | Weston Marsh | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | South East England
HND | SW_N1 | Spittal | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 2250 | 5 | North West Scotland
HND | SW_N4 | Arnish | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 740 | 2 | North West Scotland
HND | Tee1 | Hunterston | Offshore - Onshore | New offshore circuit | N/A | HVDC 525 kV XLPE pair with metallic return | 2000 | 2 | North West
HND | Tee1 | Pentir-South | Offshore - Onshore | New offshore circuit | N/A | HVDC 525 kV XLPE pair with metallic return | 2000 | 2 | North West
HND | R4_4 | Bodelwyddan | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | North West
HND | R4_5 | Penwortham | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 480 | 1 | North West
HND | R4_6 | Penwortham | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | North West
HND | R4_1 | Creyke Beck | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1440 | 1 | North East England
HND | R4_2 | Creyke Beck | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1440 | 1 | North East England
HND | PA_1 | Creyke Beck | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1440 | 1 | North East England
HND | SW_W1 | Tee1 | Offshore - Onshore | New offshore circuit | N/A | HVDC 525 kV XLPE pair with metallic return | 2000 | 2 | North West
HND | SW_E1b | Fiddes | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1200 | 2 | North East Scotland
HNDFUE | SW_N3 | Arnish | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 500 | 1 | North West Scotland
HNDFUE | SW_N2 | Dounreay | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1500 | 3 | North West Scotland
HNDFUE | SW_NE2 | Spittal | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1050 | 3 | North East Scotland
HNDFUE | SW_NE3 | New Deer 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1000 | 2 | North East Scotland
HNDFUE | SW_NE4_2 | New Deer 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 550 | 2 | North East Scotland
HNDFUE | SW_NE6 | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1000 | 2 | North East Scotland
HNDFUE | SW_NE8 | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1000 | 2 | North East Scotland
HNDFUE | SW_NE7_2 | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | HVDC 525kV Bipole | 1500 | 2 | North East Scotland
HNDFUE | SW_E2b | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1000 | 2 | North East Scotland
HNDFUE | SW_E3 | Fiddes | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1050 | 3 | North East Scotland
HNDFUE | SW_E1a_2 | Branxton | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1500 | 2 | North East Scotland/England
HNDFUE | SW_E1c_1 | Brechin | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 800 | 2 | North East Scotland/East Scotland
HNDFUE | SW_NE1a | Shetland | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 500 | 2 | North East Scotland
HNDFUE | SW_NE1b | Shetland | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 1800 | 4 | North East Scotland
HNDFUE | SW_E1c_2 | Weston Marsh | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1400 | 2 | North East Scotland/England & South East England
HNDFUE | SW_E1c_3 | Weston Marsh | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1400 | 2 | North East Scotland/England & South East England
INTOG | Scaraben | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | AC 275kV cable | 200 | 1 | North East Scotland
INTOG | Aspen | Fetteresso | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1500 | 2 | North East Scotland
INTOG | Cenos | Peterhead 2 | Offshore - Onshore | New offshore circuit | N/A | HVDC 320kV Monopole | 1400 | 2 | North East Scotland
INTOG | Cedar | Branxton | Offshore - Onshore | New offshore circuit | N/A | HVDC 525 kV XLPE pair with metallic return | 2000 | 2 | North East Scotland
INTOG | Sinclar | Scaraben | Offshore - Offshore | New offshore circuit | N/A | AC 275kV cable | 100 | 1 | North East Scotland
INTOG | Aspen | Beech | Offshore - Offshore | New offshore circuit | N/A | AC 275kV cable | 500 | 2 | North East Scotland
INTOG | Beech | Cedar | Offshore - Offshore | New offshore circuit | N/A | AC 275kV cable | 500 | 2 | North East Scotland
INTOG | Cedar | Aspen | Offshore - Offshore | New offshore circuit | N/A | AC 275kV cable | 1000 | 2 | North East Scotland