CUSC SECTION 16

QUEUE MANAGEMENT PROCESS

Introduction

16.1		The process set out in this Section 16 will be applied by The Company in measuring the progression of a User’s project (excluding any OTSDUW, except with respect to Milestone 8, Project Construction, where any OTSDUW Build or OTSDUW Staged Build shall be included) against the Completion Date, or where the User’s Project is staged, the relevant Completion Date in the Construction Agreement related to that project. The process identifies a set of milestones as set out below against which progress is measured and if not achieved provides for the termination of the Construction Agreement. Although provision for this process is included within Gate 1 Agreements the process and provisions within this Section will only be actively applied in Gate 2 Agreements.

16.2	The Queue Management Process will not be applied and included in (i) Construction Agreements with an Embedded Power Station relating to a Bilateral Embedded Generation Agreement or (ii) Construction Agreements with the owner/operator of a Distribution System directly connected to the National Electricity Transmission System where the Construction Agreement is required because of a connection to that Distribution System and the Distribution Queue Management Process applies.

16.3	The User Progression Milestones and Evidence

The milestone events/timings against which the progress of a User’s project will be measured by The Company are listed in the table below.

The table also shows the evidence a User has to provide to The Company to show that a milestone event has been met.

A User Progression Milestone must be achieved by the date which represents the end of the milestone period identified for that milestone. Once achieved a Conditional Progression Milestone must also continue to be met on an ongoing basis, that is, the statutory consent and planning permission initiated and secured and the land rights achieved to demonstrate compliance with the Conditional Progression Milestone must remain in place.

The Company will provide (in the form of Appendix Q) a Table based on the above with each Construction Agreement. This will specify the dates of the milestone periods for the User’s project derived in accordance with this Section 16 and set out in each Appendix Q.

Where a User’s project is being delivered in discrete “stages” of Equipment, or programme for example when the project relates to the installation of different technology types or co-located sites, and they are being progressed discretely a separate Appendix Q will be provided for each “stage” and the Queue Management Process applied to each “stage” separately

| Milestone | Detail | Evidence | Milestone Period |
| --- | --- | --- | --- |
| Milestone 1) Initiated Statutory Consents and Planning Permission | Where statutory consents are required for the construction of the User’s project, the User must begin the process of seeking statutory consents, including Planning Permission for the project within the timescales and be able to provide the required evidence. | Submission of planning application to the relevant Statutory Authority or, if the User’s project does not require a statutory consent, a declaration from the User to that effect. | See table (varies with lead time). |
| Milestone 2) Secured Statutory Consents and Planning Permission | Where required for the construction of the User’s project, the User must have secured statutory consents, including Planning Permission for the project within the timescales and be able to provide the required evidence | The planning decision notice confirms planning permission has been granted and that this permission allows the User to meet the terms included in its Construction Agreement. Compliance with this milestone is ongoing. | See table (varies with lead time) |
| Milestone 3) Secure Land Rights | The User must have secured the required land rights to enable the construction of the project. The User may be the owner/occupier of the land or has the necessary agreement from the owner/occupier. | The User shall provide documentation to demonstrate that: (i) The User is an owner or tenant of the land on which the proposed site is or will be situated; or (ii) The User has entered into an agreement to lease (which meets the requirements in the Gate 2 Criteria Methodology) the land from the owner of the land on which the proposed site is or will be situated; or (iii) The User has an option to purchase or to lease the land from the owner of the land on which the proposed site is or will be situated and this option meets the requirements and parameters set out in the Gate 2 Criteria Methodology; or (iv) For an Offshore Project, which depending on the type of Offshore Projects (and set out in the LoA Guidance) the land rights are provided by reference to the seabed or Onshore Connection Site (a) the User has entered into an agreement for occupation or use of the seabed upon which the User's project (excluding any OTSDUW) is or will be located or (b) the requirements at (ii) and (iii) above apply. Nb the obligation is to secure and evidence the land right for the site of the installation e.g. Power Station or demand site so the evidence does not relate to rights e.g. easements associated with that site or OTSDUW. Compliance with this milestone is ongoing and additionally measured against the requirements regarding the Original Red Line Boundary as set out in Paragraph 16.4.9.3 below. | See table |
| Milestone 4) N/A for Transmission | This milestone does not apply for Transmission | Null | Null |
| Milestone 5) Contestable Design Works Submission | This milestone will apply where a User has gone down the contestable route for connection. | Written confirmation from the Relevant Transmission Licensee that design obligations as bilaterally agreed in a User-Self Build agreement have been received. | See table (varies with lead time) |
| Milestone 6) Agree Construction Plan | The User must have agreed a construction plan for the detailed User’s Works with The Company which demonstrates how they will be progressing the User’s Works to achieve the Completion Date. | The User’s construction plan shall demonstrate how the User will be ready for the Commissioning Programme Commencement Date and Completion Date. This must include a detailed programme for the User’s Works with a fixed start and end date as agreed with the Relevant Transmission Licensee, and be a programme aligned with the Commissioning Programme Commencement Date and Completion Date. | See table (varies with lead time) |
| Milestone 7) Project Commitment | This milestone demonstrates that the project has the necessary commitment or backing for it to proceed. | One of the following: • Binding contract issued by the User for main plant equipment; or • Capital contribution payments made to The Company in advance of connection; or • A decision paper from a formal, minuted meeting of the User’s board of directors evidencing Final Investment Decision (FID); or • award of a governmental or regulatory subsidy which provides financial support or incentive to the User’s project. | See table (varies with lead time) |
| Milestone 8) Project Construction | Project construction including OTSDUW Build or OTSDUW Staged Build, is the project phase ie the period from when a User begins the site works to carry out construction of its project until completion of the User’s Works | Commence construction according to the construction plan agreed under Milestone 6. Evidence for meeting this milestone will be a letter from the User’s board of directors or equivalent to state construction has commenced. | See table (varies with lead time) |

## The date by which a User Progression Milestone has to be achieved is derived from the following Tables working (except in the case of Conditional Progression Milestone M1) backwards from the Completion Date (or where staged, relevant Completion Date) in a Connection Offer to the date on which the Connection Offer is made by The Company to the User. The date by which Conditional Progression Milestone M1 has to be achieved is derived from the following Table based on the earlier of two dates as set out in that Table.

The User Progression Milestones are categorised as Conditional Progression Milestones and Construction Progression Milestones. Different rights and obligations on The Company to terminate the User’s Construction Agreement apply for each of these categories.

As noted above compliance with the Conditional Progression Milestones is measured on an ongoing basis.

Conditional Progression Milestones

| Retained Distribution Milestone Names for consistency | From 0 up to 2 years (0 – 729 days) from contracted Completion date | 2 up to 3 years (730 – 1094 days) from contracted Completion date | 3 up to 4 years (1095 to 1459 days) from contracted Completion date | 4 up to 5 years (1460 – 1824 days) from contracted Completion date | 5 years (1825 days) and above from contracted Completion date |
| --- | --- | --- | --- | --- | --- |
| Milestones: | All durations for milestones other than M1 are calculated back from the contracted Completion Date Durations for M1 (unless M1 has already been met at the time of the Gate 2 Application) will be the earlier of (a) the date calculated forwards from the Gate 2 Offer date (based on an agreed standard time period for each planning type as referred to below) to move from M3 to M1) and (b) the date calculated back from the contracted Completion Date |  |  |  |  |
| M1​ - Initiate Planning Consent | Bilaterally negotiated | 18 months | 24 months ​​ | 36 months ​ | 48 months |
| M2 - Secure Consent​ |  |  |  |  |  |
|  |  | 12 months ​ | 18 months ​ | 24 months ​ | 30 months |
| M3​ - Land Rights |  | 21 months | 27 months ​ | 39 months | 51 months |

The standard time period for each planning type to move from M3 to M1 is as follows:

| Planning / Technology Type | Timescale from Gate 2 Offer date to M1 |
| --- | --- |
| Town and Country Planning (England, Scotland and Wales) | 2 years |
| Section 36 (England/Scotland) | 3 years |
| Development of National Significance (Wales) | 3 years |
| NSIP / DCO (England and Wales) | 3 years |
| Offshore (including Offshore Wind, Interconnectors and OHAs) | 5 years |
| Nuclear | Case by Case |
| Novel technologies | Case by Case |

Construction Progression Milestones

| Retained Distribution Milestone Names for consistency | From 0 up to 2 years (0 – 729 days) from contracted Completion date | 2 up to 3 years (730 – 1094 days) from contracted Completion date | 3 up to 4 years (1095 to 1459 days) from contracted Completion date | 4 up to 5 years (1460 – 1824 days) from contracted Completion date | 5 years (1825 days) and above from contracted Completion date |
| --- | --- | --- | --- | --- | --- |
| Milestones: | All durations referenced back from contracted Completion Date |  |  |  |  |
| M5 - Contestable Design Works Submission | Bilaterally negotiated | 12 months ​ | 15 months ​ | 18 months ​ | 21 months |
| M6 - Agree Construction Plan |  | 9 months | 12 months | 15 months ​ | 18 months |
| M7 - Project Commitment |  | 6 months | 9 months ​ | 12 months ​ | 15 months |
| M8 - Initiate Construction |  | 3 months ​ | 6 months ​ | 9 months ​ | 12 months |

Where durations are referred to as being “bilaterally negotiated” this means that The Company, the Relevant Transmission Licensee and the User will aim to agree the durations for the 	purposes of Appendix Q during the Offer preparation period. Where not so agreed by the time the Offer is made, Appendix Q will reflect the durations proposed by The Company and Relevant Transmission Licensee and discussions will continue with a view to agreeing these during the Offer acceptance period.

16.4 		Project Milestone Communications

16.4.1	As soon as practicable and in any event by the due date for meeting a User Progression Milestone, the User shall document and provide the evidence in accordance with the table above of progress on a User Progression Milestone to prove to The Company’s reasonable satisfaction that that User Progression Milestone has been met.

16.4.2	The User will notify The Company and the Relevant Transmission Licensee, at the earliest opportunity, as soon as it becomes aware of any issues that could impact on the User’s ability to meet any of the User Progression Milestones and specifically of any that the User believes could fall under 16.5 below. Where the User believes that an issue could fall under 16.5 below evidence supporting this shall be provided to The Company.

16.4.3		The Company will upon receipt of evidence provided in accordance with 16.4.1 above, advise the User within 10 Business Days as to whether it is satisfied that the User Progression Milestone has been met and whether the status of the User’s project is categorised by The Company as “On Track” or “Termination”.

16.4.4	If no evidence is provided in accordance with 16.4.1 above, or the evidence provided is considered insufficient to demonstrate that the milestone has been met, and as a consequence the status of the User’s project is categorised as “Termination” The Company will notify the User that the User’s project is categorised as “Termination” and that the Project Milestone Remedy Period has started.

16.4.5	If during the Project Milestone Remedy Period the User’s project progresses such that it achieves the User Progression Milestone against which it was categorised as “Termination”, the User’s project shall be re-categorised by The Company as being “On Track” by reference to that User Progression Milestone and the User notified accordingly.

16.4.6	Where at the end of the Project Milestone Remedy Period for a Conditional Progression Milestone the status of the User’s project is still categorised as “Termination”, The Company shall terminate the Construction Agreement.  Where at the end of the Project Milestone Remedy Period for a Construction Progression Milestone the status of the User’s project is still categorised as “Termination”, The Company may terminate the Construction Agreement.

16.4.7	Whether or not any of the User Progression Milestones have been achieved and/or what constitutes progress towards achieving them is a matter for the sole discretion of The Company.

16.4.8	The Company, the Relevant Transmission Licensee and the User shall constructively engage as required during the Project Milestone Remedy Period to understand whether the relevant User Progression Milestone can or is likely to be met and whether the issues in achieving the User Progression Milestone fall or are likely to fall under 16.5 below.

16.4.9	Ongoing compliance with the Conditional Progression Milestones

16.4.9.1	Having achieved a Conditional Progression Milestone the User shall notify The Company (or respond to The Company’s request for confirmation on this point) at the earliest opportunity in the event that it no longer meets or has reason to believe it will not continue to meet the requirements set out for that Conditional Progression Milestone.

16.4.9.2	In the event that the ongoing requirements of a Conditional Progression Milestone are no longer met, The Company will notify the User that the User’s project is categorised as “Termination” and the provisions of 16.4.5 to 16.4.8 shall apply.

16.4.9.3 		Specific Provisions regarding Ongoing Compliance with the Original Red Line Boundary

16.4.9.3.1	The User shall be required to confirm at each User Progression Milestone that the  User’s project meets the minimum acreage requirements as set out in the LoA Guidance i.e. that the land is equal to or greater than that provided for the technologies included in the Gate 2 Application.

16.4.9.3.2 	The Original Red Line Boundary can only be changed as provided for in the Queue Management Guidance.

16.4.9.3.3		Subject to any changes in the Original Red Line Boundary provided for under the Queue Management Guidance, only 50% of whatever Installed Capacity is built within the Original Red Line Boundary can then be located outside of the Original Red Line Boundary.

16.4.9.3.4	A relaxation from the 50% requirement above is possible where this is justified and evidenced by the User in accordance with the Queue Management Guidance.

16.5	 Exceptional Issues on User Progression Milestones

There may be a small number of exceptional issues outwith the User’s control which may lead to User project delay and a User not being able to meet a User Progression Milestone.

The Exceptional issues which apply in the context of the Queue Management Process are as follows:

- Where the User is delayed in carrying out the User’s Works which entitles the User to fix a later date or dates under Clause 3.2 of the Construction Agreement (Delays and Force Majeure) and that delay is the reason that a User Progression Milestone is not met;

- Where the User is not able to meet a User Progression Milestone due to an event of Force Majeure;

- Where delays caused by a party (other than the User, The Company or a Relevant Transmission Licensee)  can be demonstrated to have an impact upon the User meeting a User Progression Milestone and the User could not have avoided these delays or their impact by the exercise of Good Industry Practice

- Where a User is not able to meet a User Progression Milestone due to Planning appeals and third-party challenges in relation to the User’s Consents;

- Any delay in the achievement of a milestone by the User which is caused by a Relevant Transmission Licensee or The Company

- Where a User can demonstrate that a forward looking M1 would have a detrimental impact on developing their User’s project provided that any adjustment cannot be later than the backwards looking M1.

Where the User believes an exceptional issue applies it shall provide written evidence to this effect supported by confirmation from the User’s board of directors or equivalent body for The Company’s consideration.

Where a User’s project is not able or is considered unlikely to meet a User Progression Milestone, as a result of an exceptional issue under the headings here, and providing the User notifies The Company and the Relevant Transmission Licensee of the delay and reasons for the delay at the earliest opportunity and provides reasonable evidence to justify this and satisfies The Company that the specific delay falls under this Paragraph 16.5, such delay will not result in the User’s project being categorised as “termination” in relation to the relevant User Progression Milestone or User Progression Milestones. In such circumstances The Company will consequently issue a new milestone date for the missed milestone.

Whether or not the exceptional issues as listed here apply and the period of any extension, is a matter for the sole discretion of The Company.

16.6	Implementation

16.6.1	The Queue Management Process will be:

(i) 	included in any Construction Agreements (other than those which 	fall within Paragraph 16.2 above) offered as part of any new Connection 	Offers; and

(ii)	introduced into any Construction Agreements (other than those which fall within Paragraph 16.2 above) which do not have the Queue Management Process already included within it) when a Modification Offer is made; and

(iii) 	introduced into any Existing CMP376 Construction Agreement which does not have the Queue Management Process already included within it through an Agreement to Vary that Existing CMP376 Construction Agreement in accordance with the process set out in Paragraph 16.6.3

in each case from the CMP376 Implementation Date.

16.6.2	Each User with an Existing CMP376 Construction Agreement shall be notified by The Company within:

- ten Business Days of the CMP376 Implementation Date for an Existing Construction Agreement of a type in Paragraph 16.6.6 (c)(i) below; and

- ten Business Days of the date of the Construction Agreement for an Existing Construction Agreement of a type in Paragraph 16.6.6 (c)(ii) below; and

- in accordance with Paragraph 16.6.4 for an Existing Construction Agreement of a type in Paragraph 16.6.6 (c)(iii)

and in each case such notice shall invite the User to make a Modification Application to incorporate the Queue Management Process into its Existing CMP 376 Construction Agreement.

16.6.3	Where a User with an Existing CMP376 Construction Agreement does not make a Modification Application within 6 months of being notified in accordance with Paragraph 16.6.2 or does not accept the Modification Offer made in response to the User’s Modification Application (and acknowledging that such offer may be disputed and referred to the Authority for determination) The Company shall issue the CMP376 Agreement to Vary to the User. The CMP376 Agreement to Vary shall be issued to the User as soon as practicable after the 6 months or failure to accept.

16.6.4 A User with a Construction Agreement (other than those which fall within Paragraph 16.2 above) where the Completion Date is on or before the date which is two years from the CMP376 Implementation Date will not have the Queue Management Process introduced into that Construction Agreement provided that the User’s project is progressing in accordance with and is reasonably aligned to the Construction Programme in that Construction Agreement. If The Company has reason to believe that that is not the case and the User has not been able to demonstrate that it is progressing  to The Company’s reasonable satisfaction The Company shall notify the User that the Construction Agreement is to be treated as an Existing CMP376 Construction Agreement and the provisions of Paragraph 16.6.3 shall apply but with the reference to “within 6 months of being notified in accordance with Paragraph 16.6.2” being replaced with “2 months after the issue of such notice”.

16.6.5	In the case of Modification Offers, the Queue Management Process will be applied and Appendix Q created by reference to the Completion Date in the Modification Offer and the date on which the Modification Offer is made by The Company to the User. In the case of the CMP376 Agreement to Vary, the Queue Management Process will be applied and Appendix Q created by reference to the Completion Date in the Existing CMP 376 Construction Agreement and the date on which the CMP 376 Agreement to Vary is offered by The Company to the User.

16.6.6	In this Paragraph 16.6:

- the term CMP376 Implementation Date shall mean the Implementation Date for CUSC Modification Proposal 376 (Inclusion of Queue Management Process within the CUSC); and

- the term CMP376 Agreement to Vary shall mean the Agreement to Vary issued by The Company to the User in accordance with Paragraph 16.16.3 above introducing the Queue Management Process and Appendix Q into an Existing CMP376 Construction Agreement; and

- the term Existing CMP376 Construction Agreement shall mean a Construction Agreement (other than those which fall within Paragraph 16.2 above) where the Works under that Construction Agreement are not completed at the CMP376 Implementation Date and:

- the Construction Agreement is dated on or before the CMP376 Implementation Date and the Completion Date is after the date which is two years from the CMP376 Implementation Date; or

- the Construction Agreement is the subject of an Offer made on or prior to the CMP376 Implementation Date, is dated after the CMP376 Implementation Date and the Completion Date is after the date which is two years from the CMP376 Implementation Date; or

- the Construction Agreement has a Completion Date which is on or before the date which is two years from the CMP376 Implementation Date and where The Company has issued a notice to the User under Paragraph 16.6.4 above.