## Sheet1
GC0079 Timeline
Task | Resource | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Comments
1.0 GC0079 Phase 1 [Future Connections]
1.1 Phase 1 Consultation | WG | [12 empty] | In progress
1.2 Consultation Reviews | WG
1.3 Report To the Authority | WG
2. 0 GC0079 Phase 2[Existing Installations]
2.1 Approve Draft TOR For Funding and Implementation Groups | WG | [12 empty] | These will be further developed by the task group
2.2 Specify protection change requirements | WG
2.3 CBA for retrospective application of LoM option | WG | [12 empty] | Remove VS and apply RoCoF at 1Hz/s with 500ms delay
2.4 Assessment Of small Scale inverter Operation | UoS | [12 empty] | Interim Results to be discussed with WG
2.5 Draft Consultation paper | WG | [12 empty] | To include amendment to legal text
2.6 Industry Consultation | WG
2.7 Report To the Authority | WG
3.0 Funding
3.1 Deliver report to ENFG outlining all the options considered and the recommended funding mechanism.[TGAD1 ] | Task Group A | [12 empty] | Detaimain how an appropriate funding mechanism can be put in place
3.2 Public Consultation [TGAD2] | Task Group A
3.3 Funding Implementation plan [TGAD3] | Task Group A
3.4 Detailed developments [TGAD4] | Task Group A
3.5 Funding deliver [TGAD5] | Task Group A
4.0 Implementation | [13 empty] | Determining how the programme should be discharged.
4.1 Spec contracted work | WG | [12 empty] | Write detailed technical specification for contractual work
4.2 Outline overall approach to ENFG [TGDB1] | Task Group B | [12 empty] | Develop contractual strategy (eg number of contractors, duration, incentives, assurance)
4.3 Develop detailed implementation plan [TGBD2]
4.4 Deliver