## Grid Code Prioritisation Rule
Section GR3.2 (b) Without prejudice, the Grid Code Review Panel shall endeavour at all times to operate. (i) in an efficent, economical and expeditious manner, taking account of the complexity, importance and urgency of particular Grid Code Modification Proposals. (ii) and with a view to ensuring that the Grid Code facilitiates achievement of the Grid Code Objectives.
Complexity | The defect addressed by the proposed has implications for many different areas of the energy system which need to be taken into consideration throughout the process. The technical complexity and cross code impact of the modification will most likely require significant use of industry time and a higher than average number of workgroups to conclude the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A proposed modification which requires speedy consideration within the code governance process, as well as the timescales for implementation within the respective code.
Modifications at Workgroup Stage |  |  |  | Modifications Post-Workgroup Stage
Mod Number | Previous Priority No: | Priority No | Title | Mod Number | Previous Priority No: | Title
GC0178 | 2 | 1 | Temporary Overvoltage - Specification of Limits and Clarification of Obligations | GC0139 | 1 | Enhanced Planning Data Exchange to Facilitate Whole System Planning
GC0186 | 3 | 2 | Proposed Grid Code Changes - Post Electricity System Restoration Standard (ESRS) | GC0176 | 2 | Introduction of Demand Control Rotation Protocol within Operating Code 6 of the Grid Code
GC0155 | 1 | 3 | Clarification of Fault Ride Through Technical Requirements | GC0103 | 10 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes
GC0117 | 5 | 4 | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of Power Station requirements | GC0168 | 6 | Submission of Electro Magnetic Transient (EMT) Models
GC0182 | 6 | 5 | Standardisation of Power Flow Metering Polarity | GC0164 | 7 | Simplification of Operating Code No.2
GC0181 | 9 | 6 | Enhance the Effectiveness of System Incidents Reporting
GC0140 | 10 | 7 | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions

## Grid Code
Grid Code (GC): is the technical code for connection and development of the National Electricity Transmission System
[5 empty] | General Modification Information | [6 empty] | Workgroup | [5 empty] | Consultation |  |  |  | Ofgem
Mod Number | Title | Purpose: What is the Mod trying to deliver | Current Status | Latest Status | Priority No: | Proposer Organisation | Date raised | Impacted Parties | Governance Route | Cross Code Impact | Impact on EBR (Elec Balancing Regulation) | Number of Workgroup Members | Number of Workgroup Consultation Responses | Number of timeline amends | Number of alternative requests | Number of alternative solutions | Workgroup Report to Panel | Code Administrator Consultation | Number of Code Administrator Consultation Responses | Legal text issues from Code Administrator Consultation | Panel Vote | Sent to Ofgem / Appeals Window | Ofgem Decision Received | Implementation Date | 2025-03-31
GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | To set out within the Grid Code the compliance obligations in the EU Connection Codes as they relate to Electrical Standards | Draft Final Modification Report | The Panel met in August 2017 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 18 September 2017. July 2022 Panel priorited the modification as low on the prioritisation stack and therefore Workgroup went on hold. February 2023 Grid Code Review Panel adjusted the prioritisation of the modification and requested Workgroups be restarted. Workgroup nominations closed on 26 May 2023. The June 2023 Grid Code Review Panel approved the updated Terms of Reference for GC0103. The GC0103 Workgroup met on 10 August 2023 to scope how to assess the technical feasibility of harmonising the Relevant Electrical Standards (RES), as requested by the GC0103 Workgroup. A verbal timeline update was given to the August Grid Code Review Panel. A revised timeline will be issued to the Grid Code Review Panel for approval as soon as possible. An update was given to the February 2024 Grid Code Review Panel that analysis is currently ongoing regarding the possibility of harmonisation of the Relevant Electrical Standards, noting that the November 2023 Autumn Statement has recommended that an ENA-led forum meet to discuss harmonisation of equipment standards. It is currently unclear on how this will interact with GC0103, noting that it has not been possible to provide an updated timeline. The Panel agreed to receiving a timeline update in due course, and requested regular updates on the progress of the modification until that point. The Panel received an update on this modification in May 2024. Following a timeline update being presented to the March 2025 Grid Code Review Panel, GC0103 Workgroups have reconvened. The Workgroup Consultation opened on 21 May 2025, closed on 12 June 2025 and received 3 responses. At the November 2025 Panel meeting, the Panel agreed GC0103 had met the Terms of Reference and could proceed to Code Administrator Consultation. The Code Administrator Consultation opened on 05 December and will close on 12 January.The Draft Final Modification Report will be presented to the Panel in January 2026. The Panel agreed that further work needed to be done to the Applicable Electrical Standards, before they could vote, therefore the Draft FInal Modification Report will be presented at a future Panel meeting. TOs and Legal working on the pre-amble for the AES. The last email was sent on 02 April. Still awaiting finalised document. 06/07/2026 AES still needs some work and will return to Panel once concluded. | N/A | SSE Generation Ltd | 2017-07-01 | Medium impact on Transmission Owners, Offshore Transmission Owners, Interconnectors, Distribution Network Operators, NESO and Generators | Standard Governance (Workgroup) | STC | No | 18 | 3 | 2 | 0 | 0 | 2025-11-19 | 02/12/2025 - 07/01/2026 | 4 | Yes | 2025-01-29 | 2025-02-10 | TBC | 10 business days after Ofgem decision | 2026-07-06
GC0117 | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of Power Station requirements | This modification will set out within the Grid Code the common GB obligations in the EU Connection Codes as they relate to the specification of certain items by certain obligated party or parties. | Workgroup Stage | The Panel met in June 2018 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 18 October 2018. Workgroups were paused until May 2021 due to Panel prioritisation. Workgroup meetings restarted on 19 May 2021. In March 2022, the Workgroup received Panel approved to extend their timeline to allow a further two Workgroup meetings to refine legal text for WAGCMs. Following feedback from the Workgroup Consultation a CBA will be conducted, an amended timeline was agreed at the August Grid Code Review Panel. Further to this the October Grid Code Review Panel agreed the new timeline, allowing for the CBA to be completed by February 2023. A CBA Check in meeting was held on 8 December 2022. An updated timeline was approved by the March 2023 Grid Code Review Panel. An updated timeline was approved by the June Grid Code Review Panel for approval. Due to additional analysis required for WAGCM1 the Workgroup Report which was intended to the issued to the August 2023 Grid Code Review Panel was delayed, an updated timeline was submitted in both the July 2023 and August 2023 Grid Code Review Panels. July 2023 GCRP approved the retrospective title change to include the reference to ‘Power Station requirements’ and the new timeline as submitted within the Panel Papers. A new timeline was presented to the August 2023 Grid Code Review Panel which the panel approved. A new timeline was presented to the October 2023 Grid Code Review Panel which the panel approved. A new timeline was presented at the December 2023 Grid Code Review Panel meeting. The Panel approved the timeline. The Workgroup Report was presented at the January 2024 Grid Code Review Panel meeting. The Panel agreed that the Terms of Reference have been met and agreed for GC0117 to proceed to Code Administrator Consultation, subject to a legal text concern raised by a Panel member being addressed and confirmation from the Authority regarding a potential interaction with CMP298 (these two matters to be approved by Panel via e-mail ahead of the Code Administrator Consultation). The Code Administrator Consultation ran from 19 February 2024 and until 26 March 2024 and received 13 non-confidential responses (0 confidential). The Draft Final Modification Report was issued to the April 2024 Grid Code Review Panel for the Panel to complete their recommendation vote. The Panel held their recommendation vote, with 4 Panel members noting that the Original better facilitates the Grid Code objectives than the Baseline and 2 Panel members noting that WAGCM1 better facilitates the Grid Code objectives. The Panel were unable to reach a consensus on whether the Original Proposal better facilitated the Grid Code objectives than the Baseline. The Final Modification Report was issued to the Authority on 14 May 2024. The Authority will be running a Consultation on their draft decision letter, ahead of issuing their final decision, which is expected to be issued on 06 December 2024. Ofgem EDD for October 2024 confirms expected decision date of 06 December 2024. 06/11/2024 The authority decision will be dependent on whether a 4 or 6 week consultation period period was required and if the latter then the decision date would be in the New Year, rather than 06 December 2024. An Impact Assessment Consultation will be issued on 06/01/2025 and open for 6 weeks, with the expected decsion date to be in the New Year. The Authority sent back this modification on 18 July 2025. At the meeting on 21 August, the Panel agreed Terms of Reference and asked for the Workgroup to be re-formed. Further Workgroup nominations opened on 28 August and closed on 18 September. The Workgroup are considering feedback from the DNO's on the CBA. DNOs collectively are addressing concerns raised regarding BC1.6 but have agreed this s outside GC0117. 2nd CAC is being reviewed by members for 14 April and awaiting on the CBA plan (2 more weeks). Update will have to be May, with a timeline update. DNOs collectively are addressing concerns raised regarding BC1.6 but have agreed this s outside GC0117. CBA started this week but will need to address timeline at the June Panel. 06/07/2026 Awaiting a timeline update from the CBA owner. | 4 | SSE Generation Ltd | 2018-06-01 | Medium impact on Transmission Owners, Offshore Transmission Owners, Interconnectors, Distribution Network Operators, Transmission System Users, NESO and Generators | Standard Governance (Workgroup) | CUSC, STC & BSC | Yes | 14 | 9 | N/A | 5 | 1 | 2024-01-17 | 19/02/2024 - 26/03/2024 and 13/05/2026 - 15/06/2026 | 13 | No | 2026-07-30 | 2026-08-07 | TBC | 10 business days after Ofgem decision | 2026-07-06
GC0139 | Enhanced Planning Data Exchange to Facilitate Whole System Planning | This Modification seeks to increase the scope and detail of planning - data exchange between DNO's and ESO to help facilitate the transition to a smart, flexible energy system. | Awaiting decision | The Panel met in March 2020 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 6 May 2020. The GC0139 timetable is dependent on the CIM governance group completing their work and on 10 January 2022, Ofgem published their open letter on CIM Governance. Following the publishing of the letter, Workgroup meetings recommenced on 30 March 2022. In May 2022 the Workgroup moved back two of their meetings to allow time to develop their legal text ahead of their Workgroup Consultation. A new timeline was approved at the July 2022 Grid Code Review Panel. New timeline approved at the January 2023 Grid Code Review Panel. A new timeline was presented to the August 2023 Grid Code Review Panel which was approved. A new timeline was presented to the September Grid Code Review Panel which was approved. A new timeline was approved at the February 2024 Grid Code Review Panel Meeting. A new timeline was approved at the April 2024 Grid Code Review Panel. The August 2024 Grid Code Review Panel approved a 3 month timeline extension. The Workgroup Consultation was issued on 17 December 2024, closed on 21 January 2025 and received 7 responses. The Workgroup Vote was held in November 2025. The Workgroup Report was presented to the December Panel meeting, where the Panel agreed the Terms of Reference had been met. The Code Administrator Consultation closed on 06 February. The DFMR will be presented at the February GCRP. At the February Panel it was concluded that in order to complete the Panel Recommendation Vote, Workgroup agreement was required to proposed legal text changes, so the DFMR will come back to Panel. The Final Modification Report was sent to Ofgem on 06 April 2026. 06/07/2026 The EDD is 23 July 2026. | N/A | Electricity North West | 2020-02-10 | High Impact on NESO, Transmission Owners and Distribution Network Operators | Standard Governance (Workgroup) | STC (STCP19-5) | Yes | 12 | 7 | 2 | 0 | 0 | 2025-12-03 | 06/01/2026 - 06/02/2026 | TBC | TBC | 2026-02-26 | 2026-04-06 | TBC | 10 business days after Ofgem decision | 2026-07-06
GC0155 | Clarification of the Fault Ride Through Technical Requirements | This modification is based on an alternative proposal (WAGCM2) to GC0151 ‘Grid Code Compliance with Fault Ride Through Requirements’. It aims to clarify the technical requirements for fault ride through capability set out in the Grid Code to improve consistency, accuracy and understanding and to help prevent non-compliance with the Grid Code. | Workgroup Stage | The Panel met in January 2022 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 10 February 2022. At the Workgroup meeting on 25 July 2022, ESO provided a plan for the additional work required by the workgroup and this revised timeline was approved at the July Grid Code Review Panel. A timeline extension was approved at the November Grid Code Review Panel. An updated timeline was approved by the June 2023 Grid Code Review Panel. A new timeline was presented to the August 2023 Grid Code Review Panel and was approved. A new timeline was approved at the January 2024 Grid Code Review Panel meeting. The next Workgroup meeting will be taking place on the 15 October 2024. An updated timeline will then be presented to the November Grid Code Review Panel for approval. The Workgroup planned for 15 October was delayed to 22/11/24 allow more time for actions to be completed. At this Workgroup, the Workgroup discussed the progress on the modification to date, and determined that a CBA is required for further analysis. At the February Grid Code Review Panel, the Panel agreed to having GC0155 split into two modifications. A new modification on the Temporary Over Voltage part of the modification is expected to be raised in March 2025. A timeline and Terms of Reference update were accepted at the March 2025 Panel.The next Workgroup is scheduled for early 2026. A timeline update will be presented to the January Panel. The timeline update was approved at the January Panel. A poll has been sent to Workgroup members to select a Workgroup date at the end of this month. This will be presented at the May Panel to ask if the Governance route can be amended, It was agreed at the May Panel that this modification would follow the governance route of a limited Wokgroup, due to quoracy issues. 06/07/2026 Workgroup meetings have recommenced. | 3 | NESO | 2021-12-01 | Medium impact on Generators, Transmission System Operators, Interconnectors, Transmission Owners, Distribution Owners | Standard Governance (Workgroup) | None | No | 14 | TBC | 2 | 2 | 2 | 2026-04-15 | 30/03/2026 - 30/042025 | TBC | TBC | 2026-06-25 | 2026-07-07 | TBC | 10 business days after Ofgem decision | 2026-07-06
GC0164 | Simplification of Operating Code No.2 | This modification seeks to help Users to clearly identify and understand their obligations under Operating Code No.2 (OC2) by making it more accessible, easy to navigate and understand. This is the first modification resulting from the Alignment, Simplification and Rationalisation Workstream (ASRW) of the Digitalised Whole System Technical Code project. | Approved | On 04 October 2023 the ESO raised Grid Code Modification Proposal GC0164. The October 2023 Grid Code Review Panel recommended that GC0163 should be treated as a standard governance modification. A new timeline was approved at the January 2024 Gride Code Review Panel. At the January Panel meeting, the Panel was asked by the Authority to reconsider the governance route for GC0164. The Panel considered GC0164 under GR.19.2(d) and GR.18.4 and confirmed unanimously that it meets the Self-Governance criteria, and asked for a Workgroup to consider the modification. A new timeline was approved at the May 2024 Grid Code Review Panel meeting. The Workgroup Consultation ran from 07 June 2024 to 08 July 2024, and received 3 responses. The August Panel approved a 2 month extension to the timeline, which means that the Workgroup Report will now be presented to the October 2024 Panel. The next Workgroup meeting will be taking place on the 02 October 2024. The Workgroup report will be presented at the November Grid Code Review Panel. At the November 2024 Grid Code Review Panel, the Panel agreed that the Terms of Reference have been met and agreed for GC0164 to proceed to Code Administrator Consultation. The Code Administrator Consultation was published on 02 December, closed on 16 January 2025 and received 4 responses. The Draft Final Modification Report was submitted within the February 2025 Panel papers. The Panel agreed that further work was required to the legal text prior to undertaking the Vote. The Panel agreed the Governance update in June 2025. A timeline update will be presented to the Panel in July 2025.The Second Code Administrator Consultation was submitted in the September 2025 Panel papers for review by the Panel. The Panel asked for a further review of the legal text, with some Panel members asked to join the Workgroup.The second Code Administrator Consultation will close on 27 March 2026. The Draft FInal Modifcation will be presented at the April Panel. The Final Modification Report was sent to Ofgem on 05 May 2026. 06/07/2026 The modification was approved by the Authority on 25 June 2026. | N/A | NESO | 2023-10-04 | Low impact On Restoration Service Providers, Generators, Interconnectors, Transmission Owners, Non-Embedded Customers and NESO | Standard Governance (Workgroup) | N/A | Yes | 10 | 4 | 2 | 0 | 0 | 2024-11-28 | 02/12/2024 - 16/01/2025 TBC | 4 | Yes | TBC | TBC | 2026-06-25 | 2026-07-09 | 2026-07-06
GC0165 | Typographical and formatting changes to the Grid Code | This Grid Code modification aims to make minor typographical and formatting amendments to sections of the Grid Code. | Implemented | On 06 October 2023 the ESO raised Grid Code Modification Proposal GC0165. The October 2023 Grid Code Review Panel recommended that GC0163 should be treated as a Self Governance Fast Track Modificiation. [06/12/2023] The appeals window opened on 03 November 2023 and closed on 24 November 2023. The Code Administrator recieved no comments and GC0165 was implemeted on 04 December 2023. | n/a - hidden from tracker | ESO | 2023-10-06 | Low impact Grid Code Parties and the ESO | Fast Track self-governance | N/A | No | [5 empty] | N/A | N/A |  |  | 2023-10-26 | 03/11/2023 - 24/11/2023 | TBC | 2023-12-04 | 2025-03-31
GC0166 | Introducing new Balancing Mechanism Parameters for Limited Duration Assets | This modification seeks introduce new parameters that will allow the better use of Electricity Storage Modules within the Balancing Mechanism, with all Balancing Mechanism Units (BMUs) required to submit the new parameters. | Implemented | On 29 November 2023 the ESO raised Grid Code Modification Proposal GC0166. The December 2023 Grid Code Review Panel recommended that GC0166 should follow the Standard Governance route and proceed to a Workgroup. The Panel agreed the Terms of Reference for the Workgroup. The first Workgroup was on 01 February 2024. The April 2024 Grid Code Review Panel approved an updated timeline. The July Grid Code Review Panel approved an updated timeline and an amendments to the modification title, which removed the word "Programme" and replaced it with the word "Mechanism". A four month timeline extension was approved be the September 2024 Grid Code Review Panel and the Workgroup Report will now be presented to the April 2025 Panel. The Workgroup consultation closed on 09/12/24.The Workgroup Vote took place on 19 March 2025. The Code Administrator Consultation opened on 06 May 2025, closed on 06 June 2025 and received 6 non confidential responses and 1 confidential response. 06/01/2026: This modification was implemented on 05 December following Authority Decision on 22 October. | N/A | NESO | 2023-11-29 | Medium impact on Generators, Aggregators, storage users | Standard Governance (Workgroup) | BSC | Yes | 52 | 14 | N/A | 0 | 0 | 2025-04-23 | 06/05/2025 - 06/06/2025 | 7 | Yes | 2025-06-26 | 2025-07-08 | 2025-10-22 | 2025-12-05 | 2026-02-06
GC0168 | Submission of Electro Magnetic Transient (EMT) Models | As Great Britain’s (GB) power system moves towards a net zero carbon operation; the number of Inverter-Based Resources (IBR) is expected to increase, with the amount of synchronous generation in the grid to decline which will significantly change the characteristics of the GB network. These changes give rise to the potential control interactions between the devices across the network leading to risks of oscillations and inverter stability. This modification seeks to require certain Users to provide the ESO with EMT models to enable analyses such as system oscillation, inverter stability and Transient Over Voltage (ToV) | Workgroup stage | Proposal raised and submitted to the March 2024 Grid Code Review Panel. The March 2024 Grid Code Review Panel unanimously agreed that GC0168 should follow the Standard Governance route and proceed to a Workgroup. The Panel approved the Terms of Reference for the Workgroup. Workgroup Nominations opened on 03 May 2024 and closed on 28 May 2024. The Proposer is exploring the solution further and completing work on stakeholder feedback, prior to commencing Workgroups. The time line has been revised along with an addition to the TOR, which will be presented to Grid Code Review Panel on 24 October 2024 The revised timeline and additional TOR was approved at the October Grid code Review Panel. The following Workgroup meeting was to review the Legal text and the Workgroup consulation. The Workgroup consultation was published on 23 January 2025, closed on 21 February 2025 and received 7 non-confidential responses and 2 confidential responses. The next Workgroup meeting is on 31 March 2025. The Proposer received some feedback on the modification legal text prior to the May Grid Code Review Panel, leading to a delay in presenting the Workgroup Report. The Workgroup Report was submitted in the June 2025 Panel Papers. The Panel did not agree that the Terms of Reference had been met, and asked for further review of the legal text by the Workgroup. A timeline update will be presented at the February Panel.The new timeline was approved at the February Panel. The Code Administrator Consultation closes on 08 June 2026. 06/07/2026 The Panel requested the Workgroup to review the Legal text comments received from the Code Administrator Consultation. | N/A | NESO | 2024-03-05 | High impact on Generators, Transmission System Operators, Distribution Network Operators, Interconnector Owners, Transmission Owners | Standard Governance (Workgroup) | CUSC | No | 12 | 9 | 1 | 0 | 0 | 2026-03-18 | 30/03/2026 - 30/04/2026 | TBC | TBC | 2026-05-11 | 2026-06-08 | TBC | 10 business days after Ofgem decision | 2026-07-06
GC0169 | Material changes arising from Grid Code Modification GC0136 | This modification is designed to address a number of non-specialist changes identified following Grid Code Modification GC0136: Non-material changes to Grid Code following implementation of the EU Connection Codes | Awaiting Authority Decision | Proposal raised and submitted to the March 2024 Grid Code Review Panel. The March 2024 Grid Code Review Panel by majority agreed that GC0169 should follow the Standard Governance route and proceed to a Workgroup. At the April 2024 Grid Code Review Panel, the ESO indicated that they would be splitting GC0169 into two separate modifications. The Panel agreed to approve the Terms of Reference following completion of this. The Proposal was resubmitted to the June 2024 Grid Code Review Panel after being split into two separate modifications GC0169 and GC0173. The Panel unanimously agreed that both modifications should follow the Standard Governance route and proceed to a single joint Grid Code/Distribution Code Workgroup. The Panel approved the Terms of Reference for both modifications and Workgroup Nominations opened on 02 July 2024 and closed on 23 July 2024. The Workgroup Consultation was published on 20 March and ran until 10 April, receiving 4 responses.The Code Administrator Consultation was held from 30 July - 05 September and received 1 responses. 21/10/2025: The Final Modification Report was sent to the Authority on 07 October 2025. | N/A | NESO | 2024-03-06 | Medium impact on NESO, Grid Code Users, Transmission Licensees | Standard Governance (Workgroup) | DCode | Yes | 8 | 4 | N/A | 0 | 0 | 2025-07-16 | 30/07/2025 - 05/09/2025 | 1 | No | 2025-09-25 | 2025-10-07 | TBC | 10 business days after Ofgem decision | 2026-02-06
GC0170 | Typographical and formatting updates following the implementation of GC0156: Facilitating the Implementation of the Electricity System Restoration Standard | This modification aims to make minor amendments to the Grid Code which were highlighted through the implementation of GC0156: Facilitating the Implementation of the Electricity System Restoration Standard | Implemented | Proposal raised and submitted to the March 2024 Grid Code Review Panel. The March 2024 Grid Code Review Panel unanimously agreed that GC0170 should follow the Fast Track Self Governance route and be implemented. The Appeals Window ran from 26 March 2024 until 18 April 2024 and no responses were received. [07/05/2024] GC0170 was implemented on 22 April 2024. | n/a - hidden from tracker | ESO | 2024-03-06 | Low impact on Grid Code Parties and the ESO | Fast Track self-governance | N/A | Yes | [5 empty] | N/A | N/A |  |  | 2024-03-21 | 26/03/2024 - 18/04/2024 | N/A | 2024-04-22 | 2025-03-31
GC0171 | Improving the clarity and transparency of the Compliance Process for Small Generators with a Bilateral Embedded Generator Agreement (BEGA) | This modification aims to update the definitions of operational notifications for Embedded Small Generators with a Bilateral Embedded Generator Agreement (BEGA) with the ESO. This modification will help improve the clarity and transparency around the compliance responsibilities between the ESO and relevant Network Operator, therefore increasing overall efficiency and stakeholder satisfaction during the compliance process. | Implemented | Proposal raised and submitted to the April 2024 Grid Code Review Panel. The Panel directed the Proposer to futher develop their modification and return to a subsequent meeting. The Proposal was resubmitted as part of the May 2024 Grid Code Review Panel papers. At the May Panel meeting, the Panel unanimously agreed that GC0171 should follow the Self Governance route and proceed to Code Administrator Consultation. This was published on 05 June 2024 and ran until 05 July 2024. The Code Administrator Consultation received 1 response. The July 2024 Grid Code Review Panel unanimously agreed that proposed amendments to the legal text, identified post Code Administrator Consultation were typographical and instructed the Code Administrator to make the changes under Grid Code Governance Rule 22.4(i). The Panel also held their determination vote and unanimously determined that the Proposer’s solution better facilitated the Applicable Objectives and is implemented. The Appeals window opened on 07 August 2024 and closed on 29 August 2024. No appeals were received. [09/09/2024] This modification was implemented on 05 September 2024. | n/a - hidden from tracker | NESO | 2024-03-28 | Low impact on Generators in respect of Embedded Small Power Stations, Network Operators, NESO | Self Governance (straight to CAC) | NA | No | [5 empty] | N/A | 05/06/2024 - 05/07/2024 |  |  | 2024-07-25 | 07/08/2024 - 29/07/2024 | N/A | 2024-09-05 | 2025-03-31
GC0172 | Replacing References to Electricity Supply Industry Arbitration Association | The Electricity Arbitration Association (EAA) is now defunct. This modification looks to replace the EAA and with the London Court of International Arbitration from provisions in the general conditions and definitions sections of the codes. This body is defined in the Grid Code currently as the Electricity Supply Industry Arbitration Association. | Implemented | Proposal raised and submitted to the May 2024 Grid Code Review Panel. At the May Panel meeting, the Panel unanimously agreed that GC0172 should follow the Standard Governance route and proceed to Code Administrator Consultation. This was published on 10 June 2024 and will run until 10 July 2024. The Code Administrator Consultation received 1 response. The July Grid Code Review Panel unanimously recommended that the Proposer’s solution better facilitated the Grid Code Applicable Objectives and should be implemented. The Final Modification Report was sent to Ofgem on 07 August 2024. 07/04/25: The Authority approved the Original solution on 20 March 2025, which was implemented on 03 April 2025. | N/A | NESO | 2024-05-03 | Low impact on Grid Code Parties | Standard Governance (straight to CAC) | CUSC, STC & BSC | No | N/A | N/A | N/A | N/A | N/A | N/A | 10/06/2024 - 10/07/2024 | 1 | No | 2024-07-25 | 2024-08-07 | 2025-03-20 | 2025-03-03 | 2025-04-16
GC0173 | Consistency of Technical and Compliance Requirements between GB and European Users | This modification is designed to ensure alignment between the Grid Code Connection Conditions and European Connection Conditions and interactions with the Compliance Processes and European Compliance Processes in addition to a data clarification in the Planning Code in respect of thermal storage technologies. | Awaiting Authority Decision | The Proposal was raised and submitted to the June 2024 Grid Code Review Panel along with GC0169. The Panel unanimously agreed that both GC0169 and GC0173 should follow the Standard Governance route and proceed to a single joint Grid Code/Distribution Code Workgroup. The Panel approved the Terms of Reference for both modifications and Workgroup Nominations opened on 02 July 2024 and closed on 23 July 2024. The Workgroup Consultation was published on 20 March and ran until 10 April, receiving 4 responses. The second Code Administrator Consultation opened on the 26 September 2025 and closes on 26 October 2025. 06/01/2026: The Final Modification Report was sent to the Authority on 10 December 2025. | N/A | NESO | 2024-05-22 | Medium impact on NESO, Grid Code Users, Transmission Licensees | Standard Governance (Workgroup) | DCode | No | 8 | 4 | N/A | 0 | 0 | 2025-07-16 | 30/07/2025 - 05/09/2025 26/09/25 - 26/10/2025 | 2 1 | Yes No | 2025-11-27 | 2025-12-10 | TBC | 10 business days after Ofgem decision | 2026-02-06
GC0174 | Review of obligation to provide EU Transparency Availability Data as specified in OC2.4.7 | Following the approval of BSC Modification CP1583 (Rationalising publication of European Transparency Regulation data on Elexon Systems), the obligation for parties to submit EU Transparency Availability Data as specified in OC2.4.7 is no longer required. ​ | Implemented | The Proposal was originaly raised and submitted to the June 2024 Grid Code Review Panel. The Panel concluded that in order to determine the Governance route further clarity needed to be added into the Proposal. The Proposal was re-submitted to the July 2024 Grid Code Review Panel Panel, where the Panel agreed by majority that GC0174 should follow the Self Governance route and proceed to a Workgroup. Nominations for this modification opened on 07 August 2024 and closed on 29 August 2024. But due to a lack of quoracy, nominations were reopened on 30 August 2024 and closed on 13 September 2024. In total only two nominations were received. [27/09/24] The September 2024 Grid Code Review Panel agreed by majority that GC0174 should procced as a Limited Membership Workgroup under Governance Rule G.R.20.5 (c), after a Panel Member agreed to join the Workgroup. At the February 2025 Grid Code Review Panel, the Panel agreed that the modification could proceed to Workgroup Consultation. The Workgroup Consultation opened on 28 February 2025 and will run until 21 March 2025. The Code Administrator has also reopened nominations to run alongside the Workgroup Consultation. A Governance update was presented to the April 2025 Grid Code Review Panel, where the Panel agreed that the modification should become Standard Governance. As a result of this, a timeline update was also approved at the meeting. The Code Administrator Consultation opened on 27 June 2025, closed on 28 July 2025 and received one response.The Panel unanimously recommended implementation of GC0174. The Final Modification Report was sent to the Authority on 03 September. 06/01/2026: The Authority approved the Original solution on 28 November. This was implemented on 12 December 2025. | N/A | NESO | 2024-06-11 | Low impact on Generators, Non-Embedded Customers, NESO | Self Governance (Workgroup) | BSC | No | 3 | 1 | 1 | 0 | 0 | 2025-06-18 | 27/06/2025 - 28/07/2025 | 1 | No | 2025-08-21 | 2025-09-03 | 2025-11-28 | 2025-12-12 | 2026-03-09
GC0175 | Removing references to “Fax” or “Facsimile” within the Grid Code | This modification seeks to remove references to “fax” and “facsimile” from the Grid Code in order to reflect both current and future methods of communication between relevant Users and the National Energy System Operator (NESO) due to the national decommissioning of the Public Switched Telephone Network (PSTN). | Implemented | 06/11/2024 The Proposal was submitted to the October Grid Code Review Panel where it was unanimously agreed that GC0175 should follow the Standard Governance route and proceed straight to Code Administator Consultation. At the January 2025 Panel, the Panel unanimously recommended that GC0175 should be implemented. The Final Modification Report was sent to the Authority on 10 February 2025. 07/04/25: This modification was approved by the Authority on 14 March 2025 and was implemented on 28 March 2025. | N/A | NESO | 2024-10-08 | Medium impact on Generators, Demand Users, Interconnectors, Distribution Network Operators, NESO | Standard Governance (straight to CAC) | CUSC and STC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | 29/10/2024 - 29/11/2024 | 5 | Yes | 2025-01-30 | 2025-02-10 | 2025-03-14 | 2025-03-28 | 2025-04-16
GC0176 | Introduction of Demand Control Rotation Protocol within Operating Code 6 of the Grid Code | The modification will make changes to OC6 to allow for the Demand Control Rotation Protocol (DCRP) to be formally recognised as a tool to manage shortfalls in electricity supply, over an extended period of time (i.e. 3 to 24 hours). | Awaiting Decision | The Proposal was submitted to the December Grid Code Review Panel where it was agreed unanimously that GC0176 should follow the Standard Governance route and proceed to Workgroup. Nominations opened on 17 December 2024 and ran until 17 January 2025. The January 2025 Panel approved amendments to the Terms of Reference for this modification. The Workgroup Consultation ran from 28 July until 26 August and received 6 responses. At the November 2025 Panel meeting, the Panel agreed GC0176 had met the Terms of Reference and could proceed to Code Administrator Consultation. The Code Administrator Consultation opened on 04 December and closed on 12 January. A timeline update will be presented to the Panel in January. The Draft Final Modification Report will be delayed due to the ongoing DCode consultation. The Draft Final Modification Report will be presented at the February Panel. The Panel Recommendation Vote was deferred prior to the meeting to allow further engagement with the Energy Network Association on the definition of Load Lock. The Draft Final Modification Report will be presented at a later Panel. Code Admin met with the Proposer to explain steps for progressing DFMR after pause, Proposer chose to go back to Workgroup with second Code Administrator Consultation. A new timeline was approved at the April Panel and the next Workgroup is scheduled for 08 May 2026. The Final Modification Report was sent to Ofgem on 01 June 2026. 06/07/2026 The EDD is 31 July 2026. | N/A | NESO | 2024-11-11 | High impact on Distribution Network Operators, NESO and Consumers | Standard Governance (Workgroup) | DCode | No | 9 | 6 | 2 | 0 | 0 | 2026-11-19 | 04/12/2025 - 12/01/2026 | 4 | No | 29/01/2026 | 11/02/2026 | TBC | 10 business days after Authority decision | 2026-07-06
GC0178 | Temporary Overvoltage - Specification of Limits and Clarification of Obligations | This modification aims to specify limits on temporary overvoltage, clarify the obligations applicable during such events, and address any related issues. | Workgroup Stage | The Proposal was submitted to the March Grid Code Review Panel where it was agreed unanimously that the modification should follow the Standard Governance route and proceed to Workgroup. Workgroup Nominations opened on 01 April and closed on 01 May. A modification update will be presented to the January Panel, asking for a pause, to allow sufficeint time for a consultant to be appointed. The Proposer will present an updated and detailed timeline and the February Panel meeting. 06/07/2026 A timeline upate with be presented to the Panel, once the Consultant has signed the contract. | 1 | NESO | 2025-03-12 | High impact on Generators, Transmission System Owners, Interconnectors, Transmission Owners | Standard Governance (Workgroup) | STC | No | 10 | TBC | N/A | TBC | TBC | N/A | 04/09/2026 - 05/10/2026 | TBC | TBC | 29/10/2026 | 2026-11-16 | TBC | 10 business days after Authority decision | 2026-07-06
GC0179 | Removal of Balancing Code No.4 and Balancing Code No.5 from the Grid Code | Balancing Code No.4 (BC4) and Balancing Code No.5 (BC5) cover Terre Processes and Prequalification Processes. This modification seeks to remove them from the Grid Code due to them being no longer required following the exit of the United Kingdom from the European Union. This modification will also remove references to TERRE from the Grid Code. | Awaiting decision | The Proposal was submitted to the March Grid Code Review Panel where the Panel asked the Proposer to complete further work on their Modification Proposal before returning to a future Panel meeting. An updated Proposal was submitted in the April 2025 Panel Papers. The Panel agreed that GC0179 should follow the Standard Governance Route with a Workgroup. Workgroup Nominations opened on 06 May 2025 and closed on 28 May 2025, but were then extended until 12 June 2025. No nominations were received. At the Panel meeting on 26 June 2025, the Panel asked the Proposer to complete further work on their Modification Proposal before returning to a future Panel meeting where the Panel will determine the Governance Route.The Proposer is currently developing next steps for this Proposal. The modification was presented at the November Panel. The Panel agreed for GC0179 to proceed to Code Administrator Consultation with a delay to the timeline. The Draft Final Modification Report will be presented to the February Panel. The Final Modification Report was sent to Ogem on 11 March 2026. 06/07/2026 The EDD is 20 July 2026. | N/A | NESO | 2025-03-12 | Medium impact on Generators, Transmission System Owners, Interconnectors, Network Operators, National Energy System Operator | Standard Governance (Code Administrator Consultation) | BSC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | TBC | TBC | TBC | TBC | TBC | TBC | 10 business days after Authority decision | 2026-07-06
GC0181 | Enhance the Effectiveness of System Incidents Reporting | Reports are available for industry and the Grid Code Panel to monitor the effectiveness of technical requirements in the Grid Code and Distribution Code – GC0105 and GC0151. The data and the reports are not effectively serving their purpose due to the way the system incidents are being reported. This modification aims to be a further improvement of GC0105. | Workgroup Stage | At the Panel meeting on 24 July 2025, the Panel asked the Proposer to complete further work on their Modification Proposal before returning to a future Panel meeting where the Panel will determine the Governance Route. The Panel agreed the modification could proceed as Standard Governance with Workgroups. Workgroup Nominations opened on 28 August and were due to close on 18 September but this was extended until 03 October. Will require a timeline update to add in 3 more Workgroups before WG consultation. 06/07/2026 A timeline update will be presented at the July Panel. | 6 | Statkraft | 2025-06-26 | Low impact on Transmission System Owners | Standard Governance (Workgroup) | N/A | No | TBC | TBC | N/A | TBC | TBC | 2026-03-18 | 01/04/2026 - 01/05/2026 | TBC | TBC | 2026-06-25 | 07/07/2026 - 28/07/2026 | N/A | 2026-08-11 | 2026-07-06
GC0182 | Standardisation of Power Flow Metering Polarity | This modification aims to provide a unified standard for Power Flow Metering Polarity when data is sent to NESO. The standard will be in the format of a diagram and explanatory description. | Workgroup Consultation | The Proposal was presented to the Panel, in July 2025. The Panel agreed the modification could proceed as Standard Governance with Workgroups. Workgroup Nominations opened on 29 July and closed on 18 August. The Workgroup Consultation opens on 13 April and closes on 12 May 2026. 06/07/2026 The next Workgroup is scheduled for 07 July 2026. | 5 | NESO | 2025-07-07 | High impact on Transmission System Owners, Interconnectors, Network Operators. Low impact on Generators, Transmission Owners and Aggregators | Standard Governance (Workgroup) | STC | No | 6 | TBC | N/A | TBC | TBC | 2026-09-16 | 06/10/2026 - 06/11/2026 | TBC | TBC | 2026-11-26 | 2026-12-09 | TBC | 10 business days after Authority decision | 2026-07-06
GC0184 | Increasing Reactive Power Requirements for PPMs when Operating below Maximum Active Power | This modification proposal is to increase the minimum reactive power requirements for full converter technology connected Power Park Modules when they are operating below their maximum active power output. | Nomination stage | 13/11/2025: The Proposal was raised on 12 November 2025 and was presented at the November Grid Code Review Panel meeting. The Panel did not agree that the Proposal had a clear defect, so the Proposer is considering next steps and will return. 06/07/2026 The Panel approved the modification and to proceed to Workgroup.The nominations close on 17 July 2026. | TBC | NESO | 2025-11-12 | Low impact on Suppliers, Generators and Aggregators | Standard Governance (Workgroup) | N/A | No | TBC | TBC | N/A | 0 | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 10 business days after Authority decision | 2026-07-06
GC0185 | Grid Code Changes for Mandatory Frequency Response (MFR) replacement | NESO are launching a new response service (Real-time Dynamic Regulation) in 2026/27 to replace Mandatory Frequency Response (MFR). It is expected that the two products will run in parallel to 2029 to enable transition, before phasing out procuring of MFR. | Proposal Raised | The proposal will be presented at the January Grid Code Review Panel. The Panel agreed by majority that GC0185 does not have a clearly defined defect and scope and requested the Proposer to return to the March Grid Code Review Panel with a clarified defect and scope. 07/04/2026 The Proposer returned to the March Panel but it was agreed by majority again that there is still not a clear scope, so will return to a future Panel in the Autumn. | N/A | NESO | 2025-01-07 | Medium impact​ on Market participants and NESO | Standard Governance (Workgroup) | CUSC | Yes | TBC | TBC | N/A | 0 | 0 | 2026-09-16 | 30/09/2026 - 30/10/2026 | TBC | TBC | 2026-11-26 | 2026-12-09 | TBC | 10 business days after Authority decision | 2026-07-06
GC0186 | Proposed Grid Code Changes - Post Electricity System Restoration Standard (ESRS) | The purpose of this modification is to update the Grid Code in respect of the restoration requirements following the implementation of GC0156, in particular (but not limited to) the introduction of ’Regional Restoration Plans’, the equitable treatment of National Grid Electricity Transmission, Scottish Power Transmission and Scottish Hydro-Electric Transmission Limited during a restoration, the ability for Network Operators to switch at sufficient speed, clarifications / improvements in testing / data requirements and correction of known errors. | Workgroup Stage | 09/03/2026: The Proposal was presented at the February Panel where it was unanimously agreed that GC0186 should follow the Standard Governance route and proceed to a Workgroup. The Panel agreed by majority the Terms of Reference for the Workgroup. It was unanimously agreed this should be a joint Grid Code/D Code workgroup. Nominations will be sent shortly.Nominations have closed and the first Workgroup meeting is scheduled for 11 June 2026. 06/07/2026 The next Workgroup is scheduled for 09 July 2026 and a revised ToR will be presented at the July Panel. | 2 | NESO | 2026-02-10 | High impact​ on Transmission System Operators, Transmission Owners, Network Operators and Generators. | Standard Governance (Workgroup) | BSC, STC and DCODE | Yes | 11 | TBC | TBC | TBC | TBC | 2026-09-16 | 29/09/2026 - 29/10/2026 | TBC | TBC | 2026-11-26 | 2026-12-02 | TBC | TBC | 2026-07-06
2026-03-09
GC0187 | Grid Code Legal Text Corrections 2026 | This modification seeks to correct sections from the Grid Code. All changes within are immaterial errors that have been found within the current Grid Code legal text. | Implemented | 23/04/2026: The Modification was presented at Panel where unanimously agreed that GC0187 should follow the Fast-Track Self-Governance route and proceed to an appeals window ahead of implementation. It closes on 20 may 2026. 06/07/2026 This modification was implemented on 05 June 2026. | N/A | NESO | 2026-03-11 | Low impact Generators, Transmission System Owners, Interconnectors, Network Operators, National Energy System Operator | Fast-track Self-Governance modification | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10 Business Days following the appeals window | 2026-07-06
GC0188 | Update for Centralised Strategic Network Plan | Due to the upcoming introduction of the Centralised Strategic Network Plan (CSNP), several terms in the Grid Code need to be removed as the references are becoming outdated, including the Electricity Ten Year Statement (ETYS), the Seven Year Statement (SYS) and the Offshore Development Information Statement (ODIS). | Proposal | This has not yet been presented at the Panel, due to a delay by CSNP implementation. This modification will be presented at the June Panel. 06/07/2026 The Panel agreed by majority that GC0188 does not have a clearly defined defect and scope and will return to Panel at a later date. | N/A | NESO | 2026-04-08 | Low impact on any Grid Code parties currently impacted by ETYS/SYS or ODIS. | Standard Governance (Workgroup) | CUSC, STC | Yes | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-07-06
2026-05-18
Click to open Ofgem Implementation Timetable
Click to view the Grid Code
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The list of impacted parties is being developed by GEMSERV. An update is expected in Nov. Same list will be used by all Code Administrators