## STC
STC: System Operator Transmission Owner Code
STCP: System Operator Transmission Owner Code Procedure
STC |  |  |  |  | General Modification Information | [6 empty] | Workgroup | [5 empty] | Consultation |  |  |  | Ofgem
Mod Number | Title | Purpose: What is the Mod trying to deliver | Current Status | Latest Status | Priority Category: | Proposer Organisation | Date raised | Impacted Parties | Governance Route | Cross Code Impact | Impact on EBR (Elec Balancing Regulation) | Number of Workgroup Members | Number of Workgroup Consultation Responses | Number of timeline amends | Number of alternative requests | Number of alternative solutions | Workgroup Report to Panel | Code Administrator Consultation | Number of Code Administrator Consultation Responses | Legal text issues from Code Administrator Consultation | Panel Vote | Sent to Ofgem / Appeals Window | Ofgem Decision Received | Implementation Date | 2026-08-04
CM078 | Connections Triggering Distribution Impact Assessment | This Modification seeks to make changes to the System Operator Transmission Owner Code to reflect CUSC modification CMP328 relating to Transmission connections that trigger an impact assessment on the Distribution network. | Pending Authority Decision | The Panel met on 30 March 2022 and agreed it goes to Code Administrator Consultation Code Administrator Consultation was issued 6 April 2022 and closed 5pm on 29 April 2022. Panel held their recommendation vote on 25 May 2022 and the Final Modification Report was issued to Ofgem on 7 June 2022. (26/02/2023) Ofgem expected decision date was 14 February 2023, which was at the same time as the associated CUSC Modification (CMP328). However, on 14 February 2023, Ofgem sent back the CMP328 Final Modification Report for further work and directed CUSC Panel to revise and resubmit the CMP328 Final Modification Report. February 2023 CUSC Panel agreed for the Workgroup to be re-formed to address each of Ofgem's concerns and agreed in principle (following the assessment by the Workgroup) that a Code Administrator Consultation is needed to be run before it is re-presented to Panel for Recommendation Vote). (31/05/2023) Ofgem advised STC Panel that they are waiting for the revised FMR for (CMP328) before a decision can be made on either modification (06/10/2023) no further update to the above at present, (30/10/2023) no further update to the above at present, (21/11/2023) no further update to the above at present. (01/12/2023) As above, (08/01/2024) This modifciation was sent back from the Authority (14/02/2023) and has been waiting for a workgroup since. It will now be presented to Januaury 2024 panel to consider prioritisation. (02/02024) Awaiting confirmation of next steps (28/02/2024) Still awaiting confirmation of next, Still waiitng for confirmation of next steps, The Proposer and the Code Administrator are working to establish a timeline from when Workgroup meetings would reconvene, Proposer is withdrawing CMP328, this is to be disucssed at CUSC Panel on 26 April 2024, A new Proposer is to take over this modification. Further details to be shared once known, A new Proposer is to take over this modification. Further details to be shared once known, A new Proposer is to take over this modification. Further details to be shared once known, No futher update on progession of modificaiton (22/07/2024) No futher update on progession of modificaiton, Still no update, (06/11/2024) No new update, awaiting further clarification from CMP328. As per EDD from Ofgem October 2024. No new update, awaiting further clarification from CMP328. As per EDD from Ofgem December 2024,,29/01/2025 CUSC Panel will be reviewing the status of CMP328 in the January 2025 Panel, more infomtion on CM078 will follow afterwards, 03/03/2025 Edd authority decision TBC (06/03/2025) On 14 February 2025 Special CUSC Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. It was agreed that CMP328 remained low priority. 07/07/2026 - Awaiting Ofgem decision | N/A | NESO | 2021-03-15 | Medium impact on NESO and Transmission Owners. | Standard Governance (straight to CAC) | CUSC (CMP328) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 06/04/2022 to 29/04/2022 | 2 | no | 2022-05-25 | 2022-06-07 | TBC | TBC (at same time as CMP328 if CMP328 is Implemented)﻿ | 2026-08-04
CM079 | Consideration of STC/STCP changes in relation to CMP330/374 | This modification will consider the proposals being discussed in CMP330/374 and how these might lead to STC or STC Procedures to ensure any consequential changes are proportionate. | Withdrawn | The Panel met on 11 November 2021 and agreed that it goes to a Workgroup. Workgroup meetings commenced on 17 January 2022. Workgroup Meeting held 27 June 2022 at which a revised timeline was agreed re: related CUSC Modification (CMP330/CMP374) to allow sufficient time to finalise the legal text and agree implementation/transitional arrangements. CMP330/CMP374 Workgroup Report was presented to April 2023 CUSC Panel. [04/05/2023] An updated CM079 timeline will be issued for approval at the May STC Panel meeting. [05/06/23] The WG meeting planned for CM079 did not go ahead and was delay until 2 June where the timeline was agreed. It will now be presented to the next STC Panel on 28 June 2023 [07/08/23] Next WG 14 August 2023 to discuss WG consultation responses/refine solution.. (22/08/23) Workgroup Report is in it’s final stages with the Workgroup Vote due to be held 8 September, after which the Report is due to be submitted to Panel for 19 September (06/10/2023) Workgroup Report presented to September STC Panel where it was approved to progress to CAC (30/10/2023 Code Administrator Consultation 04/10/2023 to 25/10/2023, DFMR to be presented to November STC Panel. (21/11/2023) Draft Final Modification Report to be presented to November STC Panel, DFMR approved at November Panel, currently with Panel members to check voting. Due to go to Ofgem 11 December 2023, Currently awaiting Ofgem decision. Due date 08 May 2024, Decision date moved by Authority to 8 July 2024, Decision date moved by Authority to 8 July 2024, Authoirty decision received today, CM079 has been sent back and details can be found on the website, Once CMP414 send back has been discussed at CUSC Panel (26 July 2024), the STC modification will be discussed at August 2024 Panel, No further Update at the moment. (06/11/2024) This is a consequential modification of CMP414 which is a send back from the Authority, no further work has started yet. (22/11/2024) This is a consequential modification of CMP414 which is a send back from the Authority, no further work has started yet. No new update., 29/01/2025 CMP414 currently undergoing second Workgroup Nominations, it will run from 06/01/2024 to 27/01/2025. Update for CM079 will follow. (06/03/2025) Relates to CUSC proposals that are currently not progressing. (08/12/2025) New timeline to be presented at December STC Panel 29/04/2026 - Update presented at April 2026 STC Panel. Panel...[TBD] 07/05/2026 - Further update required at next Panel 29/07/2026 - On 23 July 2026 National Grid withdrew as Proposer following the Ofgem’s June update on Demand Connections Reform and that the Planning and Infrastructure Act will include STC Legal Text. CM079 will be presented to the STC Panel in August to formally approve the withdrawal. | N/A | NGET | 2021-10-04 | High impact on Onshore Transmission Owners; Low impact on NESO | Standard Governance (Workgroup) | CUSC (CMP330/CMP374) | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 04/10/2023 to 27/10/2023 |  |  | 2023-11-28 | 2023-12-11 | TBC | TBC | 2026-08-04
CM093 | Extending the principles of the User Commitment Methodology to Final Sums Methodology as a consequence of CUSC Modification – CMP417 | Extending the principles of the User Commitment Methodology to Final Sums Methodology as a consequence of CUSC Modification – CMP417Extending the principles of the User Commitment Methodology to Final Sums Methodology as a consequence of CUSC Modification – CMP417Extending the principles of the User Commitment Methodology to Final Sums Methodology as a consequence of CUSC Modification – CMP417 | Pending Authority Decision | 08/01/2023 Panel met on 13 December 2023 and agreed the Modification will procced to Workgroup. Nominations have completd and the 1st Workgroup will take place Next Workgroup 29 February 2024, Next Workgroup 13 March 2024, Next Worgroup to be re-arranged, date to be confirmed, Workgroup 2 due to take place on 5 May 2024, The timeline has been updated, next WG now due 6 June 2024, Awaiting next steps re CUSC modification (CMP417), Awaiting next steps re CUSC modification (CMP417),No further update at the moment, No new update. 07/07/2025: CMP417 Workgroups re-commenced in May 2025. An updated timeline will be preseted to the STC Panel. 30/09/2025 Still awaiting updated timeline to be presented to STC Panel. 29/10/2025 The Panel approved the new timeline as submitted within the Panel Papers. 29/04/2026 - Workgroup Report presented at April 2026 STC Panel. Panel...[TBD] 07/05/2026 - April Panel approved to go to CAC 29/07/2026 - At the 24 June STC Panel the Panel recommended unanimously that the Proposer’s solution is implemented and was sent to the Authority on 16 July 2026 | N/A | NESO | 2023-11-21 | NESO, Transmission Owners (TO’s) | Standard Governance (Workgroup) | CUSC CMP417 | none | 4 |  |  |  |  | 2026-06-16 | 01/07/2026 - 22/07/2026 |  | 0 | 2026-06-24 | 2026-07-16 | TBC | TBC | 2026-07-29
CM096 | Application of Gate 2 Criteria to existing contracted background | The related “Implementing Connection Reform” Modification introduces new processes and definitions that will update the existing processes and enable new applicants with more ready projects to progress more rapidly to connection. Gate 2 is a key component of the update; however, the size and rate of growth of the connections queue means that significant action is required as soon as possible to reduce the current queue so that viable projects can be connected more quickly and so that the benefits of our proposed Connections Reform model can be delivered earlier. This Modification seeks to address this by applying a project milestone / criteria (‘Gate 2’) to all existing contracted parties before they are provided with confirmed connection dates and locations. | Withdrawn | (30/04/2024) Presented to STC Panel 24 April 2024, Urgency request sent to Authority awaiting reply. (20/04/2024) Panel recommended Urgency which was granted on 1 May 2024 by the Authority. Workgroup 3 due to take place 23 May 2024 (03/05/2024) Next Workgroup 4 June 2024 (14/06/2024) Progressing through Workgroups, next Workgroup 19 June 2024. (22/07/2024) Workgroup Consultation to be issued to industry on Thursday 26 July 2024. (05/08/2024) Currently out for Workgroup Consultation, due to Close on 6 August 2024. (03/09/2024) Workgroup Alternatives being discussed at present.(07/10/2024) Workgroups 22-25 taking place during October, Workgroup Report to be issued in November 2024. (06/11/2024) A decision was made to withdraw this modification, closing date to become the offical proposer is 5 November 2024, the modification will be presented at a Special Panel on 8 November to confirm the withdrawal. | N/A | NESO | 2024-04-19 | Transmission Owners, Interconnectors, Generators, Demand, Distribution Network Operators, Independent Distribution Network Operators, NESO and Consumers | Standard Governance (Workgroup)- Urgent | CUSC CMP435 | none | [5 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | 2026-07-29
CM097 | Electromagnetic Transient (EMT) Root Mean Square (RMS) Model Submission for Transmission Owners (TOs) | As Great Britain’s (GB) power system moves towards a net zero carbon operation; the number of Inverter-Based Resources (IBR) is expected to increase, with the amount of synchronous generation in the grid to decline which will significantly change the characteristics of the GB network These changes give rise to the need for more accurate dynamic modelling and the need for analysing the effect of potential control interactions between the devices across the network leading to risks of oscillations and inverter stability. This modification seeks to require Transmission Owners (TOs) to provide the ESO with Electromagnetic Transient (EMT) and Root Mean Square (RMS) models to carry out the required analysis. | Pending Authority Decision | (20/05/2024) New Proposal to be presented at May STC Panel, 03/06/2024 Workgroup Nominations going out 3 June 2024. 22/07/2024 Workgroups due to start in August/September 2024 following the completion of Urgent modifications. 03/09/2024 Awaiting completeion of urgent modifications before Workgroups can proceed.(06/10/2024) New Timeline to be presented at November STC Panel. 06/10/2024 New Timeline to be presented at December Panel as November Panel was cancelled. Workgroups due to start 16/12/2024, (05/12/2024) New timeline to be proposed at December's STC Panel on 11/12/2024, 06/01/2025 New timeline agreed, 1st workgroup is on 16 January 2025.07/05/2025: The Workgroup consultation opened on 28 March 2025 and closed on 22 April 2025. Workgroups to re-commence in May 2025. (05/06/2025) Workgroup Consultation completed, Workgroup meetings re-commenced on 5 June. 07/07/2025 Workgroup phase ongoing following Workgroup consultation. (03/09/2025) Workgroups are paused as agreed at August 2025 STC Panel until the related CUSC modification has been approved. 25/03/26 STC Panel approved new timeline. 29/04/2026 - Workgroup Report presented at April 2026 STC Panel. 07/05/2026 - April Panel approved to go to CAC 28/07/2026 - The Draft Final Modification Report was presented to the STC Panel on 24 June where the Panel recommended unanimously that the Proposer’s solution is implemented. The Final Modificaton was submitted to the Authority on 16 July. Authority Decision TBC. | N/A | NESO | 2024-05-03 | High impact: Transmission System operators, Transmission System Owners (onshore & Offshore) | Standard Governace (Workgroup) | GC0168 | NA | 8 | TBC | TBC | 0 | 0 | 2025-08-20 | 01/09/2025 to 19/09/2025 | TBC | TBC | 2026-06-24 | 2026-07-16 | TBC | 10 Business Days following Authority Decision | 2026-07-29
CM098 | Updating STC Arrangements to replacing the Electricity Arbitration Association with the London Court of International Arbitration | The Electricity Arbitration Association (EAA) is now defunct. This modification looks to replace the EAA and replace them with the London Court of International Arbitration from the STC. | Implemented | (20/05/2024) New Proposal to be presented at May STC Panel (03/06/2024) Panel agreed modification proceed to Code Administrator Consultation, will be issued 10 June 2024. (14/06/2024) Code Administrator Consultation to conclude 1 July 2024, Draft Final Modificaiton Report will be presented to July 2024 STC Panel. (22/07/2024) As June Panel was cancelled the Draft Final Modification Report will be issued to July Panel for consideration. (05/08/2024) Currently with Panel members to check voting is correct, Final Modification report to be issued to the Authority on 7 August 2024. (03/09/2024) Final Modification report issued to the Authority 7 August 2024.(06/11/2024) Authority expected decision dated 06/12/2024 (previously 07/08/2024) as per EDD update from Ofgem October 2024, (02/12/2024) Authority expected decision dated 12 February 2025 was (previously 06/12/2024 and 07/08/2024) as per EDD update from Ofgem December 2024. 07/04/2025: The Authority approved the Original solution on 20 March 2025. This was implemented on 03 April 2025. | 0 | NESO | 2024-05-09 | Low impact: STC Parties | Standard Governance (straight to CAC) | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | 10/06/2024 to 01/07/2024 | N/A | N/A | 2024-07-31 | 2024-08-12 | 2025-03-20 | 2025-04-03
CM099 | Removing references to “Fax” and “Facsimile” within the STC | This modification seeks to remove references to “fax” and “facsimile” from the STC in order to reflect the current methods of communication between TOs and the ESO within the STC. | Implemented | (26/06/2024) Proposal due to be shared at STC June Panel for a Panel Vote on whether it should proceed as a Fast Track Self-Governance modification, but carried forward to July Panel due to quoracy issues for Panel. (22/07/2024) Proposal due to be re-presented at STC July Panel for a Panel Vote. (05/08/2024) Appeals window now open until 21 August, the Proposal will be implemented after this date if no objections are received. (03/09/2024) Proposal implemented 30 August 2024 | 0 | NESO | 2024-06-01 | Low Impact: NESO, Transmission Owners (TO’s) | Fast Track/Self Governance | Grid Code/CUSC | NA | N/A | N/A | N/A | N/A | N/A | NA | NA | N/A | N/A | NA | 1 August to 28 August 2024 | NA | 2024-08-30
CM0101 | Additional Definitions in Relation to PM0144 | This Modification’s purpose is to introduce 2 new definitions to Section J, to allow STCP mod PM0144 to be implemented | Implemented | (11/02/2025) This Proposal was presented to Panel in February and approved as a Fast Track SG Proposal. 07/04/2025: The appeals window opened on 28 February and closed on 21 March 2025. Implementation took place on 28 March 2025. | 0 | NESO | 2025-02-11 | N​ESO, Transmission Owners (TO’s)​ | ​​Fast-track Self-Governance modification​ | None | none | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 28 February 2025 to 21 March 2025 ​ | N/A | 2025-03-28
CM0102 | Recificaiton to implementaion of varoius legal text | This proposal aims to correct the legal text errors in modifications which have been approved by the Authority (CM086, CM087, CM095, CM098, CM099) | Implemented | 25/07/2025 This proposal will be presented to the STC Panel 30 July for approval.(03/09/2025) The proposal was approved at the August STC Panel, the Appeals window will close on 15 September. 30/09/2025 The appeals window closed on 15 September, no objections were received. The proposal was implemented on 24 September. | 0 | NESO | 2025-07-02 | Low Impact on Parties to the System Operator Transmission Owner Code (STC) and National Energy System Operator (NESO). | Fast Track/Self Governance | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2025-09-24
CM0103 | STC Consequential Modification for CMP447 (Follow on Modification to CMP428) | This modification seeks to introduce consequential changes needed to reflect the new CUSC definitions of terms, if CMP447 is approved as expected towards the end of October 2025 | Implemented | 25/07/2025 This proposal will be presented to the STC Panel 30 July for approval. (03/09/2025) The proposal was approved at the August STC Panel, the Code Adminstrator Consulatation closed on 15 September. 30/09/2025 Only one response was received in relation to CM0103. The Draft Final Modification Report will be submitted to October STC panel for review. 29/10/2025 The Panel has determined unanimously that the Proposer’s solution better facilitates the STC Applicable Objectives. The Appeals window will open on 07 November 2025 and will close on 28 November 2025. The implementation date will be 10 Business Days after the Authority Decision on CMP447. Implemented on 21 January 2026 | 0 | NESO | 2025-08-06 | Low Impact on Suppliers and Generators | Self Governance | CMP447 | NA | NA | NA | NA | NA | NA | NA | 22/08/2025 - 15/09/2025 | 1 | NA | 2025-10-29 | 07/11/2025 - 28/11/2025 | NA | 2026-01-21 | 2026-07-29
CM0100 | Consequential modification following the approval and implementation of CUSC modification – CMP428 User Commitment liabilities for Onshore Transmission (reinforcement) in the Holistic Network Design | This modification seeks to align changes made to definitions within the CUSC as a result of the approval and implementation of CUSC modification, CMP428 (User Commitment liabilities for Onshore Transmission (reinforcement) in the Holistic Network Design), to ensure consistency between the codes. | Implemented | (22/07/2024) Proposal due to be re-presented at STC July Panel for a Panel Vote. (05/07/2024) Proposal presented to July Panel. Code Administration Consultation will open on 5 August until 3 September 2024. (03/09/2024) Draft SG Final Modifiaction report to be issued to September STC Panel. (07/10/2024) Appeals window opened 4-24 October. (06/11/2024 Implemented 31 October 2024 | n/a- hidden from tracker | NESO | 2024-07-01 | Low Impact: NESO, Transmission owner | Self Governance | NA | NA | [5 empty] | NA | 5 August to 3 September 2024 |  |  | 2024-09-25 | appeals window 4 October to 24 October 2024 | NA | 2024-10-31 | 2025-03-31
CM0104 | Due Date for Monthly Payments to Transmission Operators (TOs) | Minor change to due dates for monthly payments to TOs, to ensure there is always one business day between the payments received by National Energy System Operator (NESO) from Connection and Use of System Code (CUSC) users for Transmission Network Use of System (TNUoS) and Connection Charges and the payments made by NESO to TOs for general system charges and site specific charges. | Implemented | 29/10/2025 The Panel unanimously agreed that CM0104 should follow the Self-Governance route and proceed to Code Administrator Consultation. 10/12/2026 The Panel determined by majority that the Proposer’s solution better facilitates the STC Applicable Objectives and should be implemented. The Appeals window will open on 18 December 2025 and will close on 13 January 2026. The implementation date will be 01 April 2026. | 0 | NESO | 2025-10-03 | Low Impact on Transmission Owners | Self-Governance (straight to CAC) | BSC / PM0150 | NA | NA | NA | NA | NA | NA | NA | 04/11/2025 - 25/11/2025 |  |  | 2025-10-29 | 18/12/2025 - 08/01/2026 |  | 2026-04-01 | 2026-07-29
CM0105 | Standardisation of Power Flow Metering Polarity | This modification aims to provide a unified standard for Power Flow Metering Polarity when data is sent to NESO. The standards should be presented in a format that includes both a diagram and a detailed explanatory description. This is a subsequent modification to GC0182. | Withdrawn | 29/10/2025 The Panel unanimously agreed that CM0105 should follow the Standard Governance route and proceed to Workgroup. The Panel agreed the Terms of Reference for the Workgroup. 28/01/2026 The Panel approved the new timeline as submitted in the Panel Papers. 25/03/26 The Proposer withdrew their support for CM0105 on 10 March 2026. A withdrawal window was opened for 5 Business Days from this date. No parties came forward to become the Proposer for this modification. The Panel agreed that this modification can be withdrawn. | N/A | NESO | 2025-10-14 | High impact on ​Transmission System Owners, Interconnectors, and Network Operators. Low impact on Generators, Transmission Owners and Aggregators | Standard Governace (Workgroup) | GC0182 | NA | NA | NA | NA | NA | NA | 2026-06-08 | 06/05/2026 - 27/05/2026 | [5 empty] | 10 Business Days after Authority decision | 2026-06-22
CM0106 | CM0106: Interface Substation Compliance Assessment | Previously in the planning code Transmission Owners (TOs) and Distribution Network Operators (DNOs) agreed on Access Groups and Access Periods. DNOs at week 24 would share schedules which would allow TOs to determine site compliance. Since NESO separation there has been no clear requirement for TOs to submit this information, which this modification aims to remedy. | Workgroup | 25/03/26 The Panel agreed by majority that this modification has a clearly defined defect and scope, subject to clarification of the Terms of Reference; should follow the Standard Governance (Ofgem decision) route; and should proceed to Workgroup. The Panel agreed the Terms of Reference, subject to amendments from the Panel being incorporated. Workgroup nominations opened on 29 May and closed on 06 May. | Standard | NESO | 2026-03-06 | Low impact on NESO, Transmission Owners (TOs), Network Operators | Standard Governace (Workgroup) | GC0139 | NA | [5 empty] | 2026-09-30 | 05/10/26 - 23/10/26 | [5 empty] | TBC | 2026-08-04
CM0107 | Update for Centralised Strategic Network Plan | Due to the upcoming introduction of the Centralised Strategic Network Plan (CSNP), several sections of the STC/STCP need to be changed as the references are becoming outdated, including the Electricity Ten Year Statement (ETYS), the Seven Year Statement (SYS), the Network Options Assessment (NOA) and the Offshore Development Information Statement (ODIS). | Appeals Window | Proposal raised on 10 April and will be presented to the STC Panel on 29 April 2026. 29/04/2026 - Proposal raised at April STC Panel. Panel decision....[TBD] 07/05/2026 - Panel approved to go to CAC 08/06/26 Code Administrator Consultation Analysis and DFMR generation 29/07/2026 - The DFMR was presented to the STC Panel on 29 July where the Panel determined unanimously that the Proposer’s solution better facilitates the STC Applicable Objectives. The Appeals window opened on 07 August 2026 and will close on 29 August 2026. Implementation date due 01 September 2026. | N/A | NESO | 2026-04-10 | ​Low impact​ on any STC parties currently impacted by the Electricity Ten Year Statement (ETYS), the Seven Year Statement (SYS), the Network Options Assessment (NOA) or the Offshore Development Information Statement (ODIS). | Standard Governance (straight to CAC) | CUSC Grid Code & European Code | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 06/05/2026 - 27/05/2026 | 2 | 1 | 2026-07-29 | 07/08/2026 - 29/08/2026 | n/A | 2026-09-01 | 2026-08-17
CM0108 | ​Managing STC impacts from CMP471 ‘Interim Connection Date Delay Process Ahead of CMP434 | This modification is to proactively assess the consequential impacts on Transmission Owners and relevant STC provisions resulting from CUSC proposal CMP471, such that a holistic solution can be developed prior to approval being sought. | Modification Raised | 07/07/2026 - Modification raised for potention consiquential STC changes from CMP471 and currently going through the criticial friend check stage. | TBC | National Grid | 2026-06-02 | High impact​ on Transmission Owners and NESO; (also indirectly Users via CUSC) | TBC | CMP471 | N/A | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 2026-08-17
CM0109 | Improving the Clarity of STC Schedule 2 | A proposal to amend STC Schedule 2 – List of Code Procedures, to make it more readable. | Appeals Window | 29/07/2026 - CM0109 was presented to the STC Panel where the Panel unanimously agreed that CM0109 should follow the Fast-Track Self Governance route and proceed to an appeals window ahead of implementation. The appeals window opened 03 August and closes 24 August with an implementation date of 01 September. | N/A | NESO | 2026-07-14 | ​Low impact​ Transmission System Operators, Transmission Owners | Fast Track Self-Governance | N/A | N/A | [10 empty] | 03/08/26 - 24/08/26 |  | 2026-09-01 | 2026-08-17
STCP |  |  |  |  | General Modification Information | [11 empty] | Workgroup | Consultation |  |  |  | Ofgem
PM0120 | CUSC Modification 'CMP328 - Connection Triggering Distribution Impact Assessment' | This Modification seeks to make changes to the System Operator Transmission Owner Code to reflect CUSC modification CMP328 relating to Transmission connections that trigger an impact assessment on the Distribution network. | Awaiting New Proposer | The Panel met on 24 February 2022 and this was presented as a draft modification, The Panel met on 31 August 2022 and agreed that PM0120 is approved 'in principle' but a formal approval will be sought once Ofgem publishes a decision on CMP328 and CM078, CMP328/CM078 sent back by Authority awaiting further Workgroups.PM0120 will be implemented once CMP328/CM078 are approved by Authority, Awaiting CMP328 to complete, will then be presented back to Panel for approval to implement, As above, Awaiting CMP328 completion, will then be go to Panel for approval for implementation, Still awaiting confirmation of next steps (Relates to CMP328 and CM078), Proposer is withdrawing CMP328, this is to be disucssed at CUSC Panel on 26 April 2024, A new Proposer is to take over this modification. Further details to be shared once know, No futher update on progession of modificaiton, awaiting further clarification from CMP328, No change, 29/01/2025 CMP328 will be disucssed at Janaury Panel, no update on this Proposal until then. (06/03/2025) On 14 February 2025 at the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications including CMP328 and agreed this modification remained low priority. As this is a concequential modification no futher action will be taken at this time. | N/A | NESO | 2021-09-13 | Medium impact on NESO and Transmission Owners. | N/A | CUSC (CMP328) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | N/A | N/A | TBC (at same time as CMP328) | 2026-08-04
PM0124 | CUSC Modification 'Enduring Expansion Constant and Factor Review' | This is a consequential modification seeks to revise data requirements set out in the STC and facilitate changes arising from CUSC modifications CMP315 and CMP375 which amend the calculation of the Expansion Constant & Expansion factors to better reflect the growth of and investment in the National Electricity Transmission System (NETS) | Proposal raised | The Panel met on 30 March 2022 and this was presented as a draft modification, This modification was presented as draft to the October 2022 Panel and will be formally presented for Panel to agree to the changes in principle once the CMP315/CMP375 solutions are fully developed. 2 of the solutions are fully developed but after CMP315/CMP375 meeting on 2 May 2023, there is one new solution (CMP375 WACM2) that needs further development - timescales (given the requirement for further data from the Transmission Owners) are currently unclear, The CMP315/CMP375 Workgroup completed their Workgroup Vote on 16 August 2023, the Workgroup Report will be issued to the October 2023 CUSC Panel., Updated STCPs to be submitted to November 2023 STC Panel, Updated STCPs to be submitted to December 2023 STC Panel, STCP to be submitted to Panel once completed., Proposal being formally submitted to February STC Panel, Approved in principle at February 2024 STC Panel. Awaiting Authority decision of conequential mods (CMP315/375), expected 30 September 2024, Decision date moved to 30 September 2024, (14/06/2024) Consequential modification of CMP315/375, awaiting Authority decision due 30 September 2024, This is a consequential modification of CMP414 which is a send back from the Authority, no further work has started yet. (22/11/2024) No change from previous comment, 29/01/2025 No change from previous comment. (06/03/2025) CMP315 was sent back my the authority and is wating for a Workgroup to be set up, CMP375 is waiting for a decision from Ofgem. As PM0124 is a consequential modification it will not progress at this time. 07/07/2026 Awaiting decision on CMP375 | N/A | NESO | 2022-03-14 | High impact on all Users who pay TNUoS charges, NESO and Onshore and Offshore Transmission Owners | N/A | CUSC (CMP315/375) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | N/A | N/A | TBC | 2026-07-29
PM0126 | CUSC Modification 'Transmission Impact Assessment Process' | This Modification seeks to facilitates an aggregated assessment that mitigates the need to assess individual smaller connections making it easier for all parties to get an accurate view of any works required | Implemented | The Panel met on 29 June 2022 and this was presented as a draft modification (01/11/2022) The Panel met on 26 October 2022 and agreed that PM0126 is approved 'in principle' and a formal approval will be sought once Ofgem publishes a decision on CMP298 and CM080. (04/09/23) Panel decision due this month, STCP's will then be presented to STC panel. (06/10/2023) CMP298/CM080 decision push out to 20 October. STCPs can then be presented Panel (30/10/2023) Still waiting for Ofgem decision on CMP298/CM080 which has bee moved out until 16 November. (21/11/2023) Still waiting for Ofgem decision on CMP298/CM080 which has been moved out until 30 November 2023. (02/02/2024) Presented to January Panel, Awaiting approval confirmation. (19/02/2024) Confirmation of approval to be granted at February 2024 Panel (03/04/2024) Still outstanding discussion to be had. Panel to approve offline once meeting has taken place to address concerns. (20/05/2024) Still awaiting confirmation that all outstanding action have been completed. Panel to approve offline once confirmation received. (03/06/2024) All actions completed and STC Panel members agreed STCP can proced to implementation. (14/06/2024) STCP implemented on 11 June 2024. | 0 | NESO | 2022-05-17 | Medium Impact on Transmission Owners, Transmission System Operators | N/A | CUSC CMP298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | N/A | N/A | 2024-06-11
PM0127 | Improving TNUoS Predictability through increased Notice of the Target Revenue & Inputs used in the TNUoS Tariff Setting Process | This modification seeks to makes changes to a number of STCPs which are required to facilitate CUSC modifications CMP286 and CMP287. The aim is to improve TNUoS predictability by increasing the notice of the Target Revenue and inputs used in the TNUoS Tariff Setting Process | Withdrawn | The Panel met on 31 August 2022 and this was presented as a draft modification [30/09/2022] The Panel met on 28 September 2022 and agreed that PM0127 is approved 'in principle' and a formal approval will be sought once Ofgem publishes a decision on CMP286/287 04/09/23 Will go back to Panel once CMP286/287 are approved, both have been sent back from Ofgem and awaiting to resume workgroup. (06/10/2023) Proposal for STCPs going to October Panel in relation to CMP286. (30/10/2023) Proposer to share STCPs with Authority re Materiality. These will be brought back to Panel (21/11/2023) Proposer to present STCPs at November STC Panel for approval. 01/12/2023) Approved at November Panel, will be implemented along with associated modifications. (0202/2024) Awaiting associated Proposal to be completed. (03/04/2024) Associated modification (CMP286) issued to Authority for decision, expected decision date 26 April 2024. (30/04/2024) Associated modification (CMP286) issued to Authority for decision, date pushed out to 03 May 2024. (07/045/2024) Associated modification (CMP286) decision received by the Authority 3 May 2024 rejecting CMP286. (20/05/2024) To be discussed at May STC Panel. (03/06/2024) This modification relates to CMP286 that was rejected by the Authoity in May 2024, STC Panel members agreed this STCP can be withdrawn. (14/06/2024) Proposal withdrawn at 29 May STC Panel 2024. | N/A | NESO | 2022-08-09 | High Impact on the NESO, Transmission Owners, Suppliers and Consumers | N/A | CUSC (CMP286/287) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | TBC | N/A | N/A | 2026-07-29
PM0133 | Network Services Feasibility Studies | It is proposed to specifically define the pathfinder feasibility process within STCP17-1 in a similar manner to the connection feasibility study process. This will include the process to be followed, all parties’ responsibilities alongside standardised terms and conditions. | Implemented | Agreed at STC Panel 28 June 2023, Meeting to take place to agree necessary changes, proposal will then be presented back to STC Panel , [04/09/23] Meeting in September to discuss Proposal, (05/10/2023) Meetings still taking place., (30/10/2023) Discussions taking place regarding materiality. Not expexcted back to panel until the new year. (21/11/2023) As above, (0202/2024) Discussions still ongoing, (30/04/2024) As above, (22/07/2024) Discussions ongoing., (03/09/2024) Discussions still ongoing, (22/11/2024) Proposal to be presented to December STC Panel., (05/02/2024) Included in Panel Papers for 11 December STC Panel meeting. (06/01/2025) Presented to STC Dcemeber Panel, more work is needed. The Proposer to bring STCP proposal back to Panel., 29/01/2025 Waiting for proposal to be re-presented to STC Panel.(06/03/2025) The proposer is to decide how to progress with this Proposal and re-present it to Panel, no date has been confirmed yet. (03/08/2025) An updated draft proposal was presented to August STC Panel, the Techincal Code representative is to contact the Authority in relation to materiality and then present a formal Proposal to the next STC Panel. 29/10/2025 The Panel did not agree to implement the modification. The Proposer was asked to liaise with Panel members and return to Panel once their concerns have been resolved. 29/04/2026 - Proposal discussed at April STC Panel. Panel decision....[TBD] 07/05/2026 - Panel Approved for implementation Implemented on 14 May 2026 | 0 | NESO | 2023-06-13 | Medium Impact - Transmission System Operator, Transmission Owners | N/A | None | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | 2024-12-11 | NA | NA | 2025-01-10 | 2026-07-29
PM0134 | Introducing Competitively Appointed Transmission Owners & Transmission Service Providers | This modification aims to introduce the concept of Competitively Appointed Transmission Owners (CATOs) to the STCPs to enable Onshore Network Competition for the design, build and ownership of Onshore Transmission assets. | Implemented | 13/12/2023 Proposal approved at STC Panel as there is no materiality. This proposal will be implemented along with the STC CATO Modifications. (22/07/2024) to be discussed at July 2024 STC Panel (05/08/2024) Discussed at July Panel, action taken by the Authority to arrange a call with ESO to clarify who will make the decision on this change. (03/09/2024) The Authority agreed that this modification would be added to the decision they make for all STC CATO modifications, Awaiting agreement for GC0159 to be shared with Authority along with CM086 & CM087, PM0134 and PM0136 (plus associated CUSC and SQSS modifications) (07/04/2025) On 25 March 2025, the Authority approved the Original solution. Implemented on 08 April 2025. | 0 | NESO | 2023-12-01 | Through the introduction of CATO arrangements, CATOs will become additional Transmission Owners (Tos) whose assets will add to the National Electricity Transmission System (NETS). CATOs will work alongside the NESO and Pre-existing Transmission Owners (PTOs) | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | 2025-03-25 | 2025-04-08
PM0136 | Introducing Connections process to facilitate Competitively Appointed Transmission Owners | This modification is being raised to align the STCP Procedures affected by the (P)TO-(CA)TO Connections process as defined in CM087 which facilitates the introduction of Competitively Appointed Transmission Owners (CATOs) to the STC. This will enable Onshore Network Competition for the design, build and ownership of Onshore Transmission assets. | Implemented | (13/12/2023) Panel and ESO agreed materiality of the draft version of PM0136 (23/04/2023) Authority view requested as to whether the Authority or Panel provide the decision for PM0136 (10/05/2024) The Authority responded to the Proposer noting matieriality of the changes but that the Authority were happy for Panel to decide on the change (05/07/2024) STC Panel Chair to contact the Authority to clarify the position on Panel making the decision following Panel feedback. (22/07/2024) to be discussed at July 2024 STC Panel (05/08/2024) Discussed at July Panel, action taken by the Authority to arrange a call with ESO to clarify who will make the decision on this change. (03/09/2024) The Authority agreed that this modification would be added to the decision they make for all STC CATO modifications Implemented 15 April 2025 | 0 | NESO | 2023-12-02 | Transmission Owners (TOs) whose assets will add to the National Electricity | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | To be implemented along with other CATO modfications (CM086/CM087)
PM0140 | Housekeeping changes following the implementation of PM0135 | The modification will make minor housekeeping changes to align STCP19-3 following the implementation of STCP Modification, PM0135 | Implemented | (20/05/2024) New STCP to be presented at May STC Panel (03/06/2024) STC Panel members approved the Proposal and agreed to the implementtion date of 13 June 2024 (14/06/2024) Modification implemented 13 June 2024. | 0 | NESO | 2024-05-07 | NA | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | TBC
PM0141 | Incorporating a revised outage change code list in STCP 11.2 Appendix 5 | Remove duplicates of the Outage Change Codes contatined with STCP 11-2 appedix 5 and include new codes to reflect the reasons for the outage change. | Implemented | (06/11/2024) Awaiting Panel approval., (22/11/2024) Update to December Panel to confirm approval and then implementation. (06/01/2025) Withdrawn from December STC Panel, will goto Janauary 2025 Panel instead., Approved at January STC Panel, implementation date to be confirmed with Proposer.(01/05/2025) Implementation date of 28 May 2025 agreed with the Proposer.05/06/2025 Proposer confirmed tht the implementation date of 28 May is to be delayed. An update on the latest postition will be shared at the July STC Panel. (03/09/2025) an Implemention date of 23 July 2025 was agreed by the Proposer and STC panel were updated. Implemented 23 July 2025 | 0 | NESO | 2024-09-25 | Users of the eNames outage planning database including TO's OFTo's DNO's DCC's and Generators | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | 2024-12-11 | NA | NA | TBC
PM0142 | Application of Gate 2 Criteria to existing contracted background | This Modification proposes to introduce a time-limited, one-off, Procedure to facilitate the introduction of CUSC Modification CMP435 | Implemented | (06/01/2025) December Panel formally agreed that this draft STCP Proposal did have materialityand the Proposers would write to the Authority, who will confirm in writing whether STC Panel are to submit a recommendation or determination vote once the official proposals have been presented to January 2025 STC Panel, (07/02/2025) Formal Proposal received on 6 February and will be presented in a Special Panel on 14 February 2025. 06/03/2025) Presented at Feburary Special Panel and was issued to Ofgem to make a decision along with other Connection modifications. 05/06/2025 Authority Decision recieved 16 May confirming approval to implement with connection modifications. Implementation date 10 June. | 0 | NESO | 2024-02-06 | Transmission System Operators, Transmission Owners (including OFTOs) | NA | CMP435 | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | 2025-06-10
PM0143 | Implementing Connection Reform | A wholesale revision to the connections process has been proposed under CUSC modification CMP434 and STC modification CM095, along with additional changes outside of the codes. This modification aligns the STCPs with the changes proposed under CM095 and the wider connections reform work. | Implemented | (06/01/2025) December Panel formally agreed that this draft STCP Proposal did have materialityand the Proposers would write to the Authority, who will confirm in writing whether STC Panel are to submit a recommendation or determination vote once the official proposals have been presented to January 2025 STC Panel, (07/02/2025) Formal Proposal received on 6 February and will be presented in a Special Panel on 14 February 2025.(06/03/2025) Presented at Feburary Special Panel and was issued to Ofgem to make a decision along with other connection modifications 05/06/2025 Authority Decision recieved 16 May confirming approval to implement with connection modifications. Implementation date 10 June. | 0 | NESO | 2024-02-06 | Transmission System Operators, Transmission Owners (including OFTOs) | NA | CMP435, CMP434 | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | 2025-06-10
PM0144 | Digital Communication System Integration | Currently digital communications between transmission system operators (TOs) and NESO are limited to emails only. We propose expanding this to include emails and other appropriate forms of digital communication. | Implemented | (06/01/2025) The Proposer recevied feedback from Panel members in readiness for submitting the official Proposal., 20/01/2025 Proposal submitted to January STC Panel and approved. 10/04/2024 This proposal was waiting the implementation of CM0101, which was completed on 28 March 2025. PM0144 was implemented 17 April 2025. | 0 | NESO | 2024-12-03 | Transmission System Operators | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | TBC
PM0145 | Digital Communication System Integration | Currently digital communications between transmission system operators (TOs) and NESO are limited to emails only. We propose expanding this to include emails and other appropriate forms of digital communication. | Withdrawn | This proposal was withdrawn and will be combined with CMP0144 after Proposers discussions (3 January 2025) | N/A | Harriet Eckweiler | 2024-12-03 | Transmission System Operators | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | TBC | 2025-04-22
PM0146 | ​Emergency Control Centre Requirements | Adjustment to the phrasing around the IT architecture required at the Emergency Control Centre, to include the option to meet the requirements with ‘capabilities’ instead of just ‘systems’. | Implemented | (07/02/2025) This Proposal was submitted and will be presented to Panel in February. (26/02/2025) Approved at February STC Panel. Implmented 12 March 2025. | 0 | National Grid | 2024-01-21 | Low impactong on ​Transmission Owners, Transmission System Operators | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | N/A | N/A | N/A | NA | NA | NA | 2025-03-12 | 2025-04-22
PM0147 | RMS and EMT Model Sharing Process (STC 122 issues 01) | Introduce a new procedure to govern the interactions between The Company and relevant Transmission Owners (TOs) relating to the exchange of RMS and EMT models | Pending Authority Decision | (14/05/2025) Proposal to be presented to May STC Panel for approval. (05/06/2025) During May STC Panel the Proposer advised that futher comments had been received in relation to the proposal, these were discussed and it was agreed that PM0147 would be prepresented to June STC Panel for approval once the comments had been considered. 07/07/25 On hold until GC0168 have completed a solution. 25/03/26 To be presented at April 2026 STC Panel Meeting. 29/04/2026 - Proposal discussed at April STC Panel. Panel decision....[TBD] Panel agreed Materiality. PM0147 was sent to the Authority on 16 July 2026 for a decision. | N/A | NESO | 2025-05-06 | Transmission System Operator, Transmission Owners | N/A | STC097/GC0168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2026-07-16 | NA | To be implemented along side CM097 | 2026-07-29
PM0148 | STCP Consequential Modification for CMP447: Removal of designated strategic works from cancellation charges/securitisation | This proposed change to STCP 19-2 supports the long term implementation of CMP447, which aims to exclude certain non-generator- dependent transmission works from cancellation charges. | Implemented | 30/09/2025 Proposal approved at STC September Panel will be implemented in line with CMP447 which will be later in the year. Legal text to be amended slightly before implemented. PM0148 implemented in line with CMP447 on 21 January 2026. | 0 | NESO | 2025-09-05 | Suppliers and Generators | NA | CMP447 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2026-01-21 | 2026-07-29
PM0149 | Reconciliation – Change to STCP 19-2 | ​This modification proposal form aims to update STCP 19-2 7.2.1 to align with CUSC Section 2.14.3 (c) to allow a longer reconciliation period for Transmission Operators when required. | Implemented | 29/10/2025 The Panel unanimously agreed that PM0149 can proceed to implementation. (08/12/2025) Implemented 12 November 2025 | 0 | NESO | 2025-09-11 | Low Impact on Generators, NESO, and Transmission Owners | NA | CUSC Section 2 2.14.3 (c) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10 Business Days after panel decision
PM0150 | Due Date for Monthly Payments to Transmission Owners (TOs) | Minor change to due dates for monthly payments to TOs, to ensure there is always one Business Day between the payments received by National Energy System Operator (NESO) from Connection and Use of System Code (CUSC) users for Transmission Network Use of System (TNUoS) and Connection Charges and the payments made by NESO to TOs for general system charges and site-specific charges. To note: This is a consequential System Operator Transmission Owner Code (STC) Procedure Modification (PM) to CM0104. | Implemented | 29/10/2025 The Panel unanimously agreed that PM0150 can be implemented in line with CM0104. (08/12/2025) Implemented 31 October 2026 | 0 | NESO | 2025-10-03 | Low Impact on Transmission Owners | N/A | CM0104 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | In line CM0104 (01/04/2026)
PM0151 | Introducing Competitively Appointed Transmission Owners to TO Lists on all Definitions | This modification adds Competitively Appointed Transmission Owners to lists of TOs in all Procedures Definitions | Implemented | 29/10/2025 The Panel unanimously agreed that PM0151 can proceed to implementation. The Panel noted that due to the number of Legal Texts to be updated, the Implementation Date will be 20 Business Days after Panel decision. (08/12/2025) Implemented 26 November 2025 | 0 | NESO | 2025-10-15 | Low Impact on Transmission Owners, Competitively Appointed Transmission Owners | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Business Days after panel decision
PM0152 | STCP Legal Text Rectifications January 2026 | This Proposal seeks to make minor corrections of errors or omissions identified from previous implementations to a number of STCPs | Implemented | (28/01/2026) The Panel unanimously agreed that the changes proposed in PM0152 are not material and agreed to the implementation next steps, noting that implementation will be on 12 February 2026. | 0 | NESO | 2026-01-09 | Low impact​ Transmission Owners, Competitively Appointed Transmission Owners | N/A | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | NA | N/A | N/A | NA | NA | 2026-02-12 | 2026-07-07
PM0153 | PM0153: System Access Reform. Emergency Return to Service (ERTS): Profiling Review. | This modification revisits the criteria for recalling of circuits with longer Emergency Return to Service (ERTS) to help secure the transmission system during the winter periods. It mandates the Winter Risk Policy Form to document system margins, constraints, mitigations, and recall plans. By aligning with proven operational methods, this change enables to progress more winter outages securely, supporting the Transmission Acceleration Action Plan and 2030 clean-power goals. | Implemented | (25/02/2026) The Panel unanimously agreed that changes in PM0153 are material. However, they also agreed that the Legal Text needs further revision and that this work must be done before formal approval of the modification can take place. 29/04/2026 - Proposal discussed at April STC Panel. Panel decision....[TBD] Implemented on 14 May 2026 | 0 | NESO | 2026-02-09 | Low impact on Transmission Owners, Transmission Licensees, Generators, and System Operators. | N/A | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | NA | N/A | N/A | NA | NA | 2026-05-14 | 2026-07-29
PM0154 | PM0154: STCP16: System Access Reform. Investment Planning Process - Data on Constraint Costs. | The proposal seeks to amend STCP 16-1 Paragraphs 4.2.7 and 4.2.8 aims to enhance investment planning for UK electricity transmission projects. Key improvements include clearer data requirements, incorporation of constraint costs, defined response times, and a streamlined Project Listing Document (PLD) in Appendix C. These changes promote efficiency, transparency, and regulatory compliance, supporting cost-effective, timely delivery and system reliability, while aligning with national decarbonisation goals and benefitting both industry stakeholders and consumers. | Implemented | (25/02/2026) The Panel unanimously agreed that the modification is non-material and agreed to the implementation next steps, noting that implementation will be in 10 Business Days postapproval. Implemented on 11 March 2026 | 0 | NESO | 2026-02-09 | Impacts: Low impact on Transmission Owners, Transmission Licensees, Generators, and System Operators. | N/A | NA | NA | NA | N/A | N/A | N/A | N/A | N/A | NA | NA | N/A | N/A | NA | NA | 2026-03-11 | 2026-07-29
PM0156 | PM0156: Consequential changes to STCP13-2 arising from CM093 | This modification makes consequential updates to STCP13-2 to align it with CM093 (and CMP417), extending relevant User Commitment Methodology principles to Final Sums Users and maintaining clarity and consistency across the STC framework. | Awaiting implementation | 29/04/2026 - Proposal raised at April STC Panel. Panel decision....[TBD] 07/05/2026 - Panel approved for implementation. In line with CM093 | N/A | NESO | 2026-04-21 | Low impact on Transmission Owners, NESO, and Users subject to Final Sums methodology. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | In line with CM093 | 2026-08-04
PM0157 | PM0157: Standardisation of Power Flow Metering Polarity | This modification aims to provide a unified standard for Power Flow Metering Polarity when data is sent to NESO. The standard should be presented in a format that includes both a diagram and a detailed explanatory description. This is a subsequent modification to GC0182. | Proposal raised | 29/04/2026 - Proposal raised at April STC Panel. Panel decision....[TBD] 07/05/2026 - Panel approved materiality. 29/07/2026 - Panel agreed to pause PM0157 until the main GC Mod GC0182 has moved further to completion and the Electrical Standard/legal wording has been finalised. | TBC | NESO | 2026-04-21 | High Impact on Onshore and Offshore Transmission Owners. Low Impact on NESO. | N/A | GC0182 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | In line with GC0182 | 2026-08-17
PM0158 | PM​158​: Changes to TNUoS timings Protocols | This change looks to update the process for provision of revenue forecasts from Transmission Owners to NESO for the use in Transmission Network Use of System (TNUoS) Tariff forecast calculations | Proposal raised | 07/07/2026 - Raised at July 2026 Panel. Panel approved materiality. PM0158 was sent to the Authority to confirm materiality and whether the STCP would require an Authority decision. The Authority confirmed the STC Panel should provide their recommendation and be sent to the Authority for a decision. PM0158 will be presented at the August 2026 Panel. | TBC |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-08-17
PM0159 | Managing STCP impacts from CMP471 ‘Interim Connection Date Delay Process Ahead of CMP43 | This modification proposes adjustments to STCP18-8 resulting from the potential approval of CUSC proposal CMP471 | Proposal raised | 07/07/2026 - Raised at July 2026 Panel. Panel agreed that this modification has a material impact. PM0159 is currently paused until CUSC Modificaton CMP471 progresses. | TBC |  |  | High impact - NESO; Onshore Transmission Owners | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-08-17
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The list of impacted parties is being developed by GEMSERV. An update is expected in Nov. Same list will be used by all Code Administrators
Click to open Ofgem Implementation Timetable
Click to view the STC