## STC Panel Actions Log
Action number | Panel raised | Action | Owner | Comments | Due by | Status | Panel closed
01 | Feb 2026 | Revise legal text for the Winter ERTS / outage modification (PM0153 / STCP-related) Work with Lewis (and relevant TO colleagues) to review the current legal text. Specifically: Reconsider whether detailed bullet‑point requirements should sit in the STCP or be referenced via an external process / framework document. Clarify roles, responsibilities, and avoid overly prescriptive wording where a principles‑based approach is intended. Circulate revised wording to panel members offline (ahead of the next panel) for visibility and comfort. | Maria Lopez | Further review of the legal text is being carried out, with engagement with TOs​ Legal to review​ Ofgem to confirm who will approve as per governance | March 2026 | Closed | April 2026
02 | Feb 2026 | Respond to technical clarifications raised by Mike Take away and come back with clear answers on: Policy treatment of demand in relation to winter outages and ERTS > 24 hours. Whether and how the policy applies to offshore transmission assets (OFTOs), including single‑circuit risk scenarios. Responses to be shared with the panel once confirmed with planning teams. | Dozie Nnabuife | Response sent to Panel | March 2026 | Closed | March 2026
03 | March 2026 | Following the presentation of a new timeline for CM097, BS requested a list of the CM097 Workgroup members to be shared with STC Panel. | Chair | Update to be shared during April Panel. | April 2026 | Closed | April 2026
04 | May 2026 | Code Governance to circulate the updated April minutes incorporating Harriet’s comments. | Chair | 11.05.2026 - Minutes for April circulated to Panel members | June 2026 | Closed
05 | May 2026 | Code Governance to send panel members the relevant SDS guidance/materials, including the links shared by DKC. | Chair | 20.05.2026 Code Governance sent Panel SDS guidance materials and links | June 2026 | Closed
06 | May 2026 | Code Governance to circulate a list of current live STC modifications ahead of the next meeting. | Chair | 20.05.2026 Code Governance sent Panel list of current live STC modifications | June 2026 | Closed
07 | May 2026 | Panel members to review the live STC mods against the new SDS prioritisation framework, considering; alignment with the STS, importance, complexity, and whether each should be treated as standard or high priority. | All | 20.05.2026 Prioritisation framework sent to Panel to consider alighment with the STS. To be discussed at next Panel Meeting | June 2026 | Open
08 | June 26 | Double check CN email comments/edits on May panel minutes, ensure they are addressed, and recirculate the updated minutes to all panel members for visibility ahead of the next meeting. | KSH/FM | Minutes updated to reflect comments and circulated with Panel. | July | Open
09 | June 26 | Speak with the connections team to provide an update (written or verbal) on the resolution of the final sums issue and why a modification is no longer needed, ideally at the next panel meeting. | CN |  | July | Open
10 | June 26 | STC Prioritisation Framework Circulation: Circulate the updated STC prioritisation framework and homework to panel members after the CUSC Panel. | FM | Circulated to Panel | July | Open
11 | June 26 | Panel members to Submit individual evaluations and rationale for SCC prioritisation homework to the Panel Secretary by July 15th, to be tallied and included in papers for the July panel meeting. | Panel Members | Update to be provided at Panel | July 15th | Open
12 | June 26 | Proposal Forms Update: Share the updated proposal forms for SCC and SCCP modifications reflecting the new prioritisation requirements and links to SDS guidance with panel members. | Code Governance | Update to be provided at Panel | July | Open
13 | June 26 | CMP471/STCP Modification Timeline Coordination: Engage with the CMP471 work group to ensure the proposal timeline for the related STCP modification (PM159) aligns with what was agreed in the meeting and schedule an extraordinary panel meeting if needed. | Code Governance | Update to be provided at Panel | July | Open